## Action Items - AMDB
Num | Assignee | Action | Due date | Status | Notes
1 | Pierre | Inform what dates he will be available for face-to-face meeting in February. | 2011-10-01 | Closed
2 | Beby | Confirm that Airbus can host Feb 2012 meeting | 2011-11-01 | Closed
3 | Marcin | Collect data showing whether computing taxiway holding position direction from existing data yields sufficient results. | 2012-02-01 | Closed
4 | Marcin | Draft proposed content for document for new attribute indicating direction of dashed portion of hold line. | 2012-02-12 | Closed | Group agreed on proposal that will be made for DO-272D/DO-291C.
5 | Marcin | Provide detailed requirements and draft document proposal for taxiway intersection attributes. | 2011-12-01 | Closed | Withdrawn (can use ASRN for desired functionality)
6 | Christian | Obtain needed model files for UML diagrams and provide to group. | 2011-10-01 | Closed
7 | Brian | Update UML model and XML schema | Ongoing | In work | In progress
8 | Marcin | Create plan for development of committee-controlled BXML encoder compatible with -2 schema. | 2013-03-01 | Closed | Options: 1. Use an existing supplier's encoder to generate the example BML file (SESAR project?) 2. Have text XML only as example, and don't include BML
9 | Carlos | Update example airport XML text files (dependent on action 51 - can SESAR provide examples)? | December 2014 web meeting | Open | SESAR cannot provide "faked" airport. Carlos volunteered to create new example airport (first compliant to -2, then later compliant to -3)
10 | Peter Grau | Create acronym list to add as an appendix. | 2011-12-01 | Closed
11 | All | Provide polynomials and conversion algorithms to use for Bezier curves. | 2012-03-09 | Closed
12 | Brian | Create diagram showing “clamping” of temporal attributes to cycle effectivities and the effect on gathering. | 2012-02-12 | Closed | clamping.vsd - update per Dec. meeting comments
13 | Brian | Update all UML diagram pictures in the document. | 2012-02-01 | Closed
14 | Pete Grau | Have adb.xsd file placed in http://www.aviation-ia.com/aeec/SupportFiles/816-1/adb.xsd | 2011-12-01 | Closed
15 | Pete Grau | Set up URL for -2 schema and example airport files (http://www.aviation-ia.com/aeec/SupportFiles/816-2/adb.xsd) | 2012-02-01 | Closed
16 | All | Identify any DO-291 attributes that are not included in ARINC 816 that are now needed. | 2012-02-12 | Closed | See sheet 2 of this file (Attributes)
17 | Brian | Determine if BridgePointSet facet can impose a multiple of 2. | 2011-12-01 | Closed | <assertion test="$value mod 2 = 0" />
18 | Beby | Add figure showing example of Bezier curves drawn using two different resolutions (for example, one with 8 segments and another with 40 segments). | 2012-03-09 | Closed
19 | All | Describe examples of temporal changes that could impact containers. | 2012-02-12 | Closed | container temporality examples.vsd - update per Jan. 17 comments
20 | Carlos | Update example airport XML binary files (dependent on action 51 - can SESAR provide examples)? | December 2014 web meeting | Open | PSW will generate the example BML file, but not share tool with ADB committee
21 | Peter Grau | Scrub the glossary (and acronym list) to make sure all terms are used in the document (e.g., Data Product Specification). | 2012-02-12 | Closed
22 | Marcin | Draft proposal to add optional subelement for AsrnNode to define list of associated edges. | 2012-02-12 | Closed | Added EdgeReferences subelement to document and model.
23 | Brian | Draft proposal for new attribute for DO-272 TaxiwayElement feature that lists all IDs associated with a taxiway intersection (e.g., like idbase). | 2012-12-01 | Closed | See Brussels debrief slides
24 | Brian | Update section 1.6 with new wording related to support files. | 2012-02-12 | Closed
25 | Marcin | Fix BML files for -0 and -1 example airport support files. | 2013-01-01 | Closed | Supp 0 has been updated
26 | John | Draft words for Appendix A. | 2012-02-12 | Closed
27 | John/Jeppesen | Provide files for ICAO sample airport (what is available - shapefiles, XML, DO-291 format, A816-0 format?) | 2013-03-01 | Closed | No AMDB exists; paper chart only in Doc 8126 - does not offer any value beyond existing example
28 | Marcin with data provider approval | Provide metrics to assist with coordinate data type decision: what is penalty of using a Count rather than a 16-bit int? This is for BXML encoding only. | 2013-09-01 | Closed | Got metrics from Marcin and Patrick. At least 25% reduction in file size going to 16-bit integers.
29 | Marcin/Kaushik (Rockwell Collins) | Draft proposal for RTCA SC-217 to resolve issues with PaintedCenterline feature capture rule for unidirection runways (need to ensure PaintedCenterline feature is always captured using both runway ends to yield good runway container results in A816). Also propose that DO-291 is consistent with DO-272 in terms of identifying runway threshold suitability. | 2013-02-01 | Closed | See Brussels debrief slides
30 | Brian | Investigate why in model the AnchorPoint subelement can have 0 instances for Container class. | 2013-01-01 | Closed | There were two Container diagrams in the model…deleted old one. Changed multiplicity to 1 and replaced diagram in draft document.
31 | Brian | Draft presentation to RTCA SC-217 to discuss taxiway intersection identifier issues and how it affects containers in ARINC 816 (TaxiwayElement feature for intersection polygons can only belong to one container, and not to others that also "belong" to that intersection). | 2013-02-01 | Closed | See Brussels debrief slides
32 | Thales | Determine method for determining which sides of a TaxiwayElement need to have bridge points that does not require "data origination." | 2013-03-01 | Closed | SC-217 is revising capture rules
33 | Boeing Airbus GE Honeywell Rockwell Collins | Propose concepts for data packaging enhancements (e.g., package each feature is a separate file) Assumptions: - Not all systems necessarily use file systems or sophisticated dataload mechanisms - Need CRC checks on entirety of what was loaded as well as for each individual file - Other applications beyond the one that draws the airport map need access to AMDB data (an even smaller, or different, subset) - Approach for AMDB could be applied to other XML DBs Goals: - Reduce dataload time - Reduce memory footprint (storage and run-time/local memory) - Reduce network latency (transmitting files) - Reduce application processing time - Allow interoperability (same DB used on multiple systems, the dataload/application software filters out data it does not need) | 2013-03-01 | Closed | See "Database Packaging discussion.doc"
34 | Christian Brian | Determine if gzip would still be beneficial after BXML optimizations | 2013-10-07 | Closed | Greg produced a dataset using 16-bit integers; gzip showed savings with integers, but not sure if it was using 16 or 32-bit integers. So the answer is yes, it would still be beneficial. Christian sent binary file to Brian to analyze. Brian confirmed it used 16-bit ints for coordinates (except AnchorPoints still used float) In general, gzip compresses ints much better than floats.
35 | Pete Grau | Create and distribute draft -3 document | 2013-01-01 | Closed | Distributed on Jan. 2, 2013.
36 | Thales | Create proposal for eliminating use of object ID references in containers | 2013-03-01 | Closed | Still need object ID references in containers - used by existing application
37 | Beby | Create proposal for eliminating major/minor taxiway containers and enhancing taxiway feature containers | 2013-03-01 | Closed | Changed default rule for major/minor determination (validate per action 53) in Section 2.6.1.5. Added attribute surfacearea to Taxiway Feature Container definition in 4.2.4.1.
38 | Jeppesen Lufthansa Systems GE Honeywell Rockwell Collins | Create proposal for adding 3D coordinates Goals: Minimize the impact of adding 3D to the spec on the size and performance of AMDBs used by applications who don’t want 3D (i.e., optional inclusion) - make inclusion of 3D optional, allow both in a given dataset Considerations: Impact of 3D points on projected coordinates - don't include z coordinate in projection Does AMDB data whose Z coordinate aligns with terrain need to have its own potentially conflicting Z coordinate value (could be surveyed differently)? - add text in 2.5.2 that warns about this, but don't try to resolve on data side, request "void" geometries or terrain mesh in DO-272 Should this only apply to vertical structure features? No, applies to all features Determine how, if possible, to align with terrain and obstacle database activities. - Add commentary to 2.5.2 and propose new content to DO-272 Interior points for different elevations within a geometry as opposed to just the outline with a height applied uniformly across the whole geometry? - Add commentary to 2.5.2 and propose new content to DO-272 | 2013-10-07 | Closed | Rockwell Collins shared some internal discussion conclusions: Z coordinates not just needed for outlines, it might be needed for interior points as well, or might increase number of outline points needed (apply vertical resolution requirements to Z coordinates) Consensus approach reached in Phoenix meeting, actions 66 and 67 created for implementation
39 | Beby | Check if somebody at Airbus can maintain the UML model. | 2013-01-01 | Closed | Not possible at this time
40 | Brian | Reported by Rockwell Collins: In 3.1.2, The Elements list for ConfDB does not contain SizeReport and FeatureList. | 2013-01-01 | Closed | Added SizeReport and FeatureList to Elements section of 3.1.2 in draft document.
41 | Brian | XSD file has no content for AsrnEdge feature (no BezierCurves content) | 2013-03-01 | Closed | Added diagram for AsrnEdge and it now shows as having Lines and BezierCurves as subelements.
42 | Brian | XSD file has no content for AsrnNode feature | 2013-03-01 | Closed | AsrnNode now as Points and EdgeReferences listed as subelements.
43 | Beby | Do the BezierControlPoint subelements need to be in a particular order? | 2013-03-01 | Closed | Added order rules in 4.3.1.18, and added exception to typical coordinate ordering in 5.3.2. Clarified general coordinate rules in 5.3.1.
44 | Marcin | Fix BML files Supplement 1 example airport support files. | 2014-05-19 | Closed | Updated files provided to Pete to get onto ARINC website.
45 | Brian | Draft presentation to RTCA SC-217 to discuss adding bridge points. | 2013-02-01 | Closed | Brussels discussion: - Go with Option 1 (new line feature) if we decide to add it - Ask Airbus/Thales to clarify need & requirements for capturing bridge points
46 | Brian | Within <xsd:complexType name="Cycle">... </xsd:complexType> element there is a <xsd:element name="FeatureList">... </xsd:element>. FeatureList should not be a child of Cycle. | 2013-03-01 | Closed | FeatureList is no longer listed as a child of Cycle.
47 | Brian | EdgeReferences type is not defined by the schema at all, but IdnumberReference is. | 2013-03-01 | Closed | EdgeReferences is now added and listed as a child of AsrnNode
48 | Brian | The sorting order for the AMDB subelements in the schema is incorrect. (Containers should be last, others are case-folded based on character set) | 2013-10-07 | Closed | Limitation of EA version; post-processing of XSD needed. There is a way of ordering them, but need to use UML to XML profile that comes with EA, and the XSD built using this profile changes the class diagrams. "Tagged values" can hold value for placement/ordering. Greg sent out example; come to conclusion in Phoenix. Corrected by hand for now.
49 | Brian | Fuel is incorrectly specified as a subelement of ParkingStandArea instead of an attribute in the schema | 2013-03-01 | Closed | Fuel is now listed as an attribute rather than an element
50 | Brian | Attribute edgetype is not specified as an attribute for AsrnEdge in the schema | 2013-03-01 | Closed | Added edgetype attribute to AsrnEdge feature definition in model.
51 | Beby | Find out if SESAR project 9.31 will be able to share their prototype -2 XML and BML files (including validation of BML files) for use to use as examples, or at least if they will encode our own example for us. Also see if they can provide their A816-0 compliant files from 2012. | 2014-05-19 | Closed | SESAR cannot help, PSW has taken over all aspects of example airport files.
52 | Patrick | Lufthansa Systems will provide data file to Marcin (use airport with large coordinate values) | 2013-03-15 | Closed | Provided to Marcin in July
53 | Christian Patrick | Provide data to validate proposed major/minor taxi container criteria (determine what taxiways have surface area greater than or equal to than mean at a varietry of airports) | 2013-10-07 | Closed | Christian presented data. The group agreed that the default criteria (surface area > mean) is acceptable.
54 | Jean-Etienne | Check to see if Anchor Lines provide needed functionality rather than splitting up taxiways that curve/loop (e.g. A and B at KORD) into multiple containers. | 2014-05-19 | Closed | Jean-Etienne confirms this is okay.
55 | Jason | Formalize proposal for Option 3 (embedded file references in AMDB) in "Database Packaging discussion.doc" | 2013-10-07 | Closed | Jason presented slides in PHX
56 | Marcin | Formalize proposal for Option 5 (treat AMDB as a stream) in "Database Packaging discussion.doc" | 2013-10-07 | Closed | Marcin presented slides in PHX
57 | Brian | Formalize proposal for adding use of IndexTable in BXML to provide indexing to feature types | 2013-10-07 | Closed | In light of XML E&C group decision to go with EXI, and discovery that EXI does not support indexing very well, there are a couple of questions: Since indexing will need to be built-in to database content, should we just create a new ConfDB element to support this, which can be used with either BXML or EXI encoding? This may be more compatible with what we are pursuing for TODB as well. If not, and we use the BXML IndexTable concept for BXML encodings, what do we do for EXI?
58 | Brian | Fix model issues: 1) The xsd:schema targetNamespace was mistakenly changed to indicate 816-1, Also the schema has a forward slash at the end of the namespace. According to the spec, that shouldn't be there. 2) The enumeration of AprontypeType seems to follow a different convention than the rest of the file 3) Points should be before EdgeReferences in the AsrnNode sequence. 4) Lines and BezierCurves of AsrnEdge features should each have maxOccurs="1" instead of maxOccurs="unbounded" 5) AMDB sequence order is still incorrect (I'm assuming this is because we don't have an available model maintainer that is experienced with EA) I'm wondering if it has anything to do with how things are defined. Notice that all of the newer features start with <xsd:element name="..." type="..." ... All of the original features start with <xsd:element ref="..." ... I'm not sure what the distinction is there, but maybe that has something to do with it. Regardless, that format is inconsistent. | 2014-05-19 | Closed | Fixed all 5 issues
59 | Brian | Fix model issues: 6) Order of elements in the Figure 3-1, Section 3.1.2, and in the schema all are different. (Plus the figure is missing VersionCompliance) Think the order should be VersionCompliance, Airports, CurrentCycle, OldCycle, FeatureList, SizeReport. (I wouldn't care if FeatureList and SizeReport were moved after VersionCompliance or Airports, I just don't think they should be between the CurrentCycle and OldCycle) 7) Per your response to my previous email about AnchorLines, there are several locations where the spec and schema don't agree on specification of required sub-Elements: AnchorLines, AnchorPoints, BridgePoints 8) RunwayThreshold is missing lat and long attribute definitions 9) There are several places where it seems that some partial xml tags got encoded as part of xsd:documentation content. It looks something like this: &lt;/xsd:documentation&gt; &lt;xsd:appinfo&gt;AttributePosition="1"&lt;/xsd:appinfo&gt; 10) HelipadThreshold is missing the elev attribute in the schema | 2013-10-07 | Closed | Fixed #8, #9, and #10 #6 and #7: have updated by hand for now
60 | Brian | Fix model issues: Are AnchorPoints always optional? There is a UML diagram for Polygons that shows they are optional for PolygonGeometry elements. A similar diagram exists for a generic Container. Other than PolygonGeometry and Container, AnchorPoints are Elements of StandGuidanceLine features as well. There's no UML diagram or anything indicating it is optional (except in the schema). I think this leads to a larger issue. We are not always clear in the spec when Elements of a feature (or nested sub-Elements) should be considered optional, or how they should be ordered within the feature. Is it intended that we rely heavily on the schema for this information? | 2014-05-19 | Closed | Changed AnchorPoints multiplicity to 1 for PolygonGeometry (it is already 1 in Container). Not sure yet the best way to show AnchorPoints connection to StandGuidanceLine feature in a diagram…the connection is there in the XSD.
61 | Brian | The schema specifies that these attributes (MetricType, edgetype, edgederv, style) are encoded as strings, while the spec states that they should be SmallNum (or ShortNum for special values): <xsd:simpleType name="MetricTypeType"> <xsd:restriction base="xsd:string"> <xsd:enumeration value="0"/> ... <xsd:simpleType name="EdgetypeType"> <xsd:restriction base="xsd:string"> <xsd:enumeration value="-32764"/> ... <xsd:simpleType name="EdgedervType"> <xsd:restriction base="xsd:string"> <xsd:enumeration value="-32764"/> ... <xsd:simpleType name="StyleType"> <xsd:restriction base="xsd:string"> <xsd:enumeration value="-32764"/> ... According to the spec, all of the instances of these attributes should be SmallNum. | 2013-10-07 | Closed | Changed enumerated values to byte for normal values, short for default values; generated XSD is setting the data type to short. Other enumerations have their type set to "Type" in the XSD, which is a union of unsignedByte and short. I think that "Type" is the way to go, but very poorly named. Is there any impact to changing this name to "enumType" or something more descriptive? I have updated these 4 attributes to use "Type" data type.
62 | Airbus | Draft proposal for runway corner points | Nov/Dec telecon | Closed | Came up with proposal to present to Airbus
63 | Christian | Provide aerodrome boundary size (coordinate extent values) metrics to help finalize 16-bit int vs. Count. vs. float discussion for geometric coordinate values. | 2013-10-07 | Closed
64 | All | Come up with concepts for adding indexing capabilities to AMDB. | Nov/Dec telecon | Closed | Came up with proposal to present to Airbus
65 | Carlos | Draft new section 5.3.3 on use of gzip with BXML. Assume each file is a standalone BXML file. | Oct meeting | In work | Reviewed PSW inputs; still 2 items left: Gzip configuration settings, and how to handle external files (if necessary)
66 | Jason | Draft new section 2.5.2 on approach to 3D coordinates | 2014-05-19 | Closed | Will paste Jason's text into draft, still a couple of open issues to resolve in new actions
67 | Marcin | Come up with method for determining "flatness" of an airport for new AirportEntry attribute | 2014-05-19 | Closed | Marcin presented proposal for new attributes; will go to RTCA SC-217 to see if they will add this data (so 816 does not need to originate it).
68 | Jason | Incorporate new 3D subelements into Section 4 | Oct meeting | In work | Jason to Incorporate new figures and lead-in text
69 | Carlos (Performance Software) | Create figure and associated text showing issue that could arise with lines and tesselation points - send to Jason to incorporate into 2.5.2 draft | 2014-05-19 | Closed | Jason did this as part of 3D text action
70 | Performance Software | Slice up some XML files and see how to apply BXML (will contribute to gzip section); assess impact on file size and other measures | 2014-05-19 | Closed | Group decided that level of fragmentation would result it too many files
71 | Brian | Add indexing concept to document | 2014-02-19 | Closed | Presented draft text based on A814 object index table.
72 | Marcin | Propose ConfDB-based file aggregation approach | Oct meeting | In work | Needs to still support one file per airport (status quo) Group generally agreed with Marcin's proposal; Marcin needs to write up some explanatory text for the document Jean-Etienne needs to discuss with engineers at Thales
73 | Brian | Prepare slides to present to Airbus/Thales on runway corner point solution | 2013-12-10 | Closed
74 | Brian | Prepare slides to present to Airbus/Thales on runway anchor point solution | 2013-12-10 | Closed
75 | Christian | Mature document text on criteria for major/minor taxiway containers | Oct meeting | Closed | Group reviewed and approved final proposed text from Christian.
76 | Brian | A.1 The syntax of enumeration values fails the XSD schema validation. <xsd:simpleType name="AprontypType"> <xsd:restriction base="Type"> <xsd:enumeration value="Reserved = 0"/> <xsd:enumeration value="General = 1"/> <xsd:enumeration value="Holding Bay/Penatly Box = 2"/> <xsd:enumeration value="Turnaround = 3"/> </xsd:restriction> </xsd:simpleType> ...(see Sergey's email for the rest)... | Oct meeting | Closed | Fixed in model
77 | Brian | A.2 DO-291B defines the minimal set of attributes for airport features. However, the attribute sets defined in ARINC and XSD are less than the sets defined in DO. The following feature attributes defined in DO-291B are not implemented in ARINC 816-2 for all required features: aslength, aslwidth, ellipse, geound, gsurftyp, hres, idarpt, integr, lighting, marking, material, pendate, piocdate, postdate, radius, revdate, rwyslope, setback, source, tdzslope, vacc, vasis, vres. The surftype attribute is not implemented for FinalApproachAndTakeOffArea and TouchDownLiftOffArea features. AerodromeReferencePoint and SurveyControlPoint are not implemented in ARINC as standalone features. Note that geopnt attribute of the AerodromeReferencePoint can be considered as "implemented" in lat and long attributes of the AirportEntry and that idarpt attribute can be considered as "implemented" in the icao attribute of the AirportEntry. Proposed Solution: Revise the attribute sets in DO-291B and/or ARINC 816-2. Correct XSD if necessary. | Oct meeting | Closed | Drafted text for document explaining that not all DO-291 attributes are carried over into ARINC 816
78 | Brian | A.3 Section 1.7 of the ARINC 816-2 states: 2. The ordering of attributes is not mandated in the XML specification; therefore, the second approach to satisfying deterministic ordering of the metadata (attributes) utilizes the “appinfo” XML schema element, in the attribute definitions, to specify the position of the attribute within the element context. It is coded using the name/value pair “AttributePosition="n",” where n is the attribute position relative to 1. Implementers of this specification can query the ADB XML schema for this information and assemble the attributes in the proper order. However, appinfo XML schema element seems to be encoded incorrectly. According to the W3C Part 1 section 3.15, the annotation schema element can contain appinfo and documentation schema elements. Attribute annotations given in XSD contain several appinfo and documentation tags enclosed in &lt; and &gt; (probably instead of < and >). As a consequence: 1) appinfo is not recognized as a standalone schema element 2) Annotation has one extra documentation closing tag | Oct meeting | Closed | Added text in new section 4.6 to draft
79 | Brian | A.4 XSD specifies all the attributes as “optional” while DO-291B states that some attributes are mandatory and some are optional. Also, since ARINC 816-2 does not trace the ConfDB-related attributes to particular DO-291B feature attributes, it is unclear which ConfDB-related attributes are optional and which are not. It seems evident, however, that all of them are mandatory, but the XSD specifies all of them as “optional” as well. ...(see Sergey's email for the rest)... | Oct meeting | Closed | Group went through all features and determined which are optional and which are conditional.
80 | Brian | A.5 The following attributes and sub-elements are defined in DO-291B and ARINC 816-2 but are not defined in XSD: Feature Type Attribute or Element Name ArrestingSystemLocation Polygons (element) Blastpad Polygons (element) RunwayCenterlinePoint Points (element) HelipadThreshold elev (attribute) As a result, specifying a feature with valid element and attribute will result in validation error. ...(see Sergey's email for the rest)... | Oct meeting | Closed | Fixed in model
81 | Brian | A.8 According to the ARINC 816-2 section 4.3.1.6, the BridgePoints element contains references to the start and end coordinates of the bridge points. This means that the BridgePoints element shall be implemented as the array of whole numbers. The XSD data type definition, however, does not satisfy this requirement: 1) The restriction base is xsd:string and 2) The array of floating-point numbers is mentioned in the annotation. ...(see Sergey's email for the rest)... | Oct meeting | Open | Need to update Supplement 2 model
82 | Brian | B.1 The definition of the fuel attribute given in DO-291B allows using it for multiple fuel types. However, the attribute implementation in ARINC 816-2 and XSD allows a single fuel type only. Definition of the fuel attribute in DO-291B: Types of fuel available. Encoding: If multiple fuel types are available at a stand point, list all of them, separated by commas. Example: Jet A1 and Mogas: 1,3 Definition of ParkingStandArea feature attributes in ARINC 816-2 (section 4.2.7.5): Attribute Description Coding … fuel fuel (DO-291/ED-119) SmallNum … SmallNum is represented by the FuelType enumeration (see below under Proposed Solution 2) ...(see Sergey's email for the rest)... | Oct meeting | Closed | Modeled fuel attribute as an array.
83 | Brian | B.2 RunwayCenterlinePoint is not specified in the Elements list (ARINC 816-2 section B.3 SizeReport and FeatureList are not specified in the Elements list (ARINC 816-2 section 3.1.2) | Oct meeting | Closed | Fixed in model
84 | Brian | B.4 ARINC 816-2 does not clarify whether the ordering of optional attributes shall be defined in the XSD or not. So, it is unclear should appinfo schema elements be specified for optional attributes. Currently optional attributes do not have associated appinfo schema element. The only exception is the thrtype attribute of the RunwayThreshold. Proposed Solution Add the appropriate definition to the ARINC document. | Oct meeting | Closed | Resolve with action 78:  Added optinal footnote to fuel attributes  Added text in new section 4.6 to draft recommending using absolute “priority” values for appinfo AttributePosition
85 | Brian | B.5 Attributes ordering implemented by appinfo schema elements is incorrect for a number of attributes. Causes are: 1) appinfo is not specified, 2) same appinfo for two or more attributes and 3) the values of appinfo are not sequential. Proposed Solution: The table in ORDERING.XLSX file lists the detected cases of Incorrect Attributes Ordering and the proposed corrections. The table does not include attributes that are: 1) considered optional in accordance with DO-291B (Problem B.04) and 2) required by DO-291B but not listed in ARINC 816-2 (Problem A.02). | Oct meeting | Open | Need to review in XSD
86 | Brian | XSD file can be improved to detect more problems with ARINC 816 XML files. Proposed Solution: The most obvious way to improve the XSD is to use it for the data value domain checking. 1) String attribute validation may include string length validation and string contents validation. For the string contents, it would be useful to define the appropriate requirements. The following example demonstrates how it can be done: <xsd:simpleType name="idarptSet"> <xsd:restriction base="xsd:string"> <!-- DO-291B defines the value domain as 1 to 5 characters --> <!-- while ICAO7910 states that it should be 4 uppercase characters --> <xsd:pattern value="[A-Z]{4}"/> </xsd:restriction> </xsd:simpleType> ...(see Sergey's email for the rest)... | Oct meeting | Closed | Add patterns to string type tags for applicable types - Assert tag is not supported in EA  Added text in new section 4.6 to draft to explain how somebody can extend the schema if they want to add assert tags.
87 | Brian | C.1 The aslwidth attribute of the ArrestingSystemLocation feature is given incorrectly in the attribute specification part of the feature catalog. Feature Attribute: 'aswidth' Name: aswidth … Proposed Solution: Feature Attribute: 'aslwidth' Name: aslwidth … | Oct meeting | Closed | DO-291 issue corrected in updated model by Scott Wilson
88 | Brian | C.2 Element name is given with the whitespace in section 3.1.5 3.1.5 Airport Entry Name: Airport Entry Proposed Solution 3.1.5 Airport Entry Name: AirportEntry | Oct meeting | Closed | Fixed in draft A816-3
89 | Brian | ARINC 816-2 section 3.1.9 traces to “Enumerations and Code Lists” section. The section number, however, is given incorrectly. Some size metrics applicable to the arrays and significant AMDB sizes have been predefined in this standard (see Section 4.3.3, Enumerations and Code Lists). Proposed Solution: The section number should be 4.3.4: Some size metrics applicable to the arrays and significant AMDB sizes have been predefined in this standard (see Section 4.3.4, Enumerations and Code Lists). | Oct meeting | Closed | Fixed in draft A816-3
90 | Airbus/Thales | Figure out how to handle issues related to major/minor taxiway container grouping by featid instead of generic ID, which would lead to only one taxiway feature container per major/minor taxiway container. | Oct meeting | Closed | Thales agrees with new approach
91 | All | Consider impact of duplicate (temporal) instances on sort order (need to have duplicate instances sequential in the file) | Oct meeting | Closed | Added stvalid as sort order tie-breaker.
92 | Jean-Etienne | Draft part of document for how to use ObjecStringTable for idnumber. Also define IndexTable for each feature instance in AMDB file. | December 2014 web meeting | Open

## Attributes
Feature | DO-291 attributes not in A816 | Definition
All | idarpt | ICAO aerodrome location indicator. Encoding: ICAO aerodrome designator (4-letter code). Example: KIAD
All | hres | Horizontal resolution of coordinates (latitude, longitude) defining the feature
All | source | Name of entity or organization that supplied data according to DO-200A/ED-76.
All | integr | Integrity of data in the aeronautical data processing chain from data origination process to present data manipulation process expressed in terms of probability of data loss or alteration (0=perfect, 1=all lost)
All | revdate | Last revision date and time of data
All | vacc | Vertical accuracy as a Linear Error Probability (LEP)
All | vres | Vertical resolution of coordinates (orthometric height) defining the feature
RunwayElement | N/A
RunwayIntersection | N/A
RunwayThreshold | tdzslope | Touchdown zone longitudinal slope (slope of 1/3 of the runway length from threshold of first 3000 feet for runways longer than 9000 feet). Only applies if threshold is suitable for landing.
RunwayThreshold | rwyslope | Runway slope corresponding to landing direction.
RunwayThreshold | vasis | Veritical guidance lighting system available corresponding to threshold location
RunwayThreshold | geound | Geoidal undulation at the point position
RunwayThreshold | ellipse | Height below/above the WGS-84 ellipsoid at the point position
RunwayMarking | N/A
PaintedCenterline | N/A
LAHSO | N/A
ArrestingGearLocation | N/A
ArrestingSystemLocation | setback | Distance from the end of the runway of the actual EMAS material to avoid damage due to jet blast and undershoots. This distance will vary depending on the available area and the EMAS materials.
ArrestingSystemLocation | aslength | Length of the EMAS bed material not including any setback
ArrestingSystemLocation | aslwidth | Width of the runway plus any sloped access ramp
RunwayShoulder | status | State of feature
RunwayShoulder | gsurftyp | Generic surface type
Stopway | N/A
RunwayDisplacedArea | idrwy->idthr
Blastpad | N/A
RunwayCenterlinePoint | idthr->idrwy
RunwayCenterlinePoint | ellipse | Height below/above the WGS-84 ellipsoid at the point position
RunwayCenterlinePoint | geound | Geoidal undulation at the point position
TLOF | surftype | Predominant surface type
FATO | surftype | Predominant surface type
HelipadThreshold | geound | Geoidal undulation at the point position
HelipadThreshold | ellipse | Height below/above the WGS-84 ellipsoid at the point position
TaxiwayElement | idapron | Name of apron. Encoding: if no apron is associated with the feature instance, use the Not Applicable default value.
TaxiwayElement | gsurftyp | Generic surface type
TaxiwayShoulder | gsurftyp | Generic surface type
TaxiwayShoulder | status | State of feature
TaxiwayHoldingPosition | N/A
TaxiwayGuidanceLine | color | Color of the line (yellow, orange, blue, white)
TaxiwayGuidanceLine | style | Style of the line (solid, dashed, dotted)
RunwayExitLine | color | Color of the line (yellow, orange, blue, white)
RunwayExitLine | style | Style of the line (solid, dashed, dotted)
TaxiwayIntersectionMarking | N/A
Hotspot | N/A
FrequencyArea | N/A
ApronElement | gsurftyp | Generic surface type
DeicingArea | idbase | Name of underlying Taxiway Element, Parking Stand Area, or Apron Element
DeicingArea | gsurftyp | Generic surface type
ServiceRoad | gsurftyp | Generic surface type
StandGuidanceLine | color | Color of the line (yellow, orange, blue, white)
StandGuidanceLine | style | Style of the line (solid, dashed, dotted)
ParkingStandLocation | N/A
ParkingStandArea | gsurftyp | Generic surface type
ParkingStandArea | jetway | Availability of jetway
ParkingStandArea | fuel | Types of fuel available. Encoding: If multiple fuel types are available at a stand point, list all of them, separated by commas. Example: Jet A1 and Mogas: 1,3
ParkingStandArea | towing | Availability of towing service
ParkingStandArea | docking | Availability of docking guidance system
ParkingStandArea | gndpower | Availability of ground-power
ParkingStandArea | idapron | Name of apron. Encoding: if no apron is associated with the feature instance, use the Not Applicable default value.
VerticalPolygonalStructure | material | Predominant surface material of the vertical structure
VerticalPolygonalStructure | height | Maximum height of top of vertical structure
VerticalPolygonalStructure | elev | Maximum elevation of feature (Orthometric height)
VerticalLineStructure | material | Predominant surface material of the vertical structure
VerticalLineStructure | height | Maximum height of top of vertical structure
VerticalLineStructure | elev | Maximum elevation of feature (Orthometric height)
VerticalLineStructure | lighting | Obstacle lighting in conformance with ICAO Annex 14, Chapter 6.
VerticalLineStructure | marking | Obstacle marking in conformance with ICAO Annex 14, Chapter 6.
VerticalPointStructure | material | Predominant surface material of the vertical structure
VerticalPointStructure | height | Maximum height of top of vertical structure
VerticalPointStructure | elev | Maximum elevation of feature (Orthometric height)
VerticalPointStructure | lighting | Obstacle lighting in conformance with ICAO Annex 14, Chapter 6.
VerticalPointStructure | marking | Obstacle marking in conformance with ICAO Annex 14, Chapter 6.
VerticalPointStructure | radius | Radius of circle around center of obstacle including body of obstacle and associated structures including guywires.
Water | N/A
ConstructionArea | pstdate | Planned construction start date
ConstructionArea | pendate | Planned construction end date
ConstructionArea | piocdate | Planned initial operational date
AerodromeSurfaceLighting | N/A
AsrnNode | catstop | Low visibility operation category of holding position
AsrnEdge | N/A