## Action Items - TOD
Num | Assignee | Section | Action | Due date | Status | Notes | DQR Applicable | DQR Comments
1 | Ryan Niehaus |  | Ask Ryan Niehaus (Rockwell Collins) how data resolutions are handled in high latitude areas for existing data sources (e.g., does it maintain arc-secs or switch to metric?) | 2012-10-01 | Closed | Spacing is decimated (~5 different levels in DTED format) as it approaches pole; all in longitudinal direction; intervals of 0-50, 50-70, 70-90,…
2 | Beby & Christian |  | Find out obstacle data quality requirements for Ground-following systems (Tactical Ground Collision Avoidance System) | 2013-03-01 | Closed | A400M TGCAS requirement is for 1/27 arc second 1 meter resolution for vertical terrain data used by FM A400M for vertical navigation Data providers not expecting to be able to produce this TGCAS will not use A815; perhaps future projects will
3 | Brian |  | Develop Overview and Background and Scope sections (1.1 and 1.2) | 2013-03-01 | Closed | Added to strawman
4 | Airbus |  | Develop Operational Overview section (1.3) | 2013-03-01 | Closed | Added to strawman
5 | Pete Grau |  | Develop Airline Objective section (1.4) | 2014-05-19 | Closed | Draft text and send to Lufthansa (Reinhard Andreae) for review
6 | Marcin |  | Develop Database Structure section (1.5) | 2014-05-19 | Closed | Pull in overview material from Marcin's section 3 draft - review latest checkin from Marcin
7 | Airbus |  | Develop Data Product Specification section (2.1) | 2013-03-01 | Closed | Added to strawman
8 | Brian |  | Develop Supplemental Data section (2.2) | 2013-03-01 | Closed | Added to strawman
9 | Honeywell |  | Develop Dataload section (2.3) | 2013-03-01 | Closed | Added to strawman
10 | Rockwell Collins |  | Develop Obstacle section 3 content (index/config and cross-reference file definitions) | 2013-10-07 | Closed | Marcin provided proposal at 7/31 web meeting, will send to group for review
11 | Rockwell Collins |  | Develop Terrain section 3 content (index/config and cross-reference file definitions) | 2014-05-19 | Closed | Revised based on Phoenix discussion
12 | Brian | Obstacle | Develop Obstacle section 4 content (features and attribute definitions) | Ongoing | Open | Auto-populate from models? Dependent on action 36
13 | Brian | Terrain | Develop Terrain section 4 content (features and attribute definitions) | Ongoing | Open | Auto-populate from models? Dependent on action 36
14 | GE Honeywell Rockwell Collins |  | Propose concept for Obstacle tile file index features | 2013-05-21 | Closed | Rockwell Collins provided some material in Frankfurt
15 | Stephane |  | Invite Mileridge to next meeting | 2012-12-01 | Closed | Stephane update Nov19: Contact has been made with Mileridge at the TOD WG and they actually committed to actively participate to the next TODB in order to contribute with inputs from the TIXM work. Please forward to Roy and Kathryn (cc'ed here) the meeting announcements.
16 | Brian |  | Initial Obstacle UML model | 2013-05-21 | Closed | Updated as far as I can, waiting for Jepp to provide contact info for their modeller
17 | Brian |  | Initial Terrain UML model | 2013-03-01 | Closed | Overcome by action 28 (use TICM as basis for terrain model)
18 | Jeppesen Lufthansa Systems |  | Propose concept for line and polygon obstacles that cross tile boundaries | 2013-03-01 | Closed | Hybrid options 2/3 solution agreed to in Frankfurt
19 | Jeppesen Boeing Airbus |  | Propose concept for how to organize obstacles into tiles (e.g., fixed size vs. variable size based on number of obstacles) | 2013-05-21 | Closed | Dec meeting: leaning towards recursive-sized based on # of obstacles Jeppesen has developed some tools to do some analysis What is appropriate number of obstacles per tile? Dependent on data gathering action 32. Decided to just provide metadata framework for provider to choose their own threshold. Some filtering may need to be applied to drastically reduce terminal area cases. | Obstacles | Obstacle count threshold for recursive subtiling
20 | Rockwell Collins |  | Propose concept for non-XML based binary format for low-level obstacle data | 2013-03-01 | Closed | Core data solution agreed to in Frankfurt
21 | Christian | Terrain | Develop Terrain file format section (5.3 in strawman) | Jan 2015 meeting | Open | Develop based on Phoenix discussions
22 | Christian |  | Develop Obstacle file format section (5.4 in strawman), including content ordering | 2014-05-19 | Closed | Initial draft in strawman, still some open issues highlighted in yellow
23 | Airbus |  | Develop Appendix C (Application Considerations) | 2013-03-01 | Closed | Added to strawman (assignments for subsection in strawman as well) - can have initial drafts in October meeting
24 | Stephane |  | Provide sample obstacle data to use for validation activities | 2013-01-01 | Closed | Stephane sent shapefiles on Nov19. Data for area 2 of LFBO by "DSNA / SIA" (French AIS) in 2009. A request to all those States / ANSPs which have started their eTOD implementation was made at the last TOD meeting so that they can provide the ARINC group with terrain and obstacle data samples. Alex Petrovsky (cc'ed), TOD WG Secretary, is the contact point to which these samples should be sent or requested from.
25 | Stephane |  | Provide sample terrain data to use for validation activities | 2013-01-01 | Closed | Received samples from numerous sources: Spain, Norway, Portugal, UAE. Files are in various formats.
26 | Pete Grau |  | Send out TODB document strawman | 2012-12-01 | Closed
27 | Brian |  | Create list of sample terrain data received, including what formats they are in and what tools are required | 2013-03-01 | Closed | Added action 31 Members wanting the data can get it on stick from Brian, or virtually by contacting Brian to set up a temporary download site
28 | Stephane |  | Check to see if Eurocontrol can provide TICM model and dependencies to ARINC ADB committee, and if there are any issues with ARINC ultimately publishing their own | 2013-03-01 | Closed | Yes, they can provide them. See action 35 for ARINC to check on providing public (free of charge) link.
29 | Stephane |  | Check to see if AIRM has changed anything in their plans to use TICM in AIRM | 2013-03-01 | Closed | Yes, they changed a couple of things. See emails from Eurocontrol.
30 | Brian |  | Ask Jean-Etienne about any plans to use TICM/TIXM in SESAR projects 9.31 and 9.48 | 2013-05-21 | Closed | Response from Jean-Etienne: "Today, the main focus of 9.31 project is on AMDB. The work performed on TODB is a high level requirement clarification and identification of issues / benefits. The aim of the issues / benefits analysis is to identify the priority level for this activity. 9.48 project does not deal with TODB. On Thales side (outside SESAR), we have a TAWS application included into the TAWS+, T2CAS, T3CAS supplied by ACSS. This TAWS application uses a Terrain and Obstacle database on a proprietary format. I try to clarify Thales’ position regarding open format TODB activity."
31 | Stephane and Christian |  | Ask terrain data experts about what GIS tools they recommend and the type of computing power needed to effectively use them | 2013-05-21 | Closed | Info from Stephane: * Terrain data fles provide altitude info at given locations or provide additional info for some elements. They are not necessarily really intended for "direct display", but can be processed for visualization (draping over a ortho-image for instance) * There are multiple terrain data formats (.asc, .mnt, ".dis", .bil, .dted, .dtm, .xyz, .dt0, .dt1, dt2, even raster formats such as Tiff , jpeg, bmp...) * In many cases, the data file needs to be pre-processed prior to being displayed / used on a standard software for PC * In terms of preferred GIS to process such files, Quantum GIS (aka QGis) is recommended as a free tool. Global Mapper (roughly $400) is also suggested. Jeppesen uses: ESRI ArcGIS and ArcMap
32 | Christian |  | Assess impact to number of tiles resulting from varying # of obstacle threshold, and using a file size criteria vs. # of obstacle criteria | 2013-10-07 | Closed | Enroute scenario: Started with 4x4 degrees tiles, recursively divided into 4 subtiles after threshold: average 200 obstacles with height of 100m per tile 2000 threshold: no effect (1700 was most for 4x4 degree tile) 1000 threshold: increases tiles from 64 to 82 in US 500 threshold: increased to 139 in US Might be worth having different tile decomposition algorithms for enroute vs. terminal? Brian's take-away: threshold has minimal impact on enroute areas - therefore terminal areas will be the real drivers of limit Terminal data: worst cases still have thousands and thousands of obstacles when you shrink down to a 0.25x0.25 degree subtile. A limit of 1000 or 2000 did not seem like it would make a dent in several cases.
33 | Pete Grau |  | Have ARINC update the ADB page on the ARINC website to include terrain and obstacles. | 2013-05-21 | Closed | New content on ARINC site now.
34 | Pete Grau |  | Ask ARINC if we can add a link to the support files (.xmi, .xsd) outside of the spec (for example, on the ADB page to the ARINC website. | 2013-05-21 | Closed | Yes, this can be done.
35 | Pete Grau |  | Post strawman on ADB page of ARINC website. | 2013-05-21 | Closed | This has been posted on the updated ARINC site.
36 | Brian | Both | Determine how to autogenerate Section 4 content from EA model. | Ongoing | Open
37 | Allan Hart |  | What level of granularity is needed for hacc/vacc? At the post level, grid level, etc. (i.e. for TAWS alerting)? Consider confidence level and integrity as well. | 2014-02-19 | Closed | Email from Allan on 1/30: Honeywell maintains a source terrain dataset with equivalent specification to SRTM DTED Level 1. We recommend that ARINC 815 reference the SRTM DTED Level 1 requirements. This is likely akin to tile level. SRTM Level 1 uses 1201x1201 posts in a single file with post spacing of 90m. Group generally agreed to convey data quality at tile level. See action 38 for discussion on whether an overall grid quality also needs to be included.
38 | Allan Hart |  | Determine approach for setting hacc/hres/vacc/vres at the grid level when different data sources may be compiled to make up the grid. Consider confidence and integrity as part of this? This applies to obstacle database as well. | 2014-02-19 | Closed | Email from Allan on 1/30: Data sources are integrated into a master dataset prior to product database generation, and is independently validated and verified to meet specifications equivalent to SRTM DTED Level 1. Rockwell recommends including overall grid-level quality metadata as well. Allan's response didn't address how to do this, it just assumed that all data met a certain quality specification. Group agreed that we shouldn't have this data at Grid level because we don't want outliers to give a false impression. Come up with scheme for regionalization to convery information about a particular region. This would be flexible enough for different providers to work out how they want to define regions. | Both | Acceptable accuracy and integrity
39 | Allan Hart |  | What is the timeframe for ICAO adopting EGM 2008? | 2014-02-19 | Closed | Will just go with EGM-96 for now. If/when ICAO sets a date for migration to EGM 2008, we can address it then (i.e., through Supplement update).
40 | All |  | Propose other obstacle index files (e.g. airport based, obstacle type based, etc.) | 2014-05-19 | Closed | Added text in overview section We won't define any other standard indexing mechanisms in the document | Both | Any custom indexing should be well-defined
41 | Marcin |  | Draft document text for general custom index framework | 2014-05-19 | Closed | Added text in overview section Standard won't use .idx extension; add language that other extensions may conflict in the future with updates to the standard
42 | Brian | Both | Create terrain and obstacle models based on schemas sketched out in Phoenix meeting | Ongoing | Open
43 | Brian |  | Send action item list to Allan | 2013-10-11 | Closed | Sent on 10/14/2013
44 | Allan Hart |  | Develop document text for how to handle mixed (non-integral) resolutions in a terrain database | 2014-05-19 | Closed | Group chose Option 2 (see Terrain meeting minutes from Phoenix) Email from Allan on 1/30: "Product hardware memory and real-time software processing constraints typically require terrain to be selectively formatted at a variety of resolutions, and not produced in its entirety at the original source data resolutions. In addition, proprietary compression encoding is used to minimize product database size."
45 | Jason (document text) Brian (add metadata to model) | Terrain | Develop document text for requirements/assumptions on terrain data capture (e.g. WGS-84 and EGM-96, use maximum elevations, etc.). Look at DO-276 wording (add reference to DO-276 sections?). | Jan 2015 meeting | Open | Email from Allan on 1/30: Honeywell terrain uses WGS-84 horizontal reference and MSL vertical reference. Maximum elevation is used for each grid cell in any given resolution layer. Ask Allan to draft document text, not just provide what Honeywell is using. Add metadata to config file indicating horizontal and vertical reference datums - enumerations with reserved space for future datums. For now, just WGS-84 and "other" for horizontal, and EGM-96:1996, EGM-96:2004, WGS-84, and "other" for vertical. A database must use a single reference - no mixed datums.
46 | Christian |  | Investigate how EXI handles array encoding to help make decision on data type to use for terrain elevation array (discuss with Rich Rollman at AgileDelta). Verify that fixed-record size assumption is correct. | 2014-01-01 | Closed | Can't do fixed record sizes with EXI
47 | All |  | Propose method for incorporating add-on temporal data (this should apply to AMDB as well, although there might be some details due to different schemas/database structures). | 2014-05-19 | Closed | Group drafted strawman text in Gdansk meeting
48 | Performance Software | Obstacle | Mature concept of how separate obstacle databases with different "detail levels" is handled. E.g., would these separate databases need to be correlated/linked somehow? Do we need metadata or some way to characterize what level of content is in a database? | 2014-02-19 | Closed | Put this type of information in UDCoverage blob.
49 | Christian |  | Assess impact of various number of obstacle thresholds on tile size and number of tiles. Just need a rough order of magnitude idea of impact to validate our data structure. Consider at what point file sizes or number of files start to impact platform - impacts performance, memory resources, etc. | 2014-05-19 | Closed | A typical scenario of 4x4 coarse grid with 2000 obstacle threshold for sub-division seemed to yield reasonable tile size and number of tile results World-wide ROM would be <100MB for everything including extended data, index, cross-reference, and config | Obstacles | See action 19
50 | All |  | Decide which obstacle LDX schema approach you prefer - Jason or Marcin proposal (see meeting notes). | 2014-05-09 | Closed | Choose more nested approach (Marcin proposal) simply because it is a bit more pure from an XML standpoint. Use Jason approach as Plan B if we run into performance/validation issues with Plan A.
51 | Brian | Both | Once DO-291 updates are made to have attributes/metadata consistent with DO-276B, work out what can refer to DO-291 and what needs to be uniquely defined in A815. | Ongoing | Open
52 | Allan Hart |  | Check how Honeywell handles mixed resolutions (non-integral) in the same database (help inform action 44). | 2014-05-19 | Closed | Email from Allan on 1/30: Honeywell’s product databases contain layers at various resolutions, typically with low resolution layers having worldwide coverage, and higher resolution layers having selected partial coverage. Terrain map files within product formatted databases are managed as quads (0.5deg x 0.5deg), with a consistent resolution within each quad map file.
53 | All |  | Consider whether we want to mandate that if a coarser resolution tile does not exist but it does exist at a finer resolution that is in the same database, that it must be down-sampled from a finer resolution and included in the coarser dataset? For example, if 9 arc-sec data does not exist for a given tile, but it does exist in 3 arc-sec dataset, then that tile cannot be empty for 9 arc-sec, it needs to be derived from 3 arc-sec. Maybe only enforce this if they are integral multiples of each other. | 2013-12-11 | Closed | Group agreed that this mandate is desired. Will incorporate into document (including down-sampling guidelines). | Terrain | Required resolutions need to be specified and possibly constrained (inclusion and/or exclusion), depending on the product and intended use.
54 | Marcin (document text) Brian (add metadata to model) | Terrain | Propose method for downsampling to cover coarser resolution tiles where no data exists, but it can be derived from finer resolution tiles. How is metadata handled? | Jan 2015 meeting | Open | Make data provider do it prior to encoding (transparent to application), but list a set of assumptions or rules for data providers to follow (e.g., using highest elevation) Single attribute for tile indicating upsampled, downsampled, or raw (replace current "upsampled" attribute)
55 | All |  | Come up with approach to define regions, which would be modeled as a sibling of Grid (provide data quality for region for each grid, may be used for other purposes). | 2014-05-19 | Closed | Added top-level metadata concept (user-defined coverage blob); see Gdansk meeting notes | Both | Regionalization boundaries (inclusive and/or exclusive, or indicate worldwide, etc.) should be conveyed
56 | All | Both | Develop DQR guideline appendix | Ongoing | Open | For now, identify topics on spreadsheet as we develop standard on things we leave open to implementation. Marcin got the list started - add tab to action item list.
57 | Jason | Terrain | In terrain section, develop commentary text to suggest maintaining geographical post density to achieve greater uniformity across all tiles (include figure). This could include polar cap considerations. | Jan 2015 meeting | Open
58 | Fabrice? | Terrain | In terrain section, add commentary about possible extension of Tile element if somebody wants to define or reference picture/pixel information corresponding to a given tile | Jan 2015 meeting | Open
59 |  | Obstacle | Consider gathering obstacles - how would this impact data model? Would we realize any size savings? |  | Closed | Decided not to gather obstacles for now because it is unlikely that very many obstacles of the same type would have the same elevation and height, and it would mess up fixed record sizes in the .dat file, potentially mess up recursive subdivision, and compression will probably provide a lot of the same savings.
60 |  | Terrain | Consider whether or not to set max limit to number of posts in tile in TDB (e.g., to bound Elevation and SurfaceType arrays) | Jan 2015 meeting | Open
61 |  | Terrain | For each float data type, consider whether round-off errors could impact things, and if scaled ints should be used instead | Jan 2015 meeting | Open
62 |  | Terrain | For TDB, decide if .dat record sizes need to be fixed; if so, how do we handle "empty" tiles (all baseelevation). If not, do we need dat_file_size and max_dat_size metadata? | Jan 2015 meeting | Open
63 | Jean-Etienne | Both | Wrote paragraph on objective of A815 in terms of defining a standard format, and standard packaging framework, but not defining specific packaging parameters. | December 2014 web meeting | Open
64 | Christian | Both | Update section 2.3.1 to replace TBDs with estimates to describe what kind of volume of data people can expect. May be formula based on known encoding size per obstacle/post. | Jan 2015 meeting | Open
65 |  | Both | Is 32-bit CRC sufficient for the file sizes we may encounter? What is the probability of detecting error using a 32-bit CRC for files GBs in size? If that is not acceptable, should be cap the max file size (e.g., 512MB or 1GB), or should be use a larger CRC? | Jan 2015 meeting | Open
66 | Jason (Honeywell) | Both | Draft text for Appendix C - Application Considerations for TAWS and Peaks | Jan 2015 meeting | Open
67 | Airbus | Both | Draft text for Appendix C - Application Considerations for VSD | Jan 2015 meeting | Open
68 | Marcin | Both | Draft text for Appendix C - Application Considerations for SVS | Jan 2015 meeting | Open
69 | Christian | Both | Draft text for Appendix C - Application Considerations for Enroute map | Jan 2015 meeting | Open
70 | Airbus (Helicopter group) | Both | Draft text for Appendix C - Application Considerations for Ground-following systems/helicopter applications | Jan 2015 meeting | Open

## Sample data
State | Format(s) | Tool(s) required
Armenia | Excel (not sure of original format) | Microsoft Excel
Norway | DEM (USGS) | Most commercial GIS tools?
Spain | GeoTIFF (data), XML (metadata) | Most commercial GIS tools, text/XML editor
Moldova | Shapefiles | Most commercial GIS tools
? | ADF (ArcGIS Binary Grid) | ArcGIS, other commerical GIS tools?
UAE | Unknown | Cannot download
Jeppesen uses ArcMap (part of ArcGIS) for production - expensive and difficult to train