## TaskSummary
2018-10-23 | Task List Summary - ARINC 661 - Supplement 7
Shows tasks and action items we are currently working
Issue# | Title | Primary Assignee | Status
08-19 | Widget Structure Meta-Definition | GE/FLX | Rob has determined plan of action and will update and report to at 11/27/18 WebEx.
13-4 | Three Dimensional Projection/Map 3D Management (consolidated from 18-1). | DA/ALL | Delayed, will update for 11/27/18 WebEx.
13-10 | Super Layer Appendix H (clarifications) | DA/PRE/ TH | Delayed, will update for 11/27/18 WebEx.
15-2 | Super Layer Appendix H (new material) | DA/TH | Defer to Supplement 8.
16-2 | Layer Definition XML Split | GE | Update for 11/27/18 WebEx.
16-4 | Framing Refresh Container (Master/Slave) | FLX | Revisit after Meta-definition.
16-5 | Update to PictureBlock for picture atlasing | GE | Defer to Supplement 8.
16-10 | Mutliple Value Animations | PRE | Defer to Supplement 8.
16-17 | Harmonize A661 Part 1 and Part 2 XML. See corresponding Part 2 Action Item. | FLX | Propose a new approach that can be applied to both Part 1 and Part 2 schemas and samples. See corresponding Part 2 Action Item. Defer to Supplement 8.
17-8 | Candidate gesture | TH/PRE | Update for 11/27/18 WebEx.
17-13 | Readouts in MapItems | DA | Update for 11/27/18 WebEx.
17-16 | Document Corrections | GE | Update for 11/27/18 WebEx.
17-17 | Update MapExternalSource (previously ExternalSource and earlier, MapGrid 3D) | DA | Update for white paper and flesh out for 11/27/18 WebEx.
18-2 | Column Widget | HWL | Delayed, will update for 11/27/18 WebEx.
18-3 | Scroll Extension | HWL | Delayed, will update for 11/27/18 WebEx.
18-10 | Legend Readouts in MapVert | DA | Update for 11/27/18 WebEx.
18-12 | Clarify TouchArea ambiguities | ES/PRE | Update for 11/27/18 WebEx.
18-15 | MapHorz and MapVert updates | DA | Insert into master and update for 11/27/18 WebEx.
18-16 | Add runtime modifiability | B | Update proposal for 11/27/18 WebEx.
18-17 | Check MapItem Idents | GE | Propose revisions for 11/27/18 WebEx.
18-18 | Document Corrections | HWL | Review document for additional corrections and use of "shall" for 11/27/18 WebEx.
18-19 | Updates to Animation Widgets | DA | Propose revisions for 11/27/18 WebEx.
18-20 | Word Wrap/WrapStyle | BA | Proposal for 11/27/18 WebEx.
18-21 | Character Set additions | DA | Proposal for 11/27/18 WebEx.
18-22 | GestureArea Event | BA | Proposal for 11/27/18 WebEx.
18-23 | ComboBox and Selector | BA | Proposal for 11/27/18 WebEx.
18-24 | PictureAnimated | BA | Proposal for 11/27/18 WebEx.
18-25 | GpTriangles Proposal | HWL | Review for 11/27/18 WebEx.
KEY
AB | Airbus | GE | GE Aviation
AR | ARINC | HWL | Honeywell International, Inc
B | Boeing | PRE | Presagis, Inc
DA | Dassault Aviation | RC | Rockwell Collins
ELB | Elbit Systems | TH | Thales Avionics
ES | Esterel Technologies | All | All Subcommittee Members
FLX | Flexible Software Solutions
Note on A3: Issues are SC discussion items. Issue# is composed of 2-digit year indicator and a sequential item number

## DetailedTasks
2012-07-23 | Task List - ARINC 661 - Supplement 5 | Shows tasks and action items we are currently working
P. Grau |  | all changes since 2/17/12 are marked in red
all changes since 7/24/12 are marked in blue
Issue# | Description | Affected Section(s) | Assignee | Priority | Opened | Closed | Status | Status/Comments/Actions | Short term actions
08-19a | Should we create a meta-definition in XML or some other notation (XSD, UML, etc) to list all widgets and their params? It would be the definitive list of correct widgets/params for the Supplement. Could be put in a new appendix for information purposes only, or it could be added to Section 6 as a way of listing the required set of XML attribute names and their correct spellings. Would not affect the binary DF or XML DF notation. Would allow people to validate DFs with tools. Meta-defs could even be used by a future tool to autogenerate sections of the ARINC 661 spec. | sec6?, newAPP? | VR, ND, RHS | 3 | 2008-11-18 |  | In work | 12/9. Yes, interesting. Herve sent writeup and files 2/15/09. He presented a new writeup and files at MLB09. Example was an XML meta-def and an XML Schema "meta-meta-definition" (grammar for the XML file). Could use other notation (DTD, UML, etc). We like the idea, but not for Suppl 4, we decided. PAR09: no discussion. Defer to Suppl 5. 6/7/11: Esterel has created something like this, along with tools. So have others. Group not sure we can agree on one schema and tool. 6/15/11: Gary sent mtrls to Aubanel and Vincent. 2/23/12: deferred to Supplement 6. Should ideally be an electronic file, sub-committee could use it to generate spec, etc. Could put hyperlnks in the document. Still deferred to Supplement 6. Linked to item 14-4 DSL. Proposal for Annapolis 9/16/14. Timeline for proposal to be presented in Paris 3/10/15. Update proposal, review XSD in Seattle. Reviewed two proposals. All to consider both to discuss and choose a path forward for 10/8/15. On 10/8/15, group decided to continue development, but delay inclusion until Supplement 7. Rob to incorporate Sofyan's comments and update his proposal. All to review and comment for 12/14/15, then decide which proposal or combination to use going forward. Decision made on 12/14/15 WEbEx to proceed using FlexSS approach with some modifications. Rob ro review comments and incorporate into an updated proposal for Toulouse. Defer to Supplement 7. Update for Warsaw 3/27/17. Update for Phoenix. Update for Paris. Lewis to organize off-line meeting with Herve, Matt, Sofyan, and Rob to determine next steps 10/23/18. Plan of action set to complete by next WebEx 11/27/2018. Will upload into Daptiv when complete.
08-19b | Dassault suggests adding use of XML namespaces so that OEMs/tool vendors can define custom extensions to the DF grammar. It would allow us to add the option of using XML Schemas instead of DTDs. Schemas are more flexible and it is easier to add extensions to them. This would increase interoperability of XML DFs between tools and would allow people to validate DFs with tools. Depending on the meta-definition notation we choose, we may want to add namespaces and schemas. | sec6, AppC | VR, ND | 3 | 2008-05-15 |  | In work | Got an updated writeup from Herve 7/21/08. Was part of item 08-08, moved here after MLB09 meeting. PAR09: no discussion. Defer to Suppl 5. 2/23/12: deferred to Supplement 6 Still deferred to Supplement 6. 7/24/12. Esterel to update, provide examples with some arrays for future teleconference. 7/11/13. Update for Annapolis 9/16/14. Timeline for proposal to be presented in Paris 3/10/15. Update proposal, review in Toulouse. Defer to Supplement 7. Update for Warsaw 3/27/17. Update for Phoenix. Update for 4/19/18 WebEx. Lewis to organize off-line meeting with Herve, Matt, Sofyan, and Rob to determine next steps 10/23/18. Plan of action set to complete by next WebEx 11/27/2018. Will upload into Daptiv when complete.
13-4 | Three Dimensional Projection/Map 3D Management |  | B/DA/ALL |  |  |  | In work | Merged with Action Item 18-1 in the Montreal meeting. Update for 10/23/18 WebEx. Update for 11/27/2018 WebEx.
13-10 | Super Layer Appendix H |  | DA/PRE/TH |  |  |  | In work | Update for 10/23/18 WebEx. Update for 11/27/2018 WebEx.
15-2 | Super Layer Appendix H (new material) |  | DA/TH |  |  |  | In work | Defer to Supplement 8.
16-2 | Layer Definition XML Split |  | PRE |  |  |  | In work | Update for 10/23/18 WebEx.
16-4 | Framing Refresh Container |  | FLX |  |  |  | In work | Revisit after Meta definition.
16-5 | Update to PictureBlock for picture atlasing |  | GE |  |  |  | In work | Update with XML examples for both options and mipmapping. Defer to Supplement 8.
16-10 | Multiple Value Animations (name changed from Animation Laws) |  | PRE |  |  |  | In work | Defer to Supplement 8.
16-17 | Harmonize A661 Part 1 and Part 2 XML |  | FLX |  | 2016-09-15 |  | In work | Propose a new approach that can be applied to both Part 1 and Part 2 schemas and samples for 10/23/18 WebEx. Defer to Supplement 8.
17-8 | Drag Start on Press gesture (possible rename?) |  | TH/PRE |  | 2017-03-28 |  | In work | Renamed Candidate gesture. Update for 10/23/18 WebEx. Update for 10/23/18 WebEx.
17-13 | Readouts in MapItems |  | DA |  | 2017-09-07 |  | In work | Herve to revise for 10/23/18 WebEx. Update for 10/23/18 WebEx.
17-16 | Document Corrections |  | GE |  | 2017-10-31 |  | In work | Update for 10/23/18 WebEx. Update for 10/23/18 WebEx.
17-17 | Update MapExternalSource (previously ExternalSource and earlier, MapGrid 3D) |  | DA |  | 2017-12-07 |  | In work | Original MapGrid 3D mothballed. Determined in Paris to change course and update ExternalSource instead. Update proposal for 10/23/18 WebEx. Update for white paper and flesh out for 11/27/18 WebEx.
18-2 | Column Widget |  | HWL |  | 2018-02-15 |  | In work | Update proposal for 10/23/18 WebEx.
18-3 | Scroll Extension |  | HWL |  | 2018-03-13 |  | In work | Update proposal for use on additional widgets 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-10 | Legend Readouts in MapVert |  | DA |  | 2018-03-13 |  | In work | Insert into Master for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-12 | Clarify TouchArea ambiguities |  | ES/PRE |  | 2018-03-16 |  | In work | Proposal for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-15 | MapHorz and MapVert updates |  | DA |  | 2018-07-24 |  | In work | Insert into Master and update for 10/23/18 WebEx. Insert into Master and update for 11/27/18 WebEx.
18-16 | Add runtime modifiability |  | B |  | 2018-07-24 |  | In work | Update for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-17 | Check MapItem idents |  | GE |  | 2018-08-01 |  | In work | Propose revisions for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-18 | Document Corrections |  | HWL |  | 2018-09-25 |  | In work | Review document for additional corrections and use of "shall" for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-19 | Updates to Animation Widgets |  | DA |  | 2018-09-28 |  | In work | Propose revisions for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-20 | Word Wrap/WrapStyle |  | BA |  | 2018-09-28 |  | In work | Proposal for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-21 | Character set additions |  | DA |  | 2018-09-28 |  | In work | Proposal for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-22 | GestureArea Event |  | BA |  | 2018-09-28 |  | In work | Proposal for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-23 | ComboBox and Selector |  | BA |  | 2018-09-28 |  | In work | Proposal for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-24 | PictureAnimated |  | BA |  | 2018-09-28 |  | In work | Proposal for 10/23/18 WebEx. Update for 10/23/18 WebEx.
18-25 | GpTriangles Proposal |  | HWL |  | 2010-10-23 |  | New
misc | Section 3.2.5: LEGEND_POPUP should be spelled LEGEND_POP_UP | 3.2.5 | CW | 1 | 2012-02-23 |  | New
misc | ShuffleToFitContainer has a StyleSet parameter (DR) in its Creation Structure, the SizeToFitContainer does not have. Is it on purpose? Is it an omission? Also, 3.6.6 says "When the widgets are shuffled horizontally their PosX values are computed. When the widgets are shuffled vertically, their SizeY values are computed." It should say "... their PosY values are computed." | 3.6.5, 3.6.6 | VR, CW | 1 | 2012-01-09 |  | In work | 1/12/12: discussed. Fixed 3.6.6 by replacing SizeY with PosY as suggested. 2/7/12: Asked Rockwell why one of these has StyleSet and one does not. We agree ShuffleToFit should have StyleSet, it can be used to control its graphical representation. 2/22/12: Rockwell does not have a need to add it to SizeToFit. Esterel may have a need, they will advise the group.
misc | Gary has a question regarding Section 5.2.3.1 which defines the SGD LEGEND_ANCHOR command. This command sets "the anchor position for the legend attached to the symbol representation." But do we explain anywhere in the spec what these legends are and how they are defined? Who controls them, CDS or UA? | 3.3.24, 3.4.5, 5.2.3.1 | GH | 1 | 2012-02-11 |  | New | 2/23/12: This lets UA set a position for a Legend that is part of an SDL-created Symbol intended for use in an MILitemlist. It is explained somewhat in Sect 5.1 and in the MapHorz and MapVert sections. Still, it could be clearer.
misc | Dassault feels the document is not clear regarding how A661_SYMBOL_DEFN_TEXT is aligned. There is no SizeX and SizeY for the text, so how should the Alignment options be interpreted? | 5.2.3.12 | HG | 2 | 2011-09-01 |  | In work | 10/5/11: for symbols, the alignment is relative to the PosX, PosY point. Rockwell will provide a diagram. 12/5/11: Because the Alignment param specifies text justification (not positioning), there is a discrepancy between the text of 5.2.3.12 and Table 5.2.3.12. The text says the "first character of the text string is placed at the specified position and subsequent characters are drawn to the right," which implies no justification is possible. The table says the text can be positioned relative to A661_SYMBOL_DEFN_TEXT's PosX/Y, but A661_SYMBOL_DEFN_TEXT has no SizeX/Y area so some of the Alignment values (TOP, BOTTOM) do not make sense. Presagis offered to propose changes to 5.2.3.12 to remove inconsistency between text and table. We maybe should add a figure to Section 5.2.3.12. 2/6/12: received proposed re-write from Mark W. 2/11/12: A different proposal was sent by Gary. 2/23/12: figured it out, Gary's proposal withdrawn. Need new section in 3.2.5.6 to explain how text align works for widgets and for SGD symbols. Mark will update proposal.
misc | Clarify 5.2.3.13 to say how size is applied to a symbol. May also want to say there are CDS-dependent aspects of how the SIZE box is aligned on the SDL symbol. | misc | CW |  | 2012-02-23 |  | New
misc | Spelling of MapHorz, MapHorz_ItemList, MapHorz_Item and MapHorz_Source is inconsistent. Ditto for MapVert, etc. There are a few places where an extra underscore appears (e.g., Map_Horz). Remove underscore in text descriptions. However, in the tables, we do want the underscores. Table 4.6-7 is correct, but add the underscores to Tables 3.3.24-2a, etc. In Table 3.4.4-2a, A661_MAP_SOURCE should be A661_MAP_VERT_SOURCE. | misc | CW |  | 2012-02-22 |  | New
misc | Idea was put forward by Steve Ellis to combine tables of Section 4.5.4.5 into one table. Could be easier to read. Ditto for Sections 4.5.4.3 and 4.5.4.4. | sec4 | SE | 3 | 2011-06-08 |  | New | Gary said June 2010 he would draft it up so we can compare it to what we have today. 2/11/12: Gary will not be able to do that. Suggesting we reassign this item to Steve. 2/16/12: Steve provided a draft
misc | In Table 3.4.4-2b are the descriptions in the Origin column clear and consistent with the two diagrams which follow? | 3.4.3, 3.4.4 | GH | 2 | 2010-11-03 |  | In work | 6/7/11: Asked group to think about this. 12/5/11: Gary to provide a more detailed question. 2/11/12: Gary drafted changes to Sects 3.4.3 and 3.4.4. 2/23/12: discussed, new wording is pretty good. Gary to update wording and Origin column. Delete diagrams for now, they are not right. Fix them later.
N/A | create Draft 2 by April 1, 2012 with ABC pages | all | PG, CW | 1 | 2011-10-13 |  | In work | Plan was that after Feb 2012 meeting Gary would prepare files and send to Pete, then AEEC would complete the files and publish it. 2/11/12: Gary updated master document and sent to Pete. 2/21/12: Chad will work this with Pete after the Melbourne meeting
Key: |  | AM | Aubanel Monnier
|  | BB | Brady Buresh
|  | BG | Brian Gilbert
|  | BM | Brooks Moorman
|  | CW | Chad Weldon
|  | CL | Colin Layden
|  | DF | David Fairchild
|  | DH | Darren Humphrey
|  | DP | Dustin Poe
|  | GD | Greg Dorland
|  | GH | Gary Hickey
|  | HG | Herve Girod
|  | IB | Ian Bull
|  | JB | Julien Barry
|  | JB2 | Jerome Barral
|  | JF | Jean-Francois Saez
|  | LC | Lewis Catton
|  | LH | Larry Hesterberg
|  | MD | Mikon Dosogne
|  | MW | Mark Waldvogel
|  | MJ | Matt Jackson
|  | ND | Nicolas Dervaux
|  | PG | Peter Grau
|  | PJT | Pierre-Jean Turpeau
|  | PP | Pranav Patel
|  | RHS | Rob Harwood-Smith
|  | RM | Rick Mahoney
|  | SE | Steve Ellis
|  | SS | Sofyan Su
|  | VR | Vince Rossignol
Note on A4: Issues are SC discussion items. Issue# is composed of 2-digit year indicator and a sequential item number
Note on E4: 1 - high 2 - medium 3 - low
Note on G4: Must update all Affected Artifacts before item can be closed
Note on H4: New In Work On Hold Pending Done

## CompletedTasks
Completed Task List - ARINC 661 - Supplement 7
This is a list of all completed tasks
Issue# | Description | Affected Doc File | Assignee | Priority | Opened | Closed | Status | Status/Comments/Actions
08-01 | We tried out Deprecation during MLB09 mtg. We need to decide if we will adopt it going forward, or not. Would have to add a note to 2.2.5 and App G about how Deprecation will work. When we list something as deprecated in the spec it means that it is out of date, it should still be supported by the supplier, but it will be deleted from the spec someday. | sec1&2, AppG | All | 1 | MLB09 | 2009-06-17 | Done | Gary drafted changes into master docs 6/11/09 for review at Paris mtg. Reworded and adopted at PAR09. We want to include Deprecation in Supplement 4.
08-01 | Change Management topic, formerly called Backwards Compatibility. All agree the spec will change in future. Want to reduce impacts of spec changes on existing installations, while at the same time allowing us to improve the 661 spec without hindrance. A typical tradeoff we encounter is "should we add a new widget or change an existing one?" Adding a Widget Extension mechanism could be helpful, it could keep the widget count down and could reduce implementation customization/non-compliances. Should we add Extensions to A661? Or, do we add Guidelines to App G? | sec1&2, AppG | GH, All | 1 | PHX07 | 2010-07-21 | Done | Gary brought a summary document to ORL08 which was discussed 7/24. Agreed on terms. Agreed to only show latest revs in each Supplement. Drafted a list of criteria for use by SubComm when evaluating changes, Gary to finish the draft. Gary to fix Section 2.2.5, too restrictive now, needs a pointer to App G. Also want a scoring spdsht, Gary to draft one. This also spawned a new issue, Command-Based Creation Structures (See Issue 08-11, Action Item 4-11). Gary drafted a new Section 2.2.5 on 11/17/08, a draft scoresheet 12/1/08 and a note seeking alignment on key principles 12/10/08. 1/20/09 Ian provided dwgs of common scenarios encountered when updating UAs and CDS. Discussed more at MLB09. Sect 2.2.5 chgs approved. Listed a set of techniques we can employ to a) mark chgs in the spec, and b) help system designers make changes to CDS and UA with fewer impacts on those systems. Decided not to put widget version numbers in the interface. 1/13/10: Defer further action until Suppl 5. 7/21/10: Decided to close it.
08-01 | Review the scoresheet Gary created on 12/1/08, especially the weighted criteria it contains. If the scoresheet is adopted, then update the guidance in App G to be consistent with the scoresheet criteria. | AppG | GH | 1 | 2009-04-15 | 2010-07-21 | Done | 1/13/10: Defer until Suppl 5. 7/21/10: Decided to close this without adopting scoresheet.
08-01 | At MLB09 we said we should take examples of changes we made for Suppl 3 and 4, then see which of our Chg Mgmnt techniques would have been best to apply. This is a study item, not a spec change at this point. We did not always solve these issues in the best way, in retrospect. | n/a | all | 1 | MLB09 | 2010-07-21 | Done | This was an item for future study. 7/21/10: Decided to close it.
08-01 | DEPRECATED WIDGETS: the group took an unofficial Action Item in Jan 2006 to list all widgets that are not being implemented, with a view toward moving them to a "Deprecated" Widgets section someday. Also should list all currently-implemented widgets that are not in 661 but should be in 661. Is this still an action? No progress made on it since Jan 2006, when it was deferred to Supplement 4. | sec1&2, sec3e | All | 2 | PHX06 | 2010-01-19 | Done | ORL08. Pierre-Jean reminded group that someday we should begin deprecating widgets. How we do it (criteria, etc) may need to be written up in a white paper, similar to the Change Mgmnt criteria list under work. At MLB09: see previous entry, we have begun defining a way to deprecate widgets and widget features (parameters). We have identified two such items so far, but we may still need to go through the spec to find other things that should be deprecated. Try to do for Suppl 4. During 9/2/09 telecon we deprecated MapLegacy. 1/13/10: we accept concept of deprecation. Gary will move deprecation paragraph to new Section 2.2.5.1 and add note that ABC pages will contain an explanation of each deprecation. 1/13/10: changes done. Reviewed at PHX10 meeting, Adopted.
08-01 | Change Management discussions at MLB09 resulted in re-introducing the idea of Widget Extensions as a way to allow optional features to be added without rolling the spec. Not for adding required or major features. Not a free data field. Rockwell will make a proposal in which we'd define a set of Extensions and which widgets they can be applied to, and how they are to be used by UA and CDS. Would have to add note to 2.2.5 and App G about how this works. | sec1&2, sec4, sec6, AppC, newsect | IB, CW | 1 | MLB09 | 2010-01-20 | Done | PAR09: Chad presented Extensions proposal. Example is an "AddAlignmentField" extension (see item 08-04). Probably would require a new section describing the concept, mechanism and rules of use. New section will list all Extensions. For each one, list the feature it adds, its structure and the widgets it can be applied to. Also list the widget params and event params it adds. Sect 6 XML grammar is affected. App C would need an example added. Should add new error notification A661_ERR_EXTEND_ABORTED to Table 4.4.2. Attendees support the concept, will try to get this into Suppl 4. Chad will provide a more detailed proposal. Gary to send Chad his notes from the PAR09 meeting. 11/24/09 telecon: group thinks we should defer until Suppl 5. PHX10: Deferred to Suppl 5. closed this item and renamed it as AI # 10-01.
08-04 | No Alignment Field for PopUpMenu widget. All other widgets having a A661_STRING or A661_STRING_ARRAY RMP have an Alignment field. Was this an oversight or was the intent for the CDS to manage alignment? If it is the former, then the alignment field should be added. If it is the latter, this seems to be a case where CDS oversteps its authority. | sec3f | GH | 3 | PHX07 | 2011-04-14 | Done | Said in PHX07 that no change is needed. Not an oversight, intent was to allow only CDS to realign PopUpMenus. Agreed it's inconsistent, but did not think there would be much need for alignment on PopUp Menu. UA can change alignment via StyleSet if need arises. Feb 5, 2008 telecon there was Hwl/RC support for adding param but only when we solve the backwards compatibility issue, because this would impact creation structure. Airbus against for now. Discuss further after we solve backwards compatibility issue (see item 08-01). 4/14/11: closed this item with no changes to document.
08-04 | Both EBN and EBN-BCD widgets have an Alignment field which controls the justification of the entire displayed value, composed of a numeric portion (FormatString) and a text portion (LegendString). There is no independent alignment of the LegendString possible. If the UA wants to change the alignment of the numeric portion only, leaving the Legend where it is, the UA must use space padding to get the desired results. If a second alignment field (LegendAlignment) was added, then no padding would be necessary. | sec4, sec8 | GH | 3 | PHX07 | 2011-05-12 | Done | No support for change at PHX07 mtg, little support at 10/30/07 telecon. Feb 5, 2008 telecon there was Hwl/RC support for adding it but will impact creation structure, so we will discuss further after we solve backwards compatibility issue (see item 08-01). PAR09: Chad's preso on Extensions showed a way to add this without affecting existing creation structures. 3/9/11: Gary sent a proposal for an extension which adds the second alignment field. 4/14/11: presented changes to group, Ok to merge into master. 5/12/11: changes ratified by group. 6/7/11: updated with final mods.
08-07 | Discussion at MLB09 of complex interactive formats led to idea of adding UA-controllable Geographic Cursor Navigation (today only CDS can do this). Would we have to expand how connectors and/or FocusIn/Out/Link work so cursor nav can jump across layers? |  | IB, CW | 2 | MLB09 | 2009-06-18 | Done | PAR09: created new item 09-09
08-07 | Rockwell may write a proposal explaining how to create complex interactive formats composed of only basic widgets. There are certain things that cannot be done with the existing widget set. This would propose new concepts/commands/framework for combining widgets. Should also be useful as guideline mtrl for newcomers. | new Appendix | IB, PJT | 3 | 2008-05-15 | 2010-07-21 | Done | Brief discussion at ORL08. Proceed. Next step is for Ian and Pierre-Jean to collect real-life examples of formats that are hard (or impossible, even) to do with existing widget set. MLB09: Ian gave examples, such as complex menus and stepping cursor cntrls. PAR09: any new widgets related to this are covered by other items in this list. Idea for an explanatory appendix has not been worked yet. If we do not have a good draft by Jan 2010 this will slip to Suppl 5. 1/13/10: Defer to Suppl 5. PHX10: later we will see if there is still a need for this, we may have created enough new widgets to cover all the examples. 6/2/10: will address at next telecon. 7/21/10: Group agreed to close this item.
08-07 | Dassault shared examples of their CDS user interface in which PopUpMenus can contain CheckBoxes at any menu level. They do not see a way to do this with existing A661 spec. They suggest one way: allow PopUpPanel to be a child of PopUpMenu. Big change to spec. All to discuss. |  | HG | 2 | 2009-04-06 | 2009-06-18 | Done | PAR09: can be done with existing spec, e.g., each submenu can be a PopupPanel. And PopupMenu can only have other PopupMenus as children. We found a better solution, see new item 09-06.
09-01 | At Paris09, Item 09-01 led to an idea to allow UAs to define Map Symbol Parking Boundaries in the DF. CDS would have to implement the parking, with details controlled by the CDS Look&Feel. Today the spec leaves all of this to the Master Appl and/or CDS. Rockwell may present a proposal in future. | tbd | CW | 2 | 2009-06-17 | 2016-03-04 | Done | 1/13/10: Defer to Suppl 5. 6/9/11: Dassault still has a need for this. Rockwell has a solution, but it may be too implementation-dependent to put in the standard. We’ll revisit this item later. Proposal for Toulouse 5/9/12. Deferred to Supplement 6. 7/24/12. Add SymbolRotated, rework diagrams for region definition, show use case, add circular, rectangular and triangular cutouts 7/11/13. Update for Paris 3/10/15. Update diagrams and language, insert into Master for Toulouse. Minor update for 3/4/16.
09-09 | UA-controllable Widget Focus Navigation. Allows UA to change order at runtime, and the order is richer than before. Would we have to expand how Connectors and FocusIn/Out/Link work so cursor nav can jump across layers? | sec4, sec8 | IB, CW | 2 | PAR09 | 2011-06-07 | Done | 12/13/10: Chad showed new proposal, now implemented as a widget extension. Uses an array of widget idents and a NumberOfDirections param. Should be no effects on Connectors and FocusIn/Out/Link. Chad will revise proposal to explain that idents are listed in the array in a certain order, with their direction to be inferred from the NumberOf Directions working clockwise. Chad made updates 12/13/10. Gary merged these revisions into the master files. 1/11/11 Gary added proposed description section wording and editorial changes. 2/10/11: Reviewed these, Chad will correct/improve the wording. 3/10/11: agreed that this is Widget Focus Nav, not Geo-Focus Nav. This will cause some re-wording. 03/24/11: Gary sent markups to Rockwell. 4/14/11: markups OK. 6/7/11: agreed on final wording, changes merged.
10-02 | Consider adding SYMBOL_RECTANGLE to Map_Vert. We specifically did not do this for Supplement 4, but may want to reconsider this. The orientation parameter would have to be converted to be relative to 12 o'clock instead of true north. | sec3f | IB, CW | 1 | PHX10 | 2010-09-22 | Done | 6/2/10: will address at next telecon. 7/21/10: decided to add it to MapVert as Section 3.4.5.2.1.21. It is interactive. 9/22/10: Agreed on markups, master file updated.
10-03 | Review list of all previously deprecated items to see if any should be deleted in Supplement 5. Most notably, we might delete MapLegacy for Suppl 5. | sec3a, sec3e, sec4 | GH, all | 1 | PHX10 | 2010-09-22 | Done | This review should be done for every Supplement. 7/21/10: Yes, delete MapLegacy. 9/22/10: Agreed on markups for deleting MapLegacy, master files updated.
10-04 | Ian noticed in early 2009 that the wording of 3.3.6 ComboBox Widget Description is still inadequate. He and Gary worked out some new wording for this and related widgets (3.4.7 ComboBoxEdit, 3.5.7 SelectionListButton), Julien provided comments. Sections 3.3.31 and 3.3.32 may also need cleanup. This was part of Item 08-17. For Suppl 4 we could not reach agreement. There are basic differences today in the Sub-Committee member's understanding of these widgets' appearance and function. We want to avoid inadvertantly redesigning these widgets from their original purpose: if we need something new we should create new widgets. Although the original 661 wording is vague, we need to reach agreement on what the original purpose was before we can clarify the widget descriptions. | sec3b, sec3f | IB, GH | 2 | PHX10 | 2011-06-08 | Done | 6/8/11: Decided to Close out this item with no further action.
10-04 | During the discussion on ComboBox clarifications at Paris09 (formerly part of item 08-17) it was suggested that ComboBox Selected Entry could be displayed as an abbreviated string to save screen space, as part of the CDS Look&Feel. It was also suggested that the CDS could even choose, as part of Look&Feel, to not display Selected Entry at all. We talked about adding this to a COMMENTARY in the ComboBox Section 3.3.10. Gary noted that this would constitute a functional change to the widget. | sec3b | GH | 2 | PAR09 | 2011-06-08 | Done | It was never the intent of the Sub-Committee to encourage CDS to abbreviate LabelStrings or otherwise significantly alter the content of the data the UA has sent for display. If we did allow this, it may not be appropriate for Air Transport aircraft: it could be hard to certify an HMI that allowed abbreviations because the crew could misinterpret abbreviated items and because of the high number of possible abbreviations (thus hard to do V&V on the system). If we do make this functional change, Gary suggests we add a commentary saying it is not recommended for use on AT. 6/8/11: Decided to Close out this item with no further action.
10-06 | Greg asked that we consider adding multi-selection capability. Boeing sees a use for this in certain applications. Would apply to widgets with selection lists (e.g., ScrollList). In order that this feature not lead to unsafe HMI choices on a critical function (especially for Air Transport applications), Gary suggests the feature be controlled by a Enable/Disable flag. | tbd | CW | 2 | 2010-06-02 | 2016-01-13 | Done | All to look at the desirability, feasibility and impact of adding this. Greg will write a paper describing how this would be useful. 6/9/11: Rockwell has implemented this and is willing to present it to the group. Deferred to supplement 6. 5/9/12. Continue to defer to Supplement 6. Adding RC to this issue because they now have an implementation 7/24/12. Update for Paris. Convert to an extension. Updated for 11/19/15. All to review their implementations to see if indexing via a CDS managed list. Update language re: different indexing approaches and insert into Master for 01/13/16. Reviewed and completed 1/13/16.
10-07a | Effects of Touchscreen on ARINC 661. At Telecon of 11/24/09 Pierre-Jean noted that touchscreen and other new technologies could affect ARINC 661. For example, our basic rules against window resizing and double-clicking may need to be revisited. Double-tapping and two-finger stretching, etc may make resizing and double-clicking safe enough for AT. Certainly some new parameters or even new widgets might be needed. We may also have to revisit our use of the term "click" when we mean "select." In Nov 2009 we thought this was an item for future study, but on 6/2/10 we decided to begin looking at this topic in the Suppl 5 timeframe, especially as regards Multi-Touch. | tbd | GD | 2 | 2009-11-24 | 2014-06-11 | Done | Greg will write a paper describing how Multi-Touch would be useful. 6/9/11: quick discussion on this. Touchscreen input devices are coming soon. They will likely result in new events and maybe new widgets. Need to address this later this year. We do not want to wait too long, should get this into Suppl 5. 2/23/12: Not ready to propose doc hcanges yet, probably will not get into the document until Supplement 6. Everyone should look for use cases. Deferred to supplement 6 5/9/12. Deferred to Supplement 6 to find use cases. 7/24/12. Presented 12/9/13, updated and presented 1/13/14. All to provide inputs to Brian to help define the gesture set. Updated for 2/12/14. Presented in Bordeaux, updated 4/9/14. Presented, accepted and completed 6/11/14.
10-07b | May want to create a widget extension to support cursor events that are needed to support touchscreen interactivity. Would include events and gestures such as CursorDragged, Pinch, Stretch, Throw?, Box, Circle, etc. This would look like the CursorEvents extension, but the event structs would be more complicated because each such event would require one or more data parameters. | sec4, sec8 | GD | 1 | 2010-12-13 | 2014-06-11 | Done | Deferred to Supplement 6 to find use cases. 7/24/12. Presented 1/9/14. Update for 2/12/14. Presented in Bordeaux, updated 4/9/14. Presented, accepted and completed 6/11/14.
10-08 | Gradient Rectangle. New widget proposed by Rockwell Collins. Similar to gpRectangle but has two colors. SDL is affected too, a new SDL command would be added. | sec3a, sec3g, sec4, sec5 | CW, BM | 1 | 2010-07-21 | 2011-08-03 | Done | Rockwell provided proposal 2/10/11. Reviewed 3/10/11. 6/8/11: Decided not to add this widget. Too complex. Can use FillIndex and StyleSet to do gradients. FillGradient Extension will be pursued instead, see item 11-10. 7/15/11: Gary removed GradientRectangle from master. Will close by Aug 3 if no further comments from group.
10-09 | gpPolyLine. New widget proposed by Rockwell Collins. Lets you specify an array of vertices, saving bus bandwidth usage. | sec3a, sec3g, sec4, sec5, sec8 | CW, BM | 1 | 2010-07-21 | 2011-08-03 | Done | Rockwell provided proposal 2/10/11. Reviewed 3/10/11, Rockwell will revise proposal to add event table, close param, and maybe a fill param. Will need a 4-Byte Array param structure. 4/23/11: Gary drafted changes to Section 4.5.4.5. 5/25/11: Corrected name of Section 4.5.4.5.20. Added pad to CellStructure. 6/8/11:studied new proposal, changed it a bit, adopted widget. Corrected Section 4.5.4.5.19/20. In 5.3.2.7 we deleted sentence saying it does not correspond to any gp widget. 7/24/11: Gary merged remaining changes into master files. Will close by Aug 3 if no further comments from group.
10-11b | Can Mapcontainer also be be a child of MapVert_Source? Why not? |  | CW, BM | 1 | 2012-02-22 | 2012-07-24 | Done | Found was moved to 12-04. 7/24/12.
10-12 | Dassault noticed that the Slider Creation Structure Table 3.5.4-2 does not include AutomaticFocusMotion. Proposed solution is to put AutomaticFocusMotion in the 8-bit UnusedPad. | sec3f | HG | 1 | 2010-07-23 | 2010-09-22 | Done | RC, Hwl and Presagis are Ok with proposed fix. 9/22/10: added it to creation structure, master file updated.
10-13 | Dassault has a need for a way to let the UA count how long the user holds down the select button on an object. They suggested a new Click & Hold widget. Julien and Chad suggested using a widget extension to add new cursor events to the Active Area widget. this would include an event array. We could add new events to the array going forward. We think this will meet Dassault's need. For now, we need to put a Press event and a Release event in this array and add them to Active Area via an "add Cursor Events" extension. | sec4, sec8 | JB2, JB | 1 | 2010-11-03 | 2011-04-14 | Done | 12/13/10 Discussed Dassault proposal for new Extension which adds cursor events. It had an event array, but we decided to remove array because it is simpler to have CDS send one event at a time. If we kept the array, we would not want it to be a free-form space, so we'd have to give guidance on how CDS loads the array, and how UA processes it. Cannot have events processed in wrong order. Removed DRAGGED event type. It is OEM-dependent exactly how widget events are translated into "selection" of a widget. 1/17/11: Jerome sent updated proposal. Replaces event array with bit mask for indicating which events UA wants to add to the widget. 2/10/11: Several concerns were raised. Not sure UAs should decide which events to process. Bit mask contents should be standardized and CDS should only send one event per cmd. Chad will send a re-write to Jerome. 2/22/11: Gary sent comments. 4/14/11: Superseded by re-write from Chad.
10-13 | Proposed re-write from Chad replaces EventMask with an EventArray containing enumerated values. Array tells CDS which event types the UA will accept. Also, there is one generic Cursor Event which sends an enumerated value indicating which event type occurred. | sec4, sec8 | CW | 1 | 2011-03-10 | 2011-05-25 | Done | Discuss at next telecon. Generic Event containing actual event that occurred is a new concept, first time we have done that in ARINC 661. 4/14/11: accepted by group. Gary will merge into master. 5/12/11: Accepted by group, but Gary must replace the word "BitMask" with "parameter." Gary to add remaining Event codes to Section 4. 5/25/11: Gary made changes.
11-01 | A new widget called ScalingContainer was proposed. Allows X/Y translation via separate X and Y percentage parameters. | sec3a, sec3g, sec4, sec8 | HG | 1 | 2011-04-11 | 2011-11-07 | Done | 4/14/11: discussed. Want to rename it since it does not scale graphics, it is another way of translating graphics. 5/12/11: Discussed updated Dassault proposal for ScaledTranslation widget. Want to rename some params, add a StayInBounds param, and change translation factor datatype to fr(1). 5/19/11: Dassault sent updated proposal. Should scaling factors be fr(1) or float? 5/26/11: Gary merged proposal into master. 6/7/11: Deleted the StayInBounds flag, adopted the widget. Master files sec3g and sec4 updated. 7/15/11: Gary added it to Table 3.2.3.1. 7/28/11: Will close by Aug 3 if no further comments from group. 9/1/11: Steve suggested changes to clarify positioning and translation operation...see next row in this table. Completed during 11/7/11 telecon. This widget was removed as a result of adotion of the DataScaling widgets. 7/25/12.
11-01 | Confirm what we agreed upon in Cheltenham: Do we want to say "Widgets placed within a ScaledTranslationContainer have their coordinates referenced from TranslationX and TranslationY" or "Widgets placed within a ScaledTranslationContainer have their coordinates referenced from the position given by StartTranslationX and StartTranslationY" ? | sec3g | GH, SE | 1 | 2011-07-28 | 2011-11-07 | Done | 9/1/11: their coordinates are referenced fromTranslationX and TranslationY. Steve Ellis provided clarifying text for Section 3.8.3 that was adopted at telecon. 9/16/11: Steve sent a new writeup. 9/22/11: Gary put Steve's Sep 1 wording in the master, for Draft 1, since that was accepted on 9/1/11. We agreed on Steve's wording at 11/7/11 telecon.
11-01 | Need a small update to the wording of Section 3.3.42 TranslationContainer. | sec3f | GH | 1 | 2011-06-07 | 2011-06-07 | Done
11-01 | How should non-linear translation be handled? By the UA? By the CDS using StyleSet or some other mechanism? By Extensions? | sec3g | PJT | 1 | 2011-07-07 | 2011-07-28 | Done | 7/28/11: Could add a param which specifies the various linear and non-linear xlation types, but it would be hard to arrive at a suitably complete list. Instead, we added a statement saying "By default the translation is linear" to the widget description. And we will address this issue further when we work on ScaledRotationContainer (item 11-05).
11-01 | Two counter-suggestions: GE suggested it should use UA coord units instead of screen coords. | sec3a, sec3g, sec4 | LC | 1 | 2011-04-14 | 2011-09-01 | Done | Lewis was going to offer a proposal. 7/28/11: Will close by Aug 3 if no further comments from group. 9/1/11: item closed, intent was met by other items.
11-02 | Dassault wants to propose a Numeric Readout widget to provide a better way to display numeric readouts (to overcome deficiencies when using Label widget for readouts). Sort of like a Label widget with an EBN-like format string added. | sec3a, sec3g, sec4, sec8 | HG, JB2 | 1 | 2011-04-14 | 2011-08-03 | Done | 5/12/11: Discussed proposal. Delete Enable param, delete description of anonymous-related operation. Add more descriptions of this widget's use. 5/19/11: Dassault sent updated proposal. 6/7/11: discussed and adopted widget after more edits. 7/15/11: Gary added this to the Master files. Will close by Aug 3 if no further comments from group.
11-02 | The idea was raised that if a disabled version of an interactive widget would be useful, and if there are more than 2 or 3 such widgets, then we should create an extension to do that instead of creating new widgets. Creating an extension would mean we would not need the new NumericReadout widget. | misc | PJT, All | 1 | 2011-05-12 | 2011-07-28 | Done | 5/12/11: The group should survey all interactive widgets before the June meeting. 7/15/11: did not discuss at CHL 11 meeting. 7/28/11: probably not enough use cases for this, we dropped the idea.
11-03 | A new widget called ImageViewer was proposed by Honeywell. Like a ScrollPanel but the Sheet being scrolled is a bitmap image. Combines elements of ExternalSource and ScrollPanel. | sec3a, sec3g, sec4, sec8 | ???? | 1 | 2011-04-23 | 2013-09-05 | Deleted | 5/12/11: Discussed proposal. Seems to be a need for this, Dave asks if it should be a new widget or a change to ExternalSource? Gary to provide a detailed proposal. 6/8/11: discussed more, leaning toward adapting ExternalSource to accept bitmaps. UA would then place an ExtSrc in a ScrollPanel. A detailed proposal is needed. 2/23/12: Dustin volunteered to work on this. Deferred to Supplement 6 7/3/12. Continue as deferred to Supplement 6 7/24/12. Deleted 9/5/13.
11-06 | Correct the ScrollPanel figure. Xframe/Yframe labels s/b FrameX/FrameY. And the Window is really the Parent Container of the ScrollPanel. Also need some minor editorial changes in Section 3.3.36. | 3.3.36 | PJT | 1 | 2011-06-08 | 2012-02-21 | Done | Group members will check their implementation to see if they all did it per the document. Hopefully everyone did it the same way. Discuss at next telecon. 2/7/12: Gary changed the figure so that it matches what the Widget Description and Param table text says. 2/21/12: finalized words and figure, made it Dynamic Motion.
11-07 | VisibleChildIndex Extension. We agreed to stay with the current convention of using WidgetIdent to refer to children in TabbedPanelGroup, MutuallyExclusiveContainer and PagingContainer. So, should we add an extension that would force the use of 0 to N instead of WidgetIdents? | sec4, sec8 | LC, CW | 1 | 2011-03-10 | 2011-08-03 | Done | 6/8/11: discussed proposal from Rockwell. Adopted it. 7/15/11: Gary added it to Section 8 master file. 7/28/11: Added to Section 4. Will close by Aug 3 if no further comments from group.
11-08 | Suggestion was made by GE Aviation for a Broadcast widget. Similar to BufferFormat widget, basically has the same parameter list, but at runtime the UA does not have to send multiple <value>s, it only has to send one <value>. Lewis will write a proposal. | sec3a, sec3g, sec4, sec8 | LC, HG | 1 | 2011-04-14 | 2012-02-21 | Done | Chad added new table 12/13/10. Gary merged it into the master files. Complete the table later, when Suppl 5 is being finalized, listing the Extensions alphabetically.
11-08 | Rob Harwood in his suggestion FSS8 wrote "There is potential for “flicker” on the CDS if the messages are processed in different update cycles, recommend this is considered by committee and a suitable note is added, either permitting it with caveats or recommending avoidance of this practice, or saying risk of flicker is CDS vendor implementation dependent." |  | RHS |  | 2012-02-06 | 2012-02-22 | Done | discuss at next meeting. 2/22/12: added COMMENTARY to Bufferformat and BroadcastReceiver
11-09 | Rockwell offered to propose a new gp-like widget for creating Filled Polygons using polygons, triangle strips and/or fans. | sec3a, sec3g, sec4, sec8 | CW | 1 | 2011-06-08 | 2012-02-21 | Done | 2/21/12: This widget will not be pursued. There are other ways to get the same effect, and the new widget would be difficult to create.
11-10 | Rockwell gave a proposal for a FillGradient Extension. Seems good, an updated proposal will be provided. | sec3a, sec3g, sec4, sec8 | CW | 1 | 2011-06-08 | 2012-02-21 | Done | 2/21/12: This widget will not be pursued. Can do with FillIndexStyle.
12-04 | Create a MapVertContainer widget that can be a child of MapVert_Source. Similar to MapHorzContainer but will have parameters to support placement on Vertical maps. |  | CW, HG | 1 | 2012-02-22 | 2016-01-13 | Done | Brooks to update for Toulouse 5/9/12. Chad and Herve to discuss and present at next telecon. 12/6/12. Defer to Supp 6 1/10/13. Insert into document for final review 12/14/15. Make edits for review 01/13/16.
12-06 | Propose a new widget called MapVertContainerInteractive if we create a MapVertContainer. Unlike MapVertContainer, this one would be able to contain interactive widgets. Will have to address effects of map translation and scaling on its children. A child of MapVert_Source only. |  | TBD | 1 | 2012-02-22 |  | Withdrawn | Withdraw? Confirm with Thales and Esterel 5/9/12. Defer to Supp 6 along with MapVertContainer 1/15/13. Combined with 12-04 into a single item.
12-19 | Should we add an MapDataOffScreen event, etc to MapHorz_ItemList and MapVert_ItemList? | 3.3.24, 3.4.5 | BG, DP |  | 2012-02-22 |  | Withdrawn | Some preliminary work done by Dustin. Dustin to review with Brian who will present in Toulouse 7/3/12. Deferred to supplement 6 1/10/13. Combined with 13-12 into a single item.
12-20 | Counter-proposal to item 10-13 AddtlCursorEvents Extension: Pierre-Jean may propose a new widget call INTERACTION_AREA which would replace ActiveArea, CursorOver, CursorPosOverlay and would meet the need of ClickAndHold. And it would be extensible too. If we add this new widget, we would have to look at deprecating the replaced widgets. | sec3a, sec3g, sec4, sec8 | PJT | 1 | 2010-11-04 |  | Withdrawn | There are installations using Active Area and CursorOver. 2/23/12: Pierre-Jean explained issues that would be encountered with this. Proposal for Toulouse 5/9/12. Deferred to Supplement 6 7/25/12. Closing this issue as a part of 10-07 7/26/12.
13-1 | Symbol Reference/Scaling SDL Commands |  | DA/PRE |  |  |  | Done | Herve verified complete 9/15/15.
13-2 | Map Frame Proposal |  | AB/B |  |  |  | Withdrawn | Supplanted by 13-15
13-3 | Modify Shuffle to Fit and Size to Fit for Off Axis Issues |  | ES |  |  | 2014-03-13 | Withdrawn | Updated in Bordeaux. Withdrawn to rely on Styleset, closed 3/13/14..
13-5 | Multi-State Toggle Button |  | B |  | 2013-12-09 | 2014-03-13 | Done | Presented and agreed to 12/9/13. Brian to make changes and insert into master document in Bordeaux 3/13/14. Presented, accepted and closed 5/7/14.
13-6 | InteractiveScrollWheellArea/InteractiveKeyBoardArea |  | AB |  |  | 2015-01-22 | Done | Presented, accepted and closed 1/22/15.
13-7 | Styleset Extension/Impact on Look Modeling |  | B/DA |  |  | 2015-03-11 | Done | Presented, accepted and closed 3/12/15.
13-8 | Highlight Extension |  | B |  |  | 2014-03-13 | Withdrawn | Dependent on 13-17. Discussed and agreed to handle now with Styleset. Closed 3/13/14.
13-9 | Picture and Symbol Extensions |  | DA |  |  | 2014-09-18 | Done | Presented 1/13/14. Reviewed, modifications to be made and inserted into document with commentary for Annapolis 9/16/14. Made final corrections, reviewed and accepted 9/18/14.
13-11 | Data Connector |  | RC |  |  | 2016-03-04 | Done | Revise, update and present for insertion into document in Toulouse. Minor update for 3/4/16.
13-12 | OutofBounds/InBounds, Boundary Check Extension |  | B |  |  | 2016-02-25 | Done | Combined with item 12-19. Presented 12/9/13. Update for Toulouse. Make corrections in document for 2/25/16. Verified complete 2/25/16.
13-13 | Revise Mask Container definition |  | ES |  |  | 2014-09-18 | Done | Proposal for Bordeaux. Presented, agreed to insert into master. Reviewed 3/13/14. Final review with minor changes accepted 9/18/14.
13-14 | Clarify number of Dfs per UA (entire document) |  | ES |  |  | 2014-09-18 | Done | Proposal for Bordeaux. Presented, agreed to insert into master. Reviewed 3/13/14. Completed and accepted 9/18/14.
13-15 | Parameter Synchronization (Framing refresh container) |  | FLX/RC |  |  | 2016-03-04 | Done | Reviewed in Bordeaux. Updated for Paris. Reviewed in Seattle. Rob to update for Toulouse. Rob to update cross-references for 3/4/16.
13-16 | Post WIMP |  | B/RC |  |  | 2014-11-20 | Withdrawn | Superceded by 14-13, EventHandler widget.
13-17 | OppositePosSizeFit Extension |  | ES |  |  | 2014-03-13 | Withdrawn | Update for Bordeaux. Withdrawn to rely on Styleset and closed 3/13/14.
13-18 | Vertex Array |  | GE |  | 2013-10-15 | 2014-06-11 | Done | Presented 12/9/13. Reviewed document additions and completed 6/11/14.
14-1 | Picture Block/Symbol Block Structures |  | PRE |  |  | 2014-09-18 | Done | Check implementations to see if your CDS allows zero or more occurrences for Bordeaux. Completed discussion 3/11/14. Mark to correct document for Annapolis 9/16/14. Reviewed and accepted 9/18/14.
14-2 | Address inconsistencies in Supplement 5 to ARINC 661 |  | ES |  |  | 2014-10-23 | Done | Proposal for Bordeaux. Some corrections made 3/11/14, ES discovered errors for Visible Child Index Ext, inserted changes. Paging container to be modified. Brian to modify InitialFocusExtension and FocusStopExtension (14-15). Rob to make GBK changes (14-16). Paging Container and Visible Child Index to be corrected with Errata on Item 14-8. Reviewed and accepted 10/23/14.
14-3 | Standardize terminology in A661 (OEM Dependent, CDS Specific, CDS Dependent, CDS-Dependent, Implementation Specific, Implementation Dependent). |  | GE |  |  | 2015-02-18 | Done | Discussed in Bordeaux. Coalescing on Implementation Dependent. Dave to look at and include the definition in Glossary. Completed with Draft 1 of Supplement 6.
14-4 | DSL |  | AB/DA/THES/PRE |  |  | 2015-09-15 | Done | Pierre-Jean presented an XML schema definition of the DSL for widget specification 6/11/14. To be refined for Annapolis 9/16/14. Working group to continue monthly teleconferences, define primitives and provide updates in Seattle. Group determined to remove this as an A661 Part 1 Action Item in Seattle 9/15/15. Actions to be covered in Part 2 Action Item List. Periodic updates to be given to Subcommittee.
14-5 | InkArea widget |  | B |  | 2014-03-12 | 2014-06-11 | Done | Presented in Bordeaux. Presented and completed 6/11/14.
14-6 | MapInkArea widget |  | B |  | 2014-03-12 | 2014-03-12 | Withdrawn | Presented in Bordeaux. Deemed unecessary- can be achieved with an InkArea Widget in a MapPanel; withdrawn and closed 3/12/14.
14-7 | Update Update Definition File Integration Process figure 4.2.2 |  | PRE |  |  | 2016-03-04 | Done | Modify as discussed on 3/12/14. Propose new wording and relocate figure 4.2.2 closer to beginning of document for Toulouse. Insert into Master for 3/4/16.
14-8 | Prepare Errata for Supplement 5 |  | ES |  |  | 2014-10-23 | Done | Prepare Supplement 5 Errata for Paging Container and Visible Child Index completed. Reviewed and accepted 10/23/14.
14-9 | Compose Chapter 2 verbiage for multi-touch and touchscreen events |  | B |  |  | 2014-10-23 | Done | Outline multi-touch and touchscreen events. Reviewed and accepted 10/23/14.
14-10 | TicsArray and NumericEdit Extensions |  | DA |  |  | 2015-01-22 | Done | Herve made final corrections and inserted into document 1/22/15.
14-11 | Animations proposal |  | DA |  |  | 2016-03-04 | Done | Herve presented on teleconference 7/30/14. Some questions whether this could be accomlished with DSL. Provide use cases for 11/20/14. Update types/widget ID for Paris. Extension concpet dropped. Updated for April WebEx and segregated into two separate actions. This action item for the widgets remains. Insert into document for July WebEx. Formed a new action item (15-11) for Animation Laws. Update tables and definition order for September WebEx. Mark to review for 01/13/16 in combination with 15-11, possible name change, reserve space for standard animations. Herve to insert into master for Toulouse. Herve to make minor corrections for 3/4/16.
14-12 | Clarify inconsistencies |  | GE |  |  | 2014-10-23 | Done | Change chapter 3 widget types to match those in chapter 4, relocate notation table to 3.3, uchar errors and numbering errors in 3.3. Reviewed and accepted 10/23/14.
14-13 | EventHandler Widget (formerly Parameter Link Extension) |  | BA |  |  | 2016-02-25 | Done | Converted to widget EventHandler. Update for Toulouse Make corrections in document for 2/25/16. Verified complete 2/25/16.
14-14 | Update 3.1.1: User Ident may or may not be the UserIdent in the definition file |  | B |  |  | 2015-04-22 | Done | Reviewed and accpeted final updates on 4/22/15.
14-15 | InitialFocusExtension and FocusStopExtension |  | B |  |  | 2014-10-23 | Done | Reviewed and accepted 10/23/14.
14-16 | GBK changes |  | ES/FLX |  |  | 2015-09-15 | Relocated | Vince to coordinate with Rob for Paris 3/10/15. Matt to coordinate with ES, FLX, and PRE for Seattle. Rolled into item 15-10.
14-17 | Modify cursor management language Sec 2.3.5 |  | PRE |  |  | 2015-09-15 | Withdrawn | Mikon to review for September WebEx. Withdrawn at the Seattle meeting.
14-18 | Review document for proper use of "event" |  | AB |  |  | 2015-03-12 | Done | Reviewed and accepted 03/12/15.
15-1 | Correct textual widget extension listings and extensions table |  | BA |  |  | 2015-03-12 | Done | Reviewed and accepted 03/12/15.
15-3 | Standardize an XSD for Chapter 6 |  | DA/AR |  |  | 2016-03-04 | Done | Herve to propose language and placement of links to replace tables for Toulouse. Mark/Mikon to review and suggest modifications for 2/25/16. Review XSD for new rule comliance. Mark to make minor wording changes for 3/4/16. Pete to establish support files on ARINC server once revisions are agreed upon.
15-4 | Replace tables in App J with annotated XSD |  | DA/AR |  |  | 2016-03-04 | Done | Herve to propose language and placement of links to replace tables for Toulouse. Herve to renumber sections, renumber figures as required and insert URL for 2/25/16. Revisions complete. Pete to establish support files on ARINC server with circulation draft.
15-5 | Replace tables in App K with annotated XSD |  | DA/AR |  |  | 2016-03-04 | Done | Herve to propose language and placement of links to replace tables for Toulouse. Herve to renumber sections, renumber figures as required and insert URL for 2/25/16. Revisions complete. Pete to establish support files on ARINC server with circulation draft.
15-6 | Add new section to Appl to discuss the use of proxy UAs to reduce latencies |  | FLX |  |  | 2015-09-16 | Done | Reviewed and accepted 09/16/15.
15-7 | LayoutBuffer extension |  | PRE |  |  | 2015-10-08 | Done | Reviewed and accepted 10/08/15.
15-8 | Specification of an FR value and Arrays of X,Y values in XML. |  | DA |  |  | 2015-07-29 | Done | Verfied complete 7/29/15.
15-9 | Propose wording for April WebEx (complete). Sofyan to update InteractiveKeyboardArea and InteractiveScrollWheelArea. |  | B/AB |  |  | 2015-05-21 | Done | Reviewed and accpeted 5/21/15.
15-10 | Character Coding Suggestions |  | PRE |  |  | 2016-03-04 | Done | Insert into Master for Toulouse with diagram revisions and wording edits. Minor updates for 3/4/16.
15-11 | Animation Laws (see item 14-11) |  | DA |  |  | 2016-02-12 | Done | Separate action item derived from 14-11. Update with new examples and insert into Master for Toulouse. Completed 2/25/16.
15-12 | Editorial corrections |  | GE |  |  | 2015-09-01 | Done | Reviewed and accepted 9/1/15.
15-13A | Consider the impact of OEM data on Appendix K |  | DA |  |  | 2017-06-20 | Done | Herve to distribute white paper summary of changes. Reviewed schema changes and agreed completed 6/20/17.
15-13B | Update Daptiv file structure to reflect Supplement 7 files |  | RC |  |  | 2016-09-15 | Withdrawn | Subcommittee agreed to retain existing Daptiv file structure.
15-14 | Clarify XML value reperesentations (Appendix C) |  | PRE |  |  | 2016-02-25 | Done | Proposal for Toulouse. Completed 2/25/16.
15-15 | Update figure 2.3.4 and section 2.3.4.2 description. |  | AB |  |  | 2017-09-25 | Done | Insert into Master for Phoenix. Presented and accepted 9/25/17.
15-16 | Custom Data Elements (Look Modeling) |  | DA |  |  | 2017-06-20 | Withdrawn | Subcommittee agreed to pass on this request.
16-1 | MultiLabel Modifications to Layout Buffer |  | PRE |  |  | 2016-02-25 | Done | Proposal for Toulouse. Mikon to update examples in App C for 2/25/16. Completed
16-3 | Review document for other OEMxxx occurences for potential change to Implementation Dependent. Remove Section 1.8. |  | AR |  |  | 2016-03-24 | Done | Corrected for circulation draft.
16-6 | Gesture Abort State Pink Page |  | PRE |  |  | 2016-04-21 | Done | Mikon to propose Pink Page revisions to be circulated and approved by subcommittee before distribution.Proposed revisions reviewed and accepted by subcommittee.
16-7 | Touch Abort State Pink Page |  | PRE |  |  | 2016-04-21 | Done | Mikon to propose Pink Page revisions to be circulated and approved by subcommittee before distribution. If simple, will be included in Supplement 6, if complex, will be included in Supplement 7. Proposed revisions reviewed and accepted by subcommittee.
16-8 | ExternalSource widget (merged with 16-23) |  | PRE |  |  | 2017-05-23 | Done | Mikon first proposed on the 4/14/16 WebEx. To be revised and updated for 5/12/16. Modified to drop MapHorz 5/12/16. Update for Warsaw 3/27/17. Proposed revisions reviewed and accepted by subcommittee.
16-9 | Data Scaling FR180 Widget Type Constant |  | RC/AR |  |  | 2016-09-01 | Done | Update in Supplement 6 published version. Completed with published version 9/1/16.
16-11 | MaskContainer widget |  | DA |  | 2016-06-07 | 2016-09-15 | Done | Herve to make Pos X and Pos Y parameters runtime modifiable and add motion allowed parameter in pad when new master is available. Proposed revisions reviewed and acepted by subcommittee.
16-12 | New MapItem types: ParkSymbolRotated, ParkSymbolRotated_Interactive, ParkSymbolTarget, and ParkSymbolTarget_Interactive and MaskContainer parameters |  | DA |  | 2016-06-07 | 2016-12-15 | Done | Correct typos and update for next WebEx 12/15/16.
16-13 | Add MaxItemSize parameter to MapHorz and MapVert widgets |  | AB |  | 2016-06-07 | 2017-06-20 | Done | Reviewed and accepted by subcommittee.
16-14 | ScaleContainer widget |  | DA |  | 2016-06-07 | 2016-12-15 | Done | Herve to add Center X and Center Y parameters and examples. Update with more example diagrams and description for next WebEx 10/20/16. Revise wording for next WebEx 11/17/16. Reviewed and agreed 12/15/16.
16-15 | ReorderExtension for widgets |  | DA |  | 2016-06-07 | 2016-12-15 | Done | Renamed from ZOrder to ReorderExtension. Update with corrections and use case for next WebEx 11/1716. Insert into Master for next Webex 12/15/16.
16-16 | Review use of of the word Layer |  | AR |  | 2016-09-15 | 2017-02-21 | Withdrawn | Subcommittee agreed to leave as is.
16-18 | Table 3.3.24-2b X/Y lat/long clarifications and propose MapDataFormat clarifications |  | PRE |  | 2016-09-15 | 2017-05-23 | Done | All to review questions for Warsaw 3/27/17. Mikon to add commentary regarding distance and defining that X implies East and Y implies North for direction. Proposed revisions reviewed and accepted by subcommittee 5/23/17.
16-19 | Appendix E clarifications |  | PRE |  | 2016-09-15 | 2017-03-31 | Withdrawn | Withdrawn in Warsaw 3/31/17.
16-20 | TabbedPanelGroup |  | DA |  | 2016-10-20 | 2017-04-26 | Done | Reviewed and accepted by subcommittee.
16-21 | FigureSpaceCharacter |  | FLX |  | 2016-11-17 | 2017-07-18 | Done | Reviewed and accepted by subcommittee.
16-22 | Allow pictures to rotate |  | ELB |  | 2016-11-17 | 2017-06-20 | Done | Reviewed and accepted by subcommittee.
16-23 | ExternalSource widget |  | RC |  | 2016-11-17 | 2017-03-27 | Closed | All to review their implementations to check feasibility of reclassifying as not a container for Warsaw 3/27/17. Subcommittee agreed not a container. Closed and consolidated into Action Item 16-8.
16-24 | Character encoding corrections for Map item types and Legend Combo |  | FLX/PRE |  | 2016-12-15 | 2018-04-19 | Merged | Merged with Action Item 18-11 on the 4/19/18 WebEx.
16-25 | Standardize common keycodes |  | AB |  | 2016-12-15 | 2018-03-13 | Done | Updated and presented in Paris. Reviewed and accepted by subcommittee.
17-1 | Selector widget (renamed from Switch widget) |  | TH |  | 2016-11-25 | 2018-01-11 | Done | Reviewed and accepted by subcommittee.
17-2 | FormatString proposal |  | RC |  | 2017-02-21 | 2018-04-19 | Done | Reviewed and accepted by subcommittee.
17-3 | Supplement 6 clarifications |  | .FLX |  | 2017-01-19 | 2017-07-18 | Done | Reviewed and accepted by subcommittee.
17-4 | Additional Supplement 6 questions |  | ES |  | 2017-03-28 | 2017-06-20 | Done | Reviewed and accepted by subcommittee.
17-5 | MapBoundary update |  | RC |  | 2017-03-28 | 2017-06-20 | Done | Reviewed and accepted by subcommittee.
17-6 | Animation widget clarifications |  | DA |  | 2017-03-28 | 2017-05-23 | Done | Subcommittee reviewed and accepted changes 5/23/17.
17-7 | Update MapVert units and types |  | AB |  | 2017-03-28 | 2017-09-26 | Done | Sofyan to propose update for Phoenix. Presented and accepted 9/26/17.
17-9 | Create summary description table for symbols |  | GE |  | 2017-03-28 | 2018-09-25 | Done | Lewis to create for 9/24/18 Montreal. Presented and accepted 9/25/18.
17-10 | Create summary description table for extensions |  | DA |  | 2017-03-28 | 2017-09-26 | Done. | Herve to insert into Master for Phoenix. Presented and accepted 9/26/17.
17-11 | Look Modeling schema updates |  | DA |  | 2017-06-21 | 2018-03-13 | Done | Subcommittee reviewed and accepted changes 3/13/18. Herve to create ReadMe file which will track changes in the support files.
17-12 | Correct Lat/Long discrepancies in Appendix E |  | PRE |  | 2017-07-18 | 2017-10-31 | Done | Mark to update for October 31 WebEx. Presented and accepted 10/31/17.
17-14 | Tree widget proposal |  | DA |  | 2017-09-26 | 2018-07-24 | Done | Presented and accepted 7/24/18.
17-15 | Slider Widget modifications |  | RC |  | 2017-10-31 | 2018-02-15 | Done | Insert into Master for February 15 WebEx. Presented and accepted 2/15/18.
17-18 | BufferFormat |  | AB |  | 2018-01-11 | 2018-03-16 | Done | Corrections presented in Paris and accepted 3/16/18.
18-1 | Map 3D Management |  | DA |  | 2018-02-15 | 2018-09-28 | Merged | Merged with Action Item 13-4 in the Montreal meeting.
18-4 | Revise Section 3.1.3.4 to soften clipping requirements |  | B |  | 2018-03-13 | 2018-06-07 | Done | Presented and accepted 6/7/18.
18-7 | Selector Widget updates |  | B |  | 2018-03-13 | 2018-06-07 | Done | Presented and accepted 6/7/18.
18-8 | Word Wrap Extension |  | B |  | 2018-03-13 | 2018-06-07 | Done | Presented and accepted 6/7/18.
18-9 | Hold Gesture Widget |  | B |  | 2018-03-13 | 2015-07-24 | Done | Presented and accepted 7/24/18.
18-14 | Appendix G update |  | Unassigned |  | 2018-04-19 | 2018-09-28 | Withdrawn | Withdrawn in Montreal 9/28/18.
18-13 | Clarify MaxStringLength parameter |  | PRE |  | 2018-04-19 | 2018-06-07 | Done | Presented and accpeted 6/7/18.
18-5 | CursorEntryEvents Extension |  | DA |  |  | 2018-10-23 | Done | Presented and accpeted 10/23/18.
18-6 | Define Popups |  | AB |  |  | 2018-10-23 | Done | Presented and accpeted 10/23/18.
18-11 | Legend Description Cleanup (also includes former action item 16-24) |  | DA/PRE |  |  | 2018-10-23 | Done | Presented and accpeted 10/23/18.
misc | It should be made more clear that when re-sizing and shuffling the children of SizeToFit and ShuffleToFit, resp., the CDS is modifying internal copies of SizeX/Y and Pos X/Y, not the widget parameter values provided by the UA. This should be added to Sections 3.6.5 and 3.6.6. | sec3g | LC | 1 | 2010-08-31 | 2010-09-22 | Done | 9/22/10: decided that no clarification to spec is needed, it is understood that CDS sometimes must override UA-provided params.
misc | In Section 3.6.6 ShuffleToFit, there is a statement that "Any widget that has a SizeX / Size Y can be a child of this widget,…" This should maybe mention PosX/PosY instead, because SizeX / Size Y are not affected by ShuffleToFit. | sec3g | GH | 1 | 2010-08-31 | 2010-09-22 | Done | 9/22/10: no, do not change spec, it is correct. It is understood that PosX/PosY can be affected. Also understood that the widget must have a SizeX/SizeY to be a child of SizeToFit and ShuffleToFit.
misc | At PHX10 meeting it was asked why in Table 3.3.24-2b ProjectionApplied is only marked "Yes" for A661_MDF_LAT_LONG. Why doesn't it apply to other MDF's that involve X/Y points expressed in real-world coordinates? | sec3e | CW | 2 | PHX10 | 2010-12-13 | Done | 11/3/10: agreed that it applies to all, we should delete the column. MapHorz does not allow absolute origin points for the UA MapltemLists. 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | In Table 3.3.25-1 the description of ScreenReferencePointX/Y is confusing, clarify. | sec3e | GH | 2 | 2010-11-23 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | For Supplement 4 we forgot to add a code for new widget POPUP_PANEL_BUTTON. Use xA4E0. | sec4 | AM | 1 | 2010-10-28 | 2010-12-13 | Done | GE, Hwl OK with new code number. 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | Table 4.6-3b has spaces in the param names. Get rid of them. | sec4 | GH | 1 | 2010-11-03 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | Section numbers and organization of Section 4.5.3.2 through 4.5.3.7 are inconsistent. Re-organize Sections numbers and titles. Update all references to these sections/tables (refs are found in sections 6 and 7) | sec4 | CW | 1 | 2010-11-03 | 2010-12-13 | Done | Gary and Chad will propose changes for the group to discuss. Search doc and find all section/table references that would have to be updated. 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | References in Table 4.5.3.2-1 are wrong: SymbolBlockStructure is Table 4.5.3.2-5 and BlockStructure is Table 4.5.3.2-4. | sec4 | LC | 1 | 2010-11-03 | 2010-12-13 | Done | 11/3/10: Gary to draft changes. Affected if we re-organize Sections 4.5.3.2 through 4.5.3.7. 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | There are incorrect table references in Section 4.5.2. Section 4.5.3.1 should be clarified. | sec4 | GH | 1 | 2010-11-23 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | RMP tables in Sections 3.3.19, 3.4.1, 3.4.2 and 3.4.3 have incorrect references to Section 4.5.4.5 (refs go to 4.5.3 instead of 4.5.4.5). | sec3d, sec3f | GH | 1 | 2010-11-23 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | Table 7-1 column heading should be "A661_Picture_Block_Structure_DT". Table 7-1 title should be "Picture Block Structure Exchanged Between UA and CDS at Definition Time," to be consistent with Section 4.5.3. | sec7 | GH | 1 | 2010-11-03 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | A661_CDS_DEPENDENT is not defined in Table 4.6.11 (Integer Constant Values). This constant is used by the PopUpMenu, in Table 3.3.31-1. | sec4 | LC | 1 | 2010-11-08 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. Used code 0x1E. 12/13/10: changes accepted.
misc | PopUpPanel 3.3.30, Table 3.3.30-1, and PopUpMenu, Table 3.3.31-1 have a parameter Visible, but the param is not in the Creation Structures. | sec3f | LC | 1 | 2010-11-12 | 2010-11-23 | Done | non-problem. These are Runtime-Modifiable only and should not be in the Creation Structures.
misc | PopUpMenu (Page 144). In Table 3.3.31-1, EnableArray mentions values ENABLE or DISABLE. These should be A661_TRUE & A661_FALSE. | sec3f | LC | 1 | 2010-11-12 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. Made it consistent with Table 3.3.32-1. 12/13/10: changes accepted.
misc | Scroll List (Page 163). Table 3.3.37-1 EnableArray specifies values TRUE or FALSE (I think these should be A661_TRUE & A661_FALSE). | sec3f | LC | 1 | 2010-11-12 | 2010-11-23 | Done | non-problem. Exact spellings are not required in the Parameter table Description column.
misc | Table 4.5.4.5.17 has an incorrect reference to Table 4.5.4.5.18. | sec4 | GH | 1 | 2010-11-23 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | Table 4.5.4.5.7-1 should be numbered 4.5.4.5.7. Most references are to 4.5.4.5.7, but in Table 3.3.32-1 we still have a reference to 4.5.4.5.7-1, so change that too. | sec3f, sec4 | GH | 1 | 2010-11-23 | 2010-12-13 | Done | 11/23/10: Gary drafted changes. 12/13/10: changes accepted.
misc | Picture Block DF structure does not have a block size field. It is different than other block structures. Parsers cannot easily detect size corruptions that may exist in the picture block. And parsers cannot easily skip over picture block (e.g., if they do not support them). Do we need to add a Block size field? Is there some other way to address this? | sec7 | LC | 1 | 2010-10-27 | 2011-02-10 | Done | 11/3/10: There is a way to check block size now, but it is not simple. Parser can use NumberOfPixelsWidth and NumberOfPixelsHeight to compute expected size of each picture's pixel buffer. Can check picture structure using that result, start/end delimiters, etc . Can compute expected Picture Block size using number of pictures, etc. 2/10/11: Decided not to change DF structure.
misc | Add material to App G saying that in the future, new Block DF Structures should be provided with a Block Size param to make for easier error checking. This would prevent the Picture Block issue from recurring. | AppG | GH | 1 | 2010-11-03 | 2011-02-24 | Done | 2/10/11: Gary said he'd draft changes for group review. Later he found no appropriate place to add this, we don't have block structure design guidelines in the doc and we probably should not try to add any. Suggest we close this item with no doc changes made.
misc | Alphabetize Table 4.6-8, it will be easier for readers to use. Look for other tables that could be organized better. | sec4 | GH | 1 | 2010-12-13 | 2011-02-24 | Done | 2/10/11: reviewed Gary's survey on table organization. Decided to alphabetize all tables. 2/24/11: Gary made changes.
misc | PopUpPanel 3.3.30 and PopUpMenu 3.3.31: should these have an Enabled parameter ? | sec3f | LC | 1 | 2010-11-12 | 2011-02-23 | Done | 11/23/10: No, because they are just popups. We don' t give the Enabled param to popup widgets and popup parts of widgets. CDS is the one who controls "enabledness" of popups, not the UA. 12/13/10: the param is also not needed because UA can get same effect by setting all EnableArray entries to disabled. Gary sent note to Lewis.
misc | In Sections 3.6.5 and 3.6.6, change "The effect of nesting SizeToFitContainers or ShuffleToFitContainers is allowed, but the effect is CDS dependent." to "Nesting of SizeToFitContainers is allowed, but the effect is CDS dependent." and "Nesting of ShuffleToFitContainers is allowed, but the effect is CDS dependent." | sec3g | GH | 1 | 2011-02-22 | 2011-02-24 | Done | 2/24/11: Gary made changes
misc | ReportAllChanges should work the same everywhere. Found inconsistency and errors in how ReportAllChanges is described. Text still says it is boolean, but it is an enumerated. Description of what happens on edit aborts is incomplete, does not cover case when param is set to A661_EDB_OPEN_CLOSE. Affected widgets are all those which allow text editing: EBM, EBN, EBT, EBML, CBE, EBN-BCD. | sec3b, sec3f | GH | 1 | 2011-02-24 | 2011-03-24 | Done | 2/24/11: Gary drafted changes and sent out for comments. 3/10/11: changes approved in telecon, merged into doc master 3/24/11.
misc | Figure 3.2.8.1.1 has a layer box missing from the diagram. | sec3a | GH | 1 | 2011-03-02 | 2011-03-24 | Done | 3/10/11: agreed that Gary should add box. Done 3/24/11.
misc | Formatting improvements for all widgets which allow editing: EBM, EBN, EBT, EBML, CBE, EBN-BCD. | sec3b, sec3f | GH | 1 | 2011-02-24 | 2011-02-23 | Done | 2/24/11: Gary made changes
misc | Tables 4.5.3.3.1 and 4.5.3.4.1 need better refs, refer to "Widget Library sections in Section 3" and "Section 5 Symbol Definition." | sec4 | GH | 1 | 2011-02-22 | 2011-02-23 | Done | 2/24/11: Gary made changes
misc | Table 3.3.22.2.1.22 – Legend_Anchor_Rotated has some blue text, change to black. Check other files that may have similar problems. App G had unaccepted changes from Suppl 4. | sec3e, AppG | GH | 1 | 2011-02-23 | 2011-02-23 | Done | 2/23/11: Gary made changes
misc | Tables in Sections 5.2.3.10 thru 5.2.3.12 need the dashing fixed. | sec5 | GH | 1 | 2011-02-22 | 2011-02-24 | Done | 2/24/11: Gary made changes
misc | Spelling mistake in the Section 4.5.3.7 heading. Error is in TOC only, Section 4.5.3.7 is OK. | toc | GH | 1 | 2010-11-03 | 2011-02-24 | Done | 2/24/11: Gary made changes
misc | Per the definition in Section 3.2.2, the following are Dynamic Motion widgets: Basic Container, Panel, MutuallyExclusive Container, CursorRef and CursorOver. "Dynamic Motion" is missing from the "Categories" list for these widgets. And, there is no "X" in the Dynamic Motion column in Table 3.2.2-2 for these widgets. If the definition is correct, then the table and the "Categories" lists need correction. Otherwise, the definition is wrong and should be updated. | sec3a, sec3e, sec3f, sec3g | GD, GH | 1 | 2011-02-22 | 2011-04-23 | Done | 2/23/11: Gary sent a note. 3/10/11: definition of Dynam Motion is OK as written. 3/24/11: Gary drafted changes for review. 4/14/11: changes accepted. 4/23/11: Gary merged changes into master.
misc | ShuffleToFit is not a Dynamic Motion widget, per Section 3.6.6. Remove the "X" from Table 3.2.2-2 for ShuffleToFit. Section 3.6.5 and Table 3.2.2-2 say that SizeToFit is a Dynamic Motion widget, but this does not make sense. The position of its children can change at runtime, but there is no reason why SizeToFit's position needs to change. ShuffleToFit and SizetoFit should be consistent. We should confirm whether or not these are Dynamic Motion widgets. | sec3a, sec3g | GH | 1 | 2011-02-22 | 2011-04-23 | Done | 2/23/11: Gary sent a note. 3/10/11: agreed that both ShuffleToFit and SizetoFit should be Dynamic Motion widgets. 3/24/11: Gary drafted changes for review. 4/14/11: changes accepted. 4/23/11: Gary merged changes into master.
misc | Conflicting use of the term "extension" in the document. Only place we should use that term is in reference to the new Widget Extension concept. Lists of widgets added for each supplement should not be listed under the heading "extensions." | sec3a, sec3b, sec3f, sec3g, sec4 | IB | 1 | 2011-04-19 | 2011-04-23 | Done | 4/23/11: Gary drafted changes. 5/12/11: fixed in Strawman.
misc | Gary to copy Strawman source files into eProjects as the new baseline of Master Suppl 5 files. Note that files have been renamed. | all | GH | 1 | 2011-05-12 | 2011-05-17 | Done | Files copied 5/17/11 with same names as for Strawman. We will rename them at Cheltenham as we ratify their contents.
misc | Widget descriptions missing from end of Table 3.2.1 | sec3a | GH | 1 | 2011-05-12 | 2011-05-25 | Done | 5/25/11: Gary added it. 6/7/11: Ratified changes at June mtg.
misc | Tables 4.5.4.4-2 and -4 have an underscore missing from title. In Table 4.5.4.5.15 delete extra space in name of code. | sec4 | GH | 1 | 2011-05-24 | 2011-05-25 | Done | 5/25/11: Fixed
misc | Delete "A661_" prefix on 4.5.4.5.1 thru .20, or add prefix to all other sections in Section 4. Should be consistent. | sec4 | GH | 1 | 2011-05-24 | 2011-06-07 | Done | 6/7/11: added it to table hdgs but did not delete from section hdgs
misc | Table 3.1.3.5 says that NextFocusedWidget of zero means no next widget specified | sec3a | GH | 1 | 2011-06-07 | 2011-06-07 | Done | Changed this during CHL11 mtg
misc | PopUpPanelButton does not have Focus Navigation parameters. It is the only focussable widget that does not have these params. It looks like this was omitted when the widget was added for Supplement 4. | sec3g | AM | 1 | 2011-05-20 | 2011-06-07 | Done | 6/7/11: added NextFocusedWidget, but automatic focus motion does not apply because there are no selection or confirmation events for this widget.
misc | Update Table 3.3.36-1 to show that the Enable flag can have value A661_TRUE_WITH_VALIDATION. | sec3f | GH | 1 | 2011-05-25 | 2011-06-07 | Done | non-problem, no action taken
misc | clarify kRepeat description. Add following text to Section 3.2.5.5. "For example, if P1 is set to 0, the set of characters would appear one time. As another example, if P1 is set to 5, the set of characters would appear six times." | sec3a, sec6 | MW, GH | 1 | 2011-06-08 | 2011-10-05 | Done | 7/24/11: Gary added "This means that if P1 is set to zero (0) the set of characters should appear one time, if P1 is set to 1 the set of characters would appear two times, and so on." 9/1/11: Group members checked their implementations. There is only one implementation, and it does not use zero for P1. Decided to rename kRepeat as kOccur. A P1 value of 1 means no repeat, 2 means 1 repeat, etc. If somebody uses zero, its meaning is OEM-dependent. Add a note warning designers about using zero for P1, Tvalue1, and Tvalue2: it makes parsing a bit more difficult because system must distinguish between numeric zero and NUL char string terminator. 9/22/11: Gary drafted changes into master, went into Draft 1. 10/5/11: decided to rename Type TRepeat as TOccur. Gary modified Master doc.
misc | Pierre-Jean found three problems: • Table 3.5.1-2 – MutuallyExclusiveContainer Creation Structure: The WidgetType/Value is not in capital letters. • Table 3.5.6-3 – SymbolAnimated Runtime Modifiable Parameters: The ColorIndex type should be A661_ParameterStructure_1Byte. • 3.4.5.3 MapVert_ItemList Interactive Items: Not all elements in this list apply to MapVert. clearly state which of them do. | sec3e, sec3f | PJT, GH | 1 | 2011-06-10 | 2011-09-01 | Done | 7/24/11: Gary made changes, reviewed with group at telecon. Changes also affect Section 3.3.22.3. No objections raised 7/28/11, will close this item out at 9/1/11 telecon if no objections by then.
misc | We want all unused pads set to zero. Add a note to Section 3.3 and App G Section G-7. Add "0" in Value column of all creation tables that don't have it already. | sec3b, sec3e, sec3f, sec3g, sec4, sec5, sec7, sec8, AppG | GH | 1 | 2011-06-07 | 2011-07-24 | Done | 6/7/11: note added to Section 3.3. 7/24/11: note added to G-7, and all tables fixed.
misc | Place new events into aphabetical order in Table 3.1.4. Split Table 3.2.3.1 into two tables, keeping alphabetical order. | sec3a, App G | GH | 1 | 2011-06-07 | 2011-07-15 | Done | done, 7/15/11. Also split Table 3.1.4 into two tables, to make room for future additions.
misc | Expand the definition of "reference" in App A to say that a reference can take different forms. It can be an Identifier or a unique CDS-wide index number that resolves to an identifer. | AppA&B | GH | 1 | 2011-06-08 | 2011-07-28 | Done | 7/24/11: Gary drafted change, reviewed with group at 7/28/11 telecon, agreed.
misc | Add a definition in App A for "Identifier." May want to just say "see Section 3.x" | AppA&B | GH | 1 | 2011-06-08 | 2011-07-28 | Done | 7/24/11: Gary drafted change, reviewed with group at 7/28/11 telecon, agreed.
misc | Delete "upon crew member validation" from Table 3.1.3.5. Go through doc and replace all instances of this with a ref to Section 3.1.3.5. | sec3a, sec3b, sec3e, sec3f, sec3g | GH | 1 | 2011-06-07 | 2011-07-24 | Done | 6/7/11: Changed Table 3.1.3.5. 7/24/11: Gary changed widget param tables
misc | Add "¦" character where missing to Tables 4.5.4.1-2 and 4.5.4.3-1. | sec4 | GH | 1 | 2011-06-08 | 2011-07-24 | Done | done, 7/24/11
misc | Figure in 5.3.2.7 is wrong, it has an unlabeled vertex. | sec5 | GH | 1 | 2011-06-08 | 2011-10-05 | Done | Correct the drawing and the text before it. Also clarify that "3<=" means the minimum number of vertices is 3. 9/22/11: Gary drafted changes into master, went into Draft 1. 10/5/11: accepted by group.
misc | In Table 3.5.5-2 the param NumberOfPictures should be type ushort, not uchar. | sec3f | VR, GH | 1 | 2011-07-01 | 2011-07-24 | Done | done, 7/24/11
misc | Sect 3.2.9: the two bullet items a and b should be capital letters A and B to be consistent with the categories given in Table 3.2.2-2. | sec3a | GH | 1 | 2011-07-22 | 2011-07-24 | Done | done, 7/24/11
misc | A question came from GE about what exactly does it mean when a widget is active. Drafted a definition of Active which Gary will add to the master. Want to add definitions for Enabled, Visible and Inactive also. | AppA&B | SE, GH | 2 | 2011-09-01 | 2011-10-05 | Done | 9/1/11: Gary will draft definitions. 10/4/11: Gary drafted changes into master. 10/5/11: Agreed changes in telecon.
misc | Issue raised by Dave Franson of Perf S/W, Phx, AZ: In 3.5.3 WatchdogContainer, the bullet point "The widget referenced by ShowIfRefreshIdent is evaluated for display. If the Visible parameter of the child widget is True then the widget is displayed" should be re-written because ShowIfRefreshIdent does not exist. Better wording would be "All child widgets of the container except for the widget referenced by ShowIfFailIdent are evaluated for display. If the Visible parameter of the child widget is True then the widget is displayed." | sec3f | GH | 1 | 2011-09-23 | 2011-10-05 | Done | 10/5/11: agreed with suggested change, Gary modified Master doc.
misc | Add headings/numbers to any figures and tables. | sec5, AppF, AppG | GH | 1 | 2011-10-19 | 2011-10-19 | Done | Gary added them and sent files to Pete
misc | When discussing Dassault question about text alignment in A661_SYMBOL_DEFN_TEXT, it became apparent that not everyone interprets text alignment the same. Need clear agreement on what text alignment is. Need clear agreement on what A661 Constants like A661_TOP_LEFT, etc mean. Gary says original intent of A661 was that Alignment refers to where the text field appears, not how characters are justified within the text field. Gary says original intent was that Alignment constant names should indicate where text field is located relative to the applicable reference point. Some think it is the other way around. Need to see if the rules are different for alignment of non-text items (if that exists). We must go through the entire document and double-check each widget, etc that uses an alignment parameter. | all | All | 1 | 2011-10-05 | 2011-12-05 | Done | 12/5/11: Actually, in most cases the document is clear that the Alignment param specifies how text is to be justified within its display area (its SizeX/Y area). For example, see the Label widget. This means a Label string can in theory appear on multiple lines (if it had embedded LF chars). Gary withdrew his question.
misc | "gpPolyline" should be GpPolyline" throughout the document. | sec3a, sec3g | PG, GH | 1 | 2011-10-19 | 2011-12-06 | Done | Pete will fix this in Draft 1
misc | Currently zero values for Escape sequence params P1, Tvalue1, and Tvalue2 are allowed. Could make parsing harder because zero could get confused with NUL char, which is used as a string delimiter in some computer languages. We just changed the document to say that for P1 the meaning of zero is OEM-dependent. Should we disallow zero values for all three parameters? Note: this might affect Section 6 (XML rules). | sec3a, sec6 | DF | 1 | 2011-10-05 | 2011-12-05 | Done | 12/5/11: decided not to disallow zero values. Zero is allowed. However, CDS vendors and OEMs can decide to forbid the use of zero if they wish. Or, they can make the meaning of OEM-dependent. No further document changes needed.
misc | In 3.3.9, EditBoxMasked, the standard does not give full details about whether the first character of the string (string[0]) corresponds to the LSB of the mask or to the MSB of the mask. | 3.3.9 | VR | 1 | 2012-01-09 | 2012-01-12 | Done | 1/12/12: discussed, modified 3.3.9 to say "Bit zero (0) of the mask controls character zero (0) of the string (LabelString)."
misc | In 3.3.30 PopUpPanel, why does it say for parameter PosX "Set to 0 when UAPositionFlag is FALSE?" Shouldn't it be removed (this is too constraining no?) ? | 3.2.3.1 | VR | 1 | 2012-01-09 | 2012-01-12 | Done | 1/12/12: discussed, removed it. Rockwell did not implement the flag. Thales did, but ignores value of PosX when flag is false.
misc | In Table 3.2.3.1, MapVert should also be allowed to have MaskContainer as a child. | sec3a | LC | 1 | 2012-01-03 | 2012-01-12 | Done | agreed and fixed master doc file, 1/12/12
misc | 3.6.6. ShuffleToFitContainer and Table 3.2.3.1: CursorRef is allowed to be child of SizeToFitContainer but NOT of a ShuffleToFitContainer (this is the only widget in that case). Is it on purpose? Is it an error? | 3.6.6 | VR, CW | 1 | 2012-01-09 | 2012-02-22 | Done | 1/12/12: discussed. CursorRef has no size. 2/7/12: Gary proposed it should not be a child of either one (i.e., remove it from SizeToFit). Group agreed to remove it from SizeToFit, pretty sure about this. Deleted it from the master doc. 2/22/12: agreed we do not want this to be a child of either.
misc | Table 3.2.2-2 should have a letter "A" in the validation column for PopUpPanelButton. It has A661_ENABLE but does not have A661_ENTRY_VALID. | 3.2.2 | MW | 1 | 2012-01-12 | 2012-01-30 | Done | 1/30/12: Gary added the "A". Confirm this change at next telecon
misc | Mikon asked why ScrollPanel has UA Validation. Why is it listed as Type B in Table 3.2.2-2? What is being validated, the event it generates is just a scroll control. There are many similar widgets, the Buttons for example. Their events are mearely button pushes. | misc | MD | 1 | 2012-02-07 | 2012-02-22 | Done | 2/7/12: group responded by saying that the spec is flexible, it allows OEMs to devise validation schemes even for events such as these. A study was done in 2006 and the group agreed on the list of widgets that needed UA validation, and on the Types. It was a Honeywell proposal, so Gary will explain to group the rationale this. 2/11/12: Gary sent an email about this to the group. He proposes this item can be closed. 2/22/12: Agreed, leave it type B.
misc | It was asked if the pilot can edit the Legend on EditBoxNumericBCD. Spec confusing in one place. Answer is this: the pilot cannot change the legend. Pilot can enter characters to represent hex values (A-F), direction (N/S/E/W) etc. The UA should interpret these characters. This is why string params are used by EditBoxNumericBCD. | 3.6.1 | MD | 1 | 2012-02-07 | 2012-02-21 | Done | 2/7/12: Added some words to Section 3.6.1 to clarify. Need Airbus and Thales to review this. Group should ratify these changes at next meeting. 2/16/12: Airbus and Thales reviewed and agreed to new wording. 2/17/12: group ratified the changes. Moved the changed paragraph so it appears before Table 3.6.1-1.
misc | In Supplement 4 we changed Table 3.2.3.1 to allow RadioBox container to have Connector as a possible child. Boeing asks if this is really what we intended. | sec3a | GD | 1 | 2011-12-14 | 2012-02-21 | Done | 1/12/12: group feels we did intend this, would let user access RadioBox children owned by different UAs. 2/22/12: Not good to allow this, removed from spec. Also, we removed ability for SymbolPushButton to be a child of RadioBox.
misc | In Section 6.2.2 Layers and Widget of the XML Definition, in the File Specification: In the layer's table: the width and height properties are not specified as optional, whereas these are supplemental information compared to a binary DF. | sec6 | PJT | 1 |  | 2012-02-22 | Done
misc | As an outgrowth of our work on Item 11-01, Steve drafted re-written Sections (2.3.4, 3.1.3.4, etc) describing Position, Origin, Orientation and Translation/Rotation. Also updated Widget Descriptions for 3.3.2 (BasicContainer), 3.3.42 (TranslationCont) and 3.3.35 (RotationCont) to add more detail about how they are positioned and how their children are positioned, etc. Idea is to make things more clear and consistent. NOTE: his writeup would rename some sections, so we need to search entire document to look for any affected section references. | sec2, sec3a, sec3f, others? | SE | 1 | 2011-09-01 | 2012-02-21 | Done | 9/1/11: Discussed his draft. Widgets with PosX,Y can be parents. Widgets with TransX,Y must be contained by another widgets. PosX,Y is the ref point for widgets that have these params. TransX,Y is effectively the ref point for those widgets that have these params. 9/16/11: Steve provided updated materials. 10/5/11: Discussed, modified 2.3.4 &ff. 11/7/11: agreed on 2.3.4, 3.1.3.4 and 3.3.42. Steve will reword Commentary in 3.3.2 and clean up 3.2.3. Need to discuss 3.3.35 at next telecon, all to check if they like the suggested rotation formula. 11/8/11: Steve finished 3.2.3. 12/5/11: Agreed on the content of 3.2.3 and Steve's latest changes to 3.3.2, 3.3.42 and 3.3.35. 2/11/12: Gary merged all changes into the master file, and updated all references to renamed sections. 2/21/12: reviewed and updated wording, especially the description of Rotation Container.
misc | Dave Franson of Perf S/W sent an errata form in. The problem is the use of A661_ParameterStructure_8bytes structure for a 64 bit BCD number. Three cases exist in EditBoxNumericBCD. As seen in table 4.5.4.5.8, the structure type A661_ParameterStructure_8bytes requires two input values (ParameterValue1 and ParameterValue2) because it is designed to be used with structures such as x,y coordinates. It is not designed to be used by one 64-bit value. It is unclear in the current specification how to pack the 64-bit BCD values for the EditBoxNumericBCD widget because the ParameterStructure requires two 32-bit parameters instead of one 64-bit parameter. | 4.5.4.5.8 | ??? | 2 | 2012-02-08 | 2012-02-21 | Done | work this item at next meeting. Initial feedback was that it is OK to pack this param with BCD numbers. 2/21/12: added a Commentary to 4.5.4.5.8 saying a 64-bit BCD can be packed into the two Params.
misc | Does the A661 document say explicitly that transformations are to be applied to all widgets in the heirarchy, from top-to-bottom? It is inferred for Visible and Enable, but it makes a big difference when applying multiple transformations. Do we need to add this? | 3.2.3 | all | 1 | 2012-02-21 | 2012-02-21 | Done | 2/21/12: we added it
misc | The data type for the ColorIndex parameter of SymbolAnimated should be A661_ParameterStructure_1Byte. | 3.5.6 | VR | 1 | 2012-02-15 | 2012-02-21 | Done | agreed, 2/21/12
misc | In Table 3.3.24-2b MapDataFormat Values for MapHorz_Source, for DIST_DIST and DIST_DIST_FIX, is it correct when we say the Alignment of +Y axis is "Various?" | sec3e | AM | 2 | 2011-06-14 | 2012-02-21 | Done | might be OK as is. "Various" allows these X/Y MILItem values to be referenced to different coordinate frames, such as aircraft, true north, etc: we need that ability. 12/5/11: Gary to send a note to Aubanel and the group proposing to close this item with no document changes. 2/11/12: sent note suggesting we close this item with no changes. 2/21/12: The table is indeed wrong. Deprecated two MDF values because we now realize they are not needed. Removed Orientation column from table. Added one MDF value, DIST_DIST_TRUE_NORTH.
misc | Should we add something to App G-7 table saying that some Containers can contain children of their same type? Add it to Sect 3.2.3.1 also? Or is this self-evident from the tables in Sect 3.2.3.1? | AppG | PG, GH | 1 | 2011-10-19 | 2012-02-11 | Done | 11/7/11: Gary to draft a sentence to be added to App G instructing widget designers to update tables in 3.2.3.1. 2/11/12: This is already covered in Section G-10.
n/a | Suggestion was made by Dassault to add some inheritible widget parameters, mainly styleset, color, etc. This would allow the UA to change the parameter for a container, using just one SetParam Cmd, and the CDS would automatically apply the change to all children widgets. Perhaps an extension could be devised to do this. Gary suggests we just look at inheritible StyleSet for now, and he notes that a second extension would be needed to add StyleSet to those containers that do not currently have it. | sec3x, AppG | JB2 | 2 | 2011-03-25 | 2011-04-14 | Done | 4/14/11: discussed. Closed, but it led to the proposal for Broadcast widget
11-TBD | When reviewing Paging Container, a new item was raised. For TabbedPanelGroup and MutuallyExclusiveContainer, should we revisit how children are indexed (i.e., use 0 to N instead of WidgetIdents)? Other widgets having multiple children might be affected also, such as PagingContainer. | sec3x | LC | 2 | 2011-03-10 | 2011-06-09 | Done | 6/9/11: do not want to change the way children are referenced.
n/a | AEEC staff and Gary will prepare the set of MSWord master files for Supplement 5. Gary will put them in eProjects. | all | GH | 1 | 2010-06-02 | 2010-09-22 | Done | new masters were prepared June 2010. Gary put files in A661-5 (In Work) folder 9/22/10.
n/a | We need to release a Strawman 1 of Supplement 5 to support AEEC Gen Session and our June 2011 face-to-face meeting. | all | GH, PG | 1 | 2011-02-10 | 2011-04-27 | Done | Gary prepared MSWord master files. ARINC finalized them. Got feedback from group April 19. Updated per feedback. Released 4/27/11.
N/A | create a Draft 1 by Sept 1, 2011 with ABC pages | all | PG, GH | 1 | 2011-06-07 | 2011-11-30 | Done | after July 28 telecon Gary will prepare files and send to Pete, then AEEC will complete the files and publish it. 9/22/11: Gary made Draft 1 files and sent them to AEEC. 10/5/11: Gary sent all updates agreed at 10/5 telecon to AEEC, Draft 1 content is final. 10/19/11: Gary and Pete made a few more editorial changes, such as adding table headings.
Note on A3: Issues are SC discussion items. Issue# is composed of 2-digit year indicator and a sequential item number
Note on E3: 1 - high 2 - medium 3 - low
Note on G3: Must update all Affected Artifacts before item can be closed
Note on H3: New In Work On Hold Pending Done