## Sheet1
Action Item | Description | Responsible | Company | Date Opened | Open Closed | Comments
1 | Provide A618 Source to SITA | Jose Godoy | ARINC IA | 2010-11-18 | Closed
2 | Verify that MIAM APIM includes Phase II | Jose Godoy | ARINC IA | 2010-11-18 | Closed | No revision needed for now
3 | draft MIAM Phase II APIM | Luc | Airbus | 2010-11-18 | Closed | No revision needed for now
4 | Set Up Online Conference for Dec 8 | Jose and Laurent | Eurocontrol and ARINC | 2010-11-18 | Closed
5 | Review PP841 Draft 6 for Dec 8th Web Call | DLK Sys SC | ALL | 2010-11-18 | Closed
6 | Incorporate A631-7 Scope List (from Rob) | Jose Godoy | ARINC IA | 2010-11-18 | Closed
7 | Additional Text for Attachment 3 (AOA Parameters) | Laurent | Eurocontrol | 2010-11-18 | Closed
8 | Can FAA/Mitre share Simulation info | Rob | Mitre | 2010-11-18 | Closed
9 | Define MIAM labels for A620 | DLK Sys SC | ALL | 2010-11-18 | Closed
10 | Circulate Draft 1 for A620 | Jose Godoy | ARINC IA | 2010-11-18 | Closed
11 | Distribute MIAM Draft 6 | Jose Godoy | ARINC IA | 2010-11-18 | Closed
12 | Discuss next meeting | DLK Sys SC | ALL | 2010-11-18 | Closed
13 | MIAM Appendix B, In or Out? | DLK Sys SC | ALL | 2010-11-18 | Closed
14 | Contact Vic & get DLK UF info | Jose Godoy | ARINC IA | 2010-11-18 | Closed
15 | APIM for 620, AMDAR inputs | Stewart Taylor Jose Godoy | MET ARINC | 2010-07-08 | Closed
16 | Provide A631 Test Cases | Laurent | Eurocontrol | 2010-11-18 | Closed | June 6, 2011 test cases provided
17 | Is A619 Open, advise Airbus | Jose Godoy | ARINC IA | 2010-11-18 | Closed | ARINC 619 is closed, Subcommittee can open
18 | EC, Laurent to update MIAM PP 5-1, 5-3 | Laurent Meyer | Eurocontrol | 2011-05-12 | Closed
19 | Fatemah to provide ARINC's A618 S7 Broadcast comments | Fatemah Alduoli | ARINC | 2011-05-11 | Closed
20 | Is multicast the right term? | DLK Sys SC | DLK Sys SC | 2011-05-11 | Closed
21 | Louis Toth to revise A618 (Sec 7.5.2 moved Appendix D if info not there) and Section 8.5 | Louis Toth | Honeywell | 2011-05-12 | Closed 3Oct2011 | Lou provided changes to VAT8 UBI Reset Timer (5.4.2.8) and deleted Section 7.5.1.4 Cat B Capability Gnd Sta. (This info is in Appendix D).
22 | Jocelyn to revise A620 Sec 3.2.3.1.1. (per A618 A/C address) | Jocelyn Descaillot | SITA | 2011-05-12 | Closed
23 | Determine MIAM Phase II scope and revise APIM | DLK Sys SC | DLK Sys SC | 2011-05-13 | Closed 10Oct2011 | See Item # 35
24 | DLK SC to review Link 2000+ Guidance Material | DLK Sys SC | DLK Sys SC | 2011-05-12 | Closed
25 | HI to advise their procedure, switch to CSC at T/O or keep present Gnd link | Louis Toth | Honeywell | 2011-05-12 | Closed | HI switches to CSC
26 | See item 25, does it need to be clarified in A631 S7? | DLK Sys SC | DLK Sys SC | 2011-05-12 | Closed | See Item 38
27 | Jose to include UK MET's APIM into existing A620 APIM | Jose Godoy | ARINC IA | 2011-05-13 | Closed | APIM 11-004A with VMO inputs accepted by AEEC ExCom @ Mid Term Session
28 | Jose to add UK MET's AMDAR and AirDat info into A620 Draft | Jose Godoy | ARINC IA | 2011-05-13 | Closed | Draft 3 of Supplement 7 to ARINC 620 was posted on 30 Dec 2011, New Turb MET material wil be incorporated into Draft 4
29 | Jose to create ARINC PP 841 Draft 2 | Jose Godoy | ARINC IA | 2011-05-13 | Closed | Published June 3, 2011
30 | Jose to create ARINC 618 S7 Draft 4 | Jose Godoy | ARINC IA | 2011-05-13 | Closed
31 | Jose to create ARINC 620 S7 Draft 3 | Jose Godoy | ARINC IA | 2011-05-13 | Closed | Draft 3 of Supplement 7 to ARINC 620 was posted on 30 Dec 2011, New Turb MET material wil be incorporated into Draft 4
32 | SC to decide next meeting (DC area Sept/Oct) | DLK Sys SC | DLK Sys SC | 2011-05-13 | Closed | Joint AEEC/RTCA VDLSG/EUROCAE WG92 Meeting at FAA Tech. Center - Atlantic City - Oct 25-27, 2011
33 | DLK SC group to review FAA FANS Over Iridium and decide if any standard has to be mod (A758, SATCOM Standard/s) | DLK Sys SC | DLK Sys SC | 2011-05-12 | Closed | No revision needed for now
34 | Request was received at SC-214 to create a MOPS to cover Higher Level CMU (ATN); rejected at SC-214 | Comments only | Comments only | Comments only | Closed | Comments only
35 | Revise MIAM APIM (09-001) to include Phase II Scope and Schedule | Luc Emberger and Stephane Pelleschi | Airbus and Rockwell Collins France | 2011-10-10 | Close | See Item # 23 and 36
36 | Jose to provide APIM 09-001 to Airbus and RC | Jose Godoy | ARINC IA | 2011-10-10 | Closed 10Oct2011 | See Item 35
37 | Jose to request RTCA VDLSG/EUROCAE WG92 A631-7 issues list | Jose Godoy | ARINC IA | 2011-10-10 | Closed 10Oct2011 | See Item 38
38 | Dongsong/Stephane to provide A631-7 Issues list | Stephane Pelleschi and Dongsong Zeng | Rockwell Collins France and MITRE | 2011-10-10 | Closed 10Oct2011 | See Item 37
39 | Jose to provide A841 Source Doc to Airbus and RC | Jose Godoy | ARINC IA | 2011-10-10 | Closed 10Oct2011 | See Item 40
40 | Provide A841 MIAM S1D1 (clarifications and Phase II inputs) | Luc Emberger and Stephane Pelleschi | Airbus and Rockwell Collins France | 2011-10-10 | Close | See Item 39
41 | Jim Sroggs to provide A618 S7D4 inputs | Jim Scroggs | Rockwell Collins | 2011-10-10 | Closed 10Oct2011 | See item 46
42 | Luc Emberger to provide white paper on Gnd-Gnd large message transfer | Luc Emberger | Airbus | 2011-10-10 | Closed | SITA provided 15Feb2012
43 | SC to review ITT VDL Gnd Station Allocation (A631 Appendix F) | DLK Sys SC | DLK Sys SC | 2011-10-10 | Closed | This is an ICAO/IATA responsibility
44 | SC to review Jetstar VDL Gnd Station Allocation (A631 Appendix F) | DLK Sys SC | DLK Sys SC | 2011-10-10 | Closed | This is an ICAO/IATA responsibility
45 | SC to review Steve Carver's A618 comments | DLK Sys SC | DLK Sys SC | 2011-10-10 | Closed | Honeywell provided response
46 | SC to review Jim Scroggs A618 S7D4 comments | DLK Sys SC | DLK Sys SC | 2011-10-10 | Closed | See Item 41
47 | Set Up Meeting Bridge | Jose Godoy | ARINC IA | 2011-10-19 | Closed
48 | Luc Emberger to provide white paper with Gnd-Gnd large message transfer requirements | Luc Emberger | Airbus | 2011-10-27 | Closed | SITA provided 15Feb2012
49 | Advise Jetstar VDL address is IATA/ICAO Responsibility | Jose Godoy |  | 2011-10-27 | Closed | IATA provided JetStar an Address
50 | DLK SC to review SITA's broadcast/multicast proposal | DLK Sys SC | DLK Sys SC | 2011-10-27 | Closed | ARINC has issues with Broadcast definition and proposes TEI, which SITA objects to
51 | DLK SC to address broadcast/Multicast/All Call in 618/620 | DLK Sys SC | DLK Sys SC | 2011-10-27 | Closed | Broadcast/Multicast removed from Supplement 7 to A620. It will be reviewed further in A618 S7 and in future Supplements to A620.
52 | SC-214/WG92/AEEC to review SITA's MOPS input | SC-214 VDLSC/EUROCAE WG92/DLK Sys SC | DLK Sys SC | 2012-01-03 | Closed
53 | Set Up conference call for Nov 15, 2011 | Jose Godoy | ARINC IA | 2011-11-02 | Closed
54 | SC-214/WG92/AEEC to review ICAO ACP Amendments to harmonize changes for Tec Doc 9776 | SC-214 VDLSC/EUROCAE WG92/DLK Sys SC | SC-214 VDLSC/EUROCAE WG92/DLK Sys SC | 2011-10-27 | Closed
55 | Next Meeting tentative in Feb 2012 in Luxembourg | SC-214 VDLSC/EUROCAE WG92/DLK Sys SC | DLK Sys SC | 2012-01-03 | Closed | Meeting scheduled Feb 13/14-17 (Joint with SC-214 VDL SG - WG92)
56 | Luc Emberger to provide white paper with Draft 1 to ARINC 841 (MIAM) material | Luc Emberger | Airbus | 2011-10-27 | Closed | SITA provided 15Feb2012
57 | Insert new TURB MET data into Draft 4 of S7 to ARINC 620 | Jose Godoy | ARINC IA | 2012-01-31 | Closed
58 | Jose to create ARINC 618 S7 Draft 5 | Jose Godoy | ARINC IA | 2011-11-13 | Closed | Draft 5 of Supplement 7 to ARINC 618 was posted in Jan 2012
59 | Set Up Conference Call 26Mar2012 1100 EST | Jose Godoy | ARINC IA | 2012-02-16 | Closed 21Feb2012 | SITA/ARINC to advise they can participate
60 | Create Draft 1 of S1 to ARINC 841 MIAM and circulate | Jose Godoy | ARINC IA | 2012-02-16 | Closed | Draft 1 of Supplement 1 to ARINC Specification 841: MIAM is posted
61 | Subcommittee to review and comment/counter propose ARINC Multicast proposal | DLK Sys SC | DLK Sys SC | 2012-02-16 | Closed | DLK decided to replace Broadcast with Multicast and specify Multicast addressing
62 | Subcommittee to review and comment AIRBUS/SITA/RCF/ARINC A841 White Papers (Draft 1) | DLK Sys SC | DLK Sys SC | 2012-02-16 | Closed
63 | Eurocontrol to submit Freq Depollution white paper | Laurent Meyer | Eurocontrol | 2012-02-16 | Closed
64 | Tentative June 26-28, 2012 in Wash/Annapolis - Orlando Area | SC-214 VDLSC/EUROCAE WG92/DLK Sys SC | SC-214 VDLSC/EUROCAE WG92/DLK Sys SC | 2012-02-16 | Closed
65 | Review ICAO VDL Tech Manual proposals | SC-214 VDLSC/EUROCAE WG92/DLK Sys SC | SC-214 VDLSC/EUROCAE WG92/DLK Sys SC | 2012-02-16 | Closed
66 | Create Draft 4 S7 to ARINC 620 (minus Multicast/Broadcast) and circulate | Jose Godoy | ARINC IA | 2012-02-16 | Closed | Draft 4 of Supplement 7 for circulation prior to AEEC Adoption consideration is complete
67 | Review the tables 5-46 with 631-6 PICS | Dongsong Zeng /Stephane Pelleschi/Andrea Berti | MITRE / RCF / | 2012-02-16 | Closed | Waiting for Rockwell Collins France to review
68 | Verify T3 calculation | Tom McGuffin /Stephane Pelleschi | Honeywell / Rockwell Collin France | 2012-02-16 | Closed
69 | Verify that tech manual ISO8208 addresses are in line with ISO standard | Stephane Pelleschi | Rockwell Collins France | 2012-02-16 | Closed | No Differences
70 | Cross-check differences between tech manual and 631-6 for the whole document in order to identify potential remaining discrepancies | Andrea Berti / Stephane Pelleschi/Dongsong Zeng | MITRE / RCF / | 2012-02-16 | Closed | Waiting for Rockwell Collins France to review
71 | Cross-check differences between tech manual and DO-224C for the whole document in order to identify potential remaining discrepancies | Andrea Berti /Stephane Pelleschi / Dongsong Zeng | MITRE / RCF / | 2012-02-16 | Closed | Waiting for Rockwell Collins France to review
72
79 | SITA to provide comments on ASRI Power Reduction Proposal | Frédéric Durand | SITA |  | Closed
80 | Review ASRI Power Reduction Proposal (ARINC Characteristic 750 - VDR) | DLK Systems Subcommittee | SITA | 2013-02-21 | Closed | Last reviewed at Joint meeting Held in Reading, UK
81 | Review Boeing A631-7 Comments for D2 strawman | DLK Systems Subcommittee | DLK Systems Subcommittee | 2013-02-21 | Closed
82 | Update A631 Issues List | DLK Systems Subcommittee | DLK Systems Subcommittee | 2013-02-21 | Ongoing
83 | Categorize A631 Issues List by Criticality (High, Medium Low) | DLK Systems Subcommittee | DLK Systems Subcommittee | 2013-02-21 | Closed
84 | Create RTCA VDLSG TOR | Dongsong Zeng | MITRE |  | Closed
85 | Create EUROCAE ED-92 TOR | Stephane Pelleschi | RC France |  | Closed
86 | Submit EUROCAE ED-92B for Approval | Stephane Pelleschi | RC France |  | Closed
87
88 | Submit RTCA DO-281B to PMC for Approval | Dongsong Zeng | MITRE |  | Closed
89 | Submit RTCA DO-224C to PMC for Approval | Dongsong Zeng | MITRE |  | Closed
90 | Provide historical doc to ICAO ACP Secretary to support WP validation for ICAO Doc 9776 - VDL Tech Manual) | Peter Muraca / Dongsong Zeng / DLK Systems SC | FAA / MITRE / DLK Systems SC | 2013-02-21 | Closed | See Item 131
91 | Universal to provide Extended General Format Identifier (EGFI) of "03) for ARINC Specification 619 | Eric Mok | Universal (UASC) | 2013-02-21 | Closed | Eric provided the white paper on 26July13 and presented to the Joint AEEC DLK/RTCA and EUROCAE VDL Groups on 1August13
98 | Submit Supplement 7 to ARINC Specification 618 to AEEC ExCom for approval | Jose Godoy | ARINC IA | 2013-04-23 | Closed | AEEC Approved A618-7 on April 23, 2013
99 | Submit Supplemet 1 to ARINC Specification 841 to AEEC ExCom for approval | Jose Godoy | ARINC IA | 2013-04-23 | Closed | AEEC Approved A841-1 on April 23, 2013
100
101 | Publish Supplement 1 to ARINC Specification 841 - MIAM | Jose Godoy | ARINC IA | 2013-04-23 | Closed
102 | Publish Supplement 7 to ARINC Specification 618 | Jose Godoy | ARINC IA | 2013-04-23 | Closed
103 | Draft 2 to Supplement 7 to ARINC Specification 631 - VDLM2 | Jose Godoy | ARINC IA | 2013-04-23 | Closed
104 | Draft 1 to Supplement 8 to ARINC Specification 620 - Add MIAM to Gnd Standard | Frédéric / Luc | SITA / AIRBUS |  | Closed | July 23, 2013: SITA provided the A620 D1S8 strawman document. See items 131 and 136
110 | Schedule next joint meeting | Jose / Dongsong / Stephane | ARINC IA / MITRE / RC France | 2013-04-17 | Closed | Announce July 30-Aug1, 2013 joint meeting hosted by Boeing in Renton
111 | Schedule next On Line Conference Call | Jose / Dongsong / Stephane | ARINC IA / MITRE / RC France | 2013-06-11 | Closed | Scheduled for June 20, 2013 @ 11:00 EDT
112 | Advise group of RTCA PMC decision (Change 1 to RTCA DO-224C and DO-281B | Dongsong Zeng | MITRE | 2013-06-11 | Closed | Dongsong to advise during June 20, 2013 conference
113 | Draft 1 to Supplement 2 to ARINC Specification 841 - Add MIAM over IP/TCP | Frédéric / Luc | SITA / AIRBUS | 2013-06-11 | Closed | Posted 23July13 and discussed on 31July13 at DLK Subcommittee meeting
114 | Schedule next On Line Conference Call | Jose / Dongsong / Stephane | ARINC IA / MITRE / RC France | 2013-06-20 | Closed | Scheduled for June 24, 2013 @ 1100 to 1400 EDT
115 | Set Up SharePoint for DLK documents | Jose Godoy | ARINC IA | 2013-06-24 | Closed
116 | Review MOPS Comments | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-06-24 | Closed | Continuing. Comments to be further reviewed during next Online Conference
117 | Distribute updated MOPS worksheet and List of Issues for future A631 Supplements and VDL documents | Jose / Dongsong / Stephane | ARINC IA / MITRE / RC France | 2013-06-24 | Closed
118 | Update A631 Issues List | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-06-24 | Closed | Last reviewed at Joint meeting in Melbourne, FL (Nov 14, 2013
119 | Schedule next On Line Conference Call | Jose / Dongsong / Stephane | ARINC IA / MITRE / RC France | 2013-06-24 | Closed | Scheduled for July 8, 2013 @ 1100 to 1400 EDT
120 | Clarify MOPS Transmission Procedures | Tom McGuffin | Honeywell |  | Closed | Tom provided white paper; group reviewed and updated @ Joint Meeting Seattle (1Aug13)
121 | From update MOPS Comments - Incorporate into MOPS | Dongsong | MITRE |  | Closed | See Item 137
122 | Fatemah to submit sequence frequency recovery diagrams | Fatemah Alduoli | ARINC DSP | 2013-08-01 | Closed | See Item 138
123 | Submit to ICAO ACP M the VDL Tech Manual (ICAO Doc 9776 Support) letter | Jose Godoy | ARINC IA | 2013-08-01 | Closed | See Item 140
124 | ARINC and SITA to provide response to EC Proposal 1 (Impact of increasing RR and proposed data format) | Fatemah Alduoli and Frederic Durand | ARINC and SITA | 2013-08-01 | Closed | See Item 141
125 | Eric to provide A619 APIM | Eric Mok | Universal | 2013-08-01 | Closed | Eric Mok provided the draft APIM on September 4, 2013. It was discussed at the DLK Online conference on September 5, 2013.
126 | Group to review A631 D2S7 Section 7.9 | DLK and VDL | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed | At Joint meeting in Melbourne, the group decided to remove the strike-outs, add (i.e., AOA to second bullet (non-VDLM2 8208 only (i.e., AOA).
127 | Eric to provide inputs for A619 | Eric Mok | Universal | 2013-08-01 | Closed
128 | Mike to update A618 APIM | Michael Matyas | The Boeing Company | 2013-08-01 | Closed | APIM 13-013
129 | Jose to seek guidance on how to proceed with ACARS timer/counter subgroup evaluation | Jose Godoy | ARINC IA | 2013-08-01 | Closed | AEEC recommends submitting the APIM draft for consideration at the AEEC Mid-Term
130 | Review Frederic's A841 draft | DLK and VDL | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed
131 | Review Frederic's (SITA) ARINC 620 S8D1 Project paper | DLK and VDL | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed | Group started review at the joint DLK/VDL meeting in Melbourne, FL.
132 | Luc to add Version information to A841 (including keeping Ver 1 info in current draft) | Luc Emberger | Airbus | 2013-08-01 | Closed | Airbus agreed to provide the A841-2 input prior to September 24, 2013, so AEEC ExCom may be consider adoption at the Mid-Term
133 | EC to provide supporting data for proposal 2 (N2-T1 and T3 change) | Patrick Delhaise and Alexandre Simonin | EUROCONTROL | 2013-08-01 | Closed
134 | Schedule next conference call (Sept 5) | DLK and VDL | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed | Scheduled for 05Sept13
135 | Schedule next DLK Sys SC meeting | DLK and VDL | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed | Scheduled for Nov 12-15, 2013 @ Harris in Melbourne, FL
136 | Create Draft 1 of A620-8 | DLK SC | DLK SC | 41487 | Closed
137 | Incorporate the MOPS comments resolutions to draft MOPS Change 1 and Corrigendum 1. | DZeng/ SPelleschi | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed
138 | Draft a sequence diagram showing the intended use of frequency recovery | Fatemah Alduoli | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed | See Action Item 183
139 | Check the usage of AVLC specific option bit 6 (or “a” bit) as described in section 7.9 of ARINC 631-6 | Fatemah Alduoli | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed
140
141 | Check the impact on DSP of RR expansion to include CU information | Fatemah/Frederick | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-08-01 | Closed | See new item 162
142 | Schedule next Online Conference Call, discuss A618 APIM and A618 timers and counters | Jose Godoy | ARINC IA | 2013-09-05 | Closed | The Online conference is scheduled for September 25, 2013
143 | Schedule next Online Conference Call | Jose Godoy | ARINC IA | 2013-11-14 | Closed | The next Online Conference is tentatively scheduled for December 3, 2013, and another on 12Dec13 for ACARS Improvement. See item 147 and 148.
144 | Stephane to add MIAM sublabels "H1" info to ARINC 618 and 620 | Stephane Pelleschi | Rockwell Collins | 2013-11-14 | Closed
145 | Jose Godoy to provide A618 and A620 to Stephane | Jose Godoy | ARINC IA | 2013-11-14 | Closed
146 | Stephane to ask EUROCAE consul to advise how to document VDLM2 ground Requirements | Stephane Pelleschi | Rockwell Collins | 2013-11-14 | Closed | Should VDL gnd requirements be added to ED-92 or other document (i.e., SARPS). 22Oct2014: Stephane (EUROCAE): consider new document with grnd requirements. Tom (HI): harmonizing two docs is difficult, best have avionics and gnd requirements in different sections of same document. To be further discussed at next meeting. 11June2015: Ongoing as part of ELSA
147 | DLK/VDL groups to decide how to expand RR for Channel Utilization reporting (i.e., Raw CU over 1 sec., or processed (avg) CU over 1 sec.) | DLK and VDL | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-11-14 | Closed | Set up conference call (must include EC, ARINC, SITA, HI, RC). Scheduled for December 3, 2013. ARINC is proposing not averaging but RR frame from 2 seconds ago, see item 158.
148 | Clarify MIAM Version 2 and ARINC 620 MIAM gnd/gnd exchange (how will ARINC support MIAM gnd to gnd transfer?) | DLK and VDL | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-11-14 | Closed | Set up conference call (must include Lufthansa, ARINC, SITA, HI, RC). During the 3Dec13 conference call ARINC mentioned that A620 should be used for small file transfers and presently do not see a demand for it?
149 | Schedule ACARS Improvement Online Conference Call | Jose Godoy | ARINC IA | 2013-11-14 | Closed | The next Online Conference is tentatively scheduled for December 12, 2013. See item 147 and 148.
150 | Contact Eurocontrol and confirm they can host next joint DLK/VDL meeting (Jun 17-19, 2014); if not Rockwell Collins to attempt hosting in Toulouse | Jose Godoy | ARINC IA | 2013-11-14 | Closed | Patrick Delhaise has confirmed June 17-19, 2014 (Sirisu Meeting Room; 32 person maximum).
151 | DLK/VDL group to evaluate SITA's ATN simplification presentation | DLK and VDL | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2013-11-14 | Closed | 22Oct2014: SITA provided new simplification slides at DLUF (Sept at Eurocontrol). Joint group to comment on both presentations. See new action item 182
152 | Inmarsat to investigate and advise if R600 low speed rate can be left out | Alan Schuster-Bruce | Inmarsat | 2013-11-15 | Closed | Item was discussed during 12Dec13 Online Conference call
153 | ACARS Improvement leadership team to define SDU to CMU signaling | AAL, UPS, Boeing, ARINC, SITA, Inmarsat, HI, RC, etc. | ACARS Improvement Leadership | 2013-11-15 | Closed | Item was discussed during 12Dec13 Online Conference call. Using S1 was determined not to be effective as not all avionics use it. Investigate if CMU being informed of the type of link would be helpful.
154 | Boeing to provide, for DLK/VDL group distribution IPACG FANS Interoperability Team WP with VHF regions. | Michael Matyas | The Boeing Company | 2013-11-15 | Closed | Mike provided working paper November 25, 2013. Jose distributed the next day.
155 | UPS to request FAA ADS-C data and share with Boeing | Kevin Swiatek | UPS | 2013-11-15 | Closed | Item was discussed during 12Dec13 Online Conference call
156 | Boeing to request recent FAA >180s data and share with SITA and ARINC | Michael Matyas | The Boeing Company | 2013-11-15 | Closed | Data was discussed during 12Dec13 Online Conference call
157 | Schedule next ACARS Improvement Online Conference Call | Jose Godoy | ARINC IA | 2013-12-03 | Closed | The next Online Conference is scheduled for 04March14. It will be followed by a DLK Systems SC Standards conference.
158 | ARINC to provide draft text on CU using RR Frame (from 2 seconds ago) | Mark Layton and Ramsey Abid ARINC | ARINC DSP | 2013-12-03 | Closed | See new item 162
159 | Continue ACARS Improvement: Investigate it is worth having CMU informed of type of link, should DSP uplink value of retry timer, look at VHF/Satcom transition (retries), spotbeam operation drops, SDU and/or CMU changes, should VAT7 and other ARINC 618 timers and counters be revised?, etc. | ACARS Improvement Leadership team | ARINC (DSP), Boeing, Inmarsat, Honeywell, MITRE, Rockwell Collins, SITA | 2013-12-03 | Closed | See item 163 and 168 (consolidate)
160 | A619 Attachment 12.4.3.1 - SDU File Format: Ref to Section 6.6.1.2.1 and Figure 6.6.3.1-1 does not exist | DLK Systems SC | DLK Systems SC | 2014-02-14 | Closed | Section 6.6.1.2.1 S/B 12.4.2.1; Figure 6.6.1.3-1 S?B table 12.4.3.1-1
161 | A631 Appendix C - Message Sequence Charts: review notes/sequence updates | DLK Systems SC | DLK Systems SC | 2014-02-18 | Closed | 18June2014; Charts were reviewed and accepted at BRU Joint meeting
162 | DLK Subcommittee/VDL Groups review Channel Utilization (RR) inputs from RC/ARINC DSP, A631 Section 7.15 | DLK Systems SC | DLK Systems SC | 2014-02-19 | Closed | See item 141 and 158. 15June2014: Eurocontrol provided revised CU Proposal (Proposal # 1). 17June2014: Eurocontrol presented revised proposal. Group updated RC IMS proposal and will be part of Section 7.15 on next draft of Supplement 7 to ARINC 631
163 | Schedule next ACARS Improvement Online Conference Call | Jose Godoy | ARINC IA | 2014-03-04 | Closed | The next Online Conference is scheduled for 24April14.
164 | DLK Subcommittee/VDL Groups review FSL/Gnd Bit inputs from HI/RC/SITA; A631 Section 9.8.2.2 | DLK Systems SC | DLK Systems SC | 2014-03-07 | Closed | 18June2014: Subcommittee reviewed and accepted Honeywell proposal for A631 Section 9.8.2.2
165 | DLK Subcommittee to review A620 D1S8 | DLK Systems SC | DLK Systems SC | 2014-03-07 | Closed | See new Item 169
166 | DLK/VDL Group to strategize how to address, Provider Aborts (PA), delays and any other Link 2000+ issues | DLK Systems SC | DLK Systems SC | 2014-04-21 | Closed | 15June2014: EUROCAE and RTCA VDL Groups and AEEC DLK to review EASA DLK Report at Joint meeting in BRU. 17June2014: Group was presented EASA PA report. Will continue to investigate and develop standards based on investigation results. 20Jan2015: Ongoing. 11June2015: Ongoing - ELSA
167 | ARINC IA to brief DLK Subcommittee on other AEEC Activities (AGCS, AOC, EFB UF, DLUF, SAI (AeroMACS, SELCAL), etc,) | Jose Godoy | ARINC IA | 2014-04-21 | Closed
168 | DLK/VDL Group to strategize what ACARS Improvement Program suggestions to consider implementing | DLK Systems SC | DLK Systems SC | 2014-04-24 | Closed | 15June2014: Group to discuss subject at Joint meeting in BRU. Including VAT7 Retry Timer inputs from Honeywell and Universal. 11Dec2014: Boeing narrowed options being considered. In progress. 20Jan2015: Ongoing. 11June2015: Developing D2S8 to ARINC 618 02Sept2015: Ongoing. 13 Oct 2015: A618 D2S8 posted. RAT1 definition to be further reviewed. Include Duplicate UBI issue in Draft 3. Ongoing.
169 | DLK Subcommittee to review A620 D2S8 and ARINC comments | DLK Systems SC | DLK Systems SC | 2014-04-24 | Closed | 15June2014: D2S8 has been posted with WMO MET inputs, RC (ARINC DSP)Comments on Section 7. Since SITA has provided a strawman with response to RC (ARINC DSP) concerns (notes).
170 | RTCA/EUROCAE VDL Groups and AEEC DLK to review Proposals provided by Eurocontrol (1. Perceived Ch Utilization reporting; 2. Link Establishment; 3. Deployed Software Builds; 4. T1 for Long Frames; 5. ISO 8208 Reconnect attempts); and all comments received | RTCA/EUROCAE VDL Groups and AEEC DLK | RTCA/EUROCAE VDL Groups and AEEC DLK | 2014-06-15 | Closed | 15June2014: Lufthansa has provided ISO 8208 reconnection (5.) comments. Honeywell has Link Establishment (2.), Deployed Software (3.), and T1 for Long Frames (4.) comments. 11Dec2014 Progress with CU, others = work in progress
171 | AEEC DLK to review ARINC 841 supplement 3 (MIAM) inputs from Airbus and SITA | DLK Systems SC | DLK Systems SC | 2014-06-15 | Closed | 19June2014: Group reviewed and edited inputs from Airbus and SITA. 08Aug2014: Lufthansa provided inputs that will be used in Draft 1 of Supplement 3 to ARINC 841 (MIAM). 15June2014: SC to also review Lufthansa' inputs to the Draft 1 strawman. 20Jan2015: Reviewed during the Online conference call. Thomas Bernwald will review Aircraft MIAM version support and provide feedback so Draft 1 can be released.
172 | AEEC DLK to review Inmarsat ATN over OSI proposal for the SBB Satcom defined in ARINC 781 | DLK Systems SC | DLK Systems SC | 2014-06-15 | Closed | 15June2014: Avionics Suppliers to assess Avionics Impact (hardware/software). Aircraft OEMs to asses aircraft retrofit/wiring requirements, DLK Subcommittee: Standards Requirements. 11Dec2014: AEEC Executive Committee decided no to authorize project.
173 | Joint Group to evaluate VAT7 proposals (Honeywell: change from 45 to 90 seconds; Universal: make VAT7 value dynamic) | RTCA/EUROCAE VDL Groups and AEEC DLK | RTCA/EUROCAE VDL Groups and AEEC DLK | 2014-06-15 | Closed | 11Dec2014: Waiting updated input
174 | Honeywell to prepare various VAT7 value scenarios to be reviewed a next joint meeting | Tom McGuffin | Honeywell | 2014-06-15 | Closed | Required prior to December 9-11, 2014 meeting 11Dec2014: See 173
175 | Joint Group to evaluate impact of changing (increasing) T1 value (from 12 or 35 seconds) | RTCA/EUROCAE VDL Groups and AEEC DLK | RTCA/EUROCAE VDL Groups and AEEC DLK | 2014-06-15 | Closed
176 | Boeing, Rockwell Collins and Honeywell to comment on feasibility of a flight evaluation of ACARS Improvement proposal (i.e., software modified CMU on test or revenue flight) | Michael Matyas, Jim Scroggs and Tom McGuffin | The Boeing Company, Rockwell Collins and Honeywell | 2014-06-15 | Closed | September 18: Mike Matyas advised that there was no way that Boeing can provide a test bed. Jim Scroggs stated that Rockwell Collins was still investigating. 22Oct2014: Jim Scroggs: RC will modify avionics (from 180s to 160s) and evaluate impact on UPS aircraft. Update will be provided at next DLK meeting. 11Dec2014: RC cannot provide unit at this time (cert issue). Oter options being considerd. 20Jan2015: Ongoing 11June2015: Not feasible
177 | Schedule ATN over OSI Online Conference | Jose Godoy | ARINC IA | 2014-06-30 | Closed | Scheduled for July 16, 2014 (noon EST)
178 | Schedule next DLK Conference Call | Jose Godoy | ARINC IA | 2014-07-16 | Closed | Scheduled for Sept 18, 2014
179 | Schedule next DLK Sys SC meeting | Jose Godoy | ARINC IA | 2014-07-16 | Closed | Scheduled for Dec 9-11, 2014
180 | Schedule next DLK Conference Call | Jose Godoy | ARINC IA | 2014-07-16 | Closed | Scheduled for Oct 22 2014
181 | ARINC IA to distribute SITA ATN presentations | Jose Godoy | ARINC IA | 2014-10-22 | Closed | See item 151 and 182
182 | DLK/VDL group to evaluate SITA's two ATN simplification presentations | RTCA/EUROCAE VDL Groups and AEEC DLK | RTCA/EUROCAE VDL Groups and AEEC DLK | 2014-10-22 | Closed | See item 151 and 181. 11Dec2014: Still open 11June2015: Still open. 02Sept2015: Ongoing.
183 | Draft a sequence diagram showing the intended use of frequency recovery | Mark Layton | AEEC DLK / RTCA SC-214 VDLSG / EUROCAE WG-92 | 2014-10-22 |  | This item is initially for ARINC Specification 631. Frequency recovery is in the list of items for future VDL standardization. Replaces Action Item 138. 11Dec2014: Still open. 20Jan2015: Still open. 11June2015: Still open. 13 Oct 2015: Ongoing. 11 Nov 2015: Ongoing.
184 | SITA to provide A620-8 XML links |  |  |  | Closed
185 | ARINC DSP + SITA to provide comments on new timestamp (TEI) proposal) | Mark Layton and Jocelyn Descaillot | RC IMS SITA |  | Closed | 11June2015: Ongoing. 02Sept2015: Ongoing
186 | Schedule next DLK Conference Call | Jose Godoy | ARINC IA |  | Closed | Scheduled for 20Jan2015
187 | Schedule next DLK Sys SC meeting | Jose Godoy | ARINC IA |  | Closed | 23March2015: Rockwell Collins France will host next Joint Meeting June 9-11, 2015
188 | Group to provide comments on Honeywell Gnd Sta VDLM2 uplink N2 = Options 1 and 2 and Option 3 which is leave as is | RTCA/EUROCAE VDL Groups and AEEC DLK | RTCA/EUROCAE VDL Groups and AEEC DLK | 2015-01-20 | Closed | 20Jan2015: Still open. Originally presented by Honeywell 09April2015: Being Discussed by ELSA and Eurocontrol, briefing expected at next meeting.
189 | Review Swiss ANSP N2 white paper | Jose Godoy | ARINC IA | 2015-01-20 | Closed | 11June2015: Advise Swiss ANSP that we reviewed their presentation and its in ELSA's hands, thank you
190 | Schedule next DLK Conference Call | Jose Godoy | ARINC IA |  | Closed | Scheduled for 05March2015
191 | Schedule next DLK Conference Call | Jose Godoy | ARINC IA |  | Closed | Scheduled for 09 Apr2015
192 | Send Inmarsat SAT7 expiration time data for analysis | Tom McGuffin and Mike Matyas | Honeywell and Boeing | 2015-06-11 | Closed | Boeing and Honeywell sent data to Inmarsat. Waiting for inmarsat's Comments (See Action Item # 193).
193 | Inmarsat to review Honeywell and Boeing data (ACARS Improvement) | Alan Shuster-Bruce | Inmarsat | 2015-06-11 | Closed | 2 Sept 2015: Honeywell and Boeing have provided data to Inmarsat for their review and comments (See Action Item 193). 13 Oct 2015: Ongoing. 11 Nov 2015: Ongoing. 13Jan2016: Alan confirmed Inmarsat recoomends a value of 150 seconds for SAT7 timer.
194 | Stephane to review VDL Issues list and correlate with ELSA | Stephane Pelleschi | Rockwell Collins | 2015-06-11 | Closed | 2 Sept 2015: Stephane will present during the next WebEx (13Oct2015). Ongoing.
195 | Luc to provide ARINC 841 D2S3 update, if needed (MIAM secundary address guidance) | Luc Emberger | Airbus | 2015-06-11 | Closed | 13 Oct 2015: Luc will inputs to draft, or draft, at the next DLK meeting. There will be working session and APIM schedule discussion during the next DLK meeting (Nov 11-12, 2015). 2 Nov 2015: Luc provided Draft 2 Strawman.
196 | Stephane to initiate recommend Gnd Requirements for MOPS - DSPs to provide comments | Stephane, Mark and Jocelyn | Rockwell Collins, RC IMS, SITA | 2015-06-11 |  | 2 Sept 2015: Started looking at traseability for MOPS. Ongoing. 13 Oct 2015: Ongoing. 11Nov2015: Tom (Honeywell) to provide white paper (start with N2 event). 12 Jan 2016: Work in progress. Do we need to add HO action after N2 event? Discuss then draft if required. 02Nov2016: Group discussed Stephane list & ELSA Recommendations ONGOING
197 | Boeing to provide ARINC 618 input for D2S8 | Mike Matyas | Boeing | 2015-06-11 | Closed | 28 August 2015: Boeing (Mike) provided inputs for Draft 2 of Supplement 8 to ARINC 618
198 | Boeing to report meeting results to ICAO (ICAO Request to group) | Mike Matyas | Boeing | 2015-06-11 | Closed | 12 October 2015: Boeing (Mike) provided email with info of CNSG meeting, Will update Subcommittee during October 13, 2015 Online Conference
199 | Prepare MIAM supplemental Address info for A620 | All | All | 2015-06-11 | Closed | 2 Sept 2015: Ongoing. 12 Oct 2015: Develop D3S8 to ARINC 618, Ongoing. 13 Oct 2015: Ongoing.11Nov2015: Resoved with an alternate manner
200 | Harmonize Frame types 3.2.2.4.10.1.2 | Stephane and Dongsong | Rockwell Collins and MITRE | 2015-06-11 | Closed | 2 Sept 2015: Ongoing. 13 Oct 2015: Ongoing.
201 | Schedule next DLK Conference Call | Jose Godoy | ARINC IA | 2015-06-11 | Closed | Scheduled for 02 Sept2015
202 | Schedule next DLK Face to Face meeting | Jose Godoy | ARINC IA | 2015-06-11 | Closed | Nov 10-11, 2015 in Sarasota, followed by AeroMACS WG meeting (Nov 12-13)
203 | Distribute A618 White Paper | Jose Godoy | ARINC IA | 2015-09-02 | Closed
204 | Schedule next DLK Conference Call | Jose Godoy | ARINC IA | 2015-09-02 | Closed | Scheduled for 13 Oct 2015
205 | SITA and RC IMS to comment on ARINC 618 White paper and DSP managing | Jocelyn Descaillot and Mark Layton | SITA and Rockwell Collins IMS | 2015-09-02 | Closed | 13 Oct 2015: Discussed DSP proposals (see Action Item # 210). Ongoing
206 | Post Draft 2 of Supplement 8 to ARINC Specification 618 | Jose Godoy | ARINC IA | 2015-09-02 | Closed
207 | Stephane to contact ELSA and discuss who will present the Status Report at the November Joint Meeting | Stephane Pelleschi | Rockwell Collins | 2015-10-13 | Closed
208 | post 13Oct2015 Conference Call white paper (SharePoint site and distribute) | Jose Godoy | ARINC IA | 2015-10-13 | Closed
209 | Stephane to provide statement on Gnd requirements needed for ICAO Doc 9776 and ARINC 631 (are there differences) | Stephane Pelleschi | Rockwell Collins | 2015-10-13 | Closed
210 | Advise SITA their A618 Mode Character proposal to address to address duplicate UBIs (Lower case/Upper case characters) was discussed. But it is a bit complex and some Avionics might not support it. It will be discussed @ the next meeting in Cocoa Beach). | Jose Godoy | ARINC IA | 2015-10-13 | Closed | 13 Oct 2015: email was sent to Jocelyn Descaillot
211 | DSP to advise when they will implement Multicast addressing per A618-7 Section 2.3.3.4 | Jocelyn Descaillot and Mark Layton | SITA and Rockwell Collins IMS | 2015-11-11 | Closed | 12 Jan 2016: Still Open; ongoing
212 | Progress investigation on linkless Mode 2 | DLK Systems Subcommittee | DLK Systems Subcommittee | 2015-11-11 |  | 11 Nov 2015: SITA will provide test results by next meeting, others to review and provide comments.
213 | Mike (Boeing) to provide A618 D3S8 Strawman and DLK Subcommittee to review my inputs to the draft | Mike and DLK Systems Subcommittee | Mike and DLK Systems Subcommittee | 2015-11-11 | Closed | 04 Dec 2015: Mike provided proposed wording for Section 9.1.3 - Media Routing, including to RAT1 VHF to Satom Routing Timer
214 | Ask ELSA Consortium to share interrum report | Stephane | Rockwell Collins | 2015-11-11 |  | 12 Jan 2016: Expect answer at Jan 27, 2016 ELSA meeting. 28June2016: Stephane advises that he does not expect to receive an ELSA update prior to September.
215 | Post A618 D3S8 | Jose Godoy | ARINC IA | 2015-11-11 |  | Dependent on 213. 04 Dec 2015: A618 D3S8 Starwman will be placed on SharePoint; Posting Process commences. 28June2016: In Final stages of Posting Process
216 | Luc to provide A841-3 MIAM strawman | Luc Emberger | Airbus | 2015-11-11 | Closed
217 | Post A841-3 for Posting | Jose Godoy | ARINC IA | 2015-11-11 |  | 06 Jan 2016: Circulation for adoption draft in work. 28June2016: In Final stages of Posting Process
218 | Subcommittee to comment on D. Zeng Proposals (PBNet and Power Control) | DLK Systems Subcommittee | DLK Systems Subcommittee | 2015-11-11 |  | 28June2016: Ongoing
219 | SITA to provide Power Control testing results | Jocelyn Descaillot | SITA | 2015-11-11 |  | 28June2016: Ongoing
220 | Schedule next DLK Conference Call | Jose Godoy | ARINC IA | 2015-11-11 | Closed | Scheduled for 12 Jan 2016
221 | Schedule next DLK Sys SC meeting | Jose Godoy | ARINC IA | 2015-11-11 | Closed | Scheduled for May or June (posible sites Montreal , Eurocontrol). 12 Jan 2016: Tentative next joint meeting is scheduled for July 26-28, 2016. 28June2016: Scheduled for July 26-28 at Inmarsat in London.
222 | Send RC A834 SFA presentation to SITA | Jose Godoy | ARINC IA | 2016-01-12 | Closed
223 | DSPs to review Stephane's 834 SFA presentation and advise if MFI with or without Supplementary address will be processed | Jocelyn Descaillot and Mark Layton | SITA and Rockwell Collins IMS | 2016-01-12 | Closed | 28June2016: DSP agree thay can support a method so messages with and without a Supplemental Address are correctly routed (A620-9 APIM).
224 | Are ARINC 620 changes /clarification required ? | DLK Systems Subcommittee | DLK Systems Subcommittee |  | Closed | Jose to advise the GS cutoff date. 28June2016: A620-9 APIM has been created and will be considered at the Mid-term Session. See Action item 227
225 | Schedule next Conference call | Jose Godoy | ARINC IA |  | Closed | Scheduled for June 28, 2016
226 | Rockwell Collins to present draft APIM for ARINC 758-4 (Add Ethernet ports to CMU) | Jim Scoggs | Rockwell Collins | 2016-06-28 | Closed
227 | Create Draft APIM for A620-9 | Jose Godoy | ARINC IA | 2016-06-28 | Closed | APIM has been created and is being presented to the SAI Subcommittee
Annapolis Meeting
230 | Gnd Req # 1: RC IMS to research impact of complying with A631 Section 9.8.1 | Trishal | Rockwell Collins IMS | 2016-11-01 |  | DSP does not maintain original GS VSDA when requesting an Autotune, per A631. submit comment for discussion during next Conference Call (November 29, 2016)
231 | Gnd Req # 2: Add wording for new Section 4.3.3 - GS Recovery from N2 | DLK Systems Subcommittee | DLK Systems Subcommittee | 2016-11-01 |  | Expected behavior when T1N2 retries
232 | Gnd Req # 3: DSP to investigate TG5 and brief DLK/VDL Group | Jocelyn , Trishal | RC IMS and SITAONAIR | 2016-11-01 |  | Provide briefing on last day of meeting (Wednesday, November 2, 2016)
233 | Gnd Req # 4: Rockwell Collins to add wording for Section 9 | Stephane | Rockwell Collins France | 2016-11-01 | VOID | GS (on Freq from Gnd FSL) should provide Air FSL systematically
234 | Gnd Req # 5: DSPs to research and explain the reason/s why DISC are sent (loss of link?) | Jocelyn , Trishal | RC IMS and SITAONAIR | 2016-11-01 |  | 5a: DSP not to send GSIF during unavailability time. 5b: Should GRAIHO/GIHO be sent instead of DISC
235 | Gnd Req # 6: DSPs to research and explain the reason/s why CLEAR Request is sent | Jocelyn , Trishal | RC IMS and SITAONAIR | 2016-11-01 |  | Should DISC be replaced by
236 | Gnd Req # 7: Switch between ADM-ARS w/o link interruption |  |  | 2016-11-01
237 | Zbig to advise if slide 3 A/C equipment on white list | Zbig | RC IMS and SITAONAIR | 2016-11-01
238 | Zbig to add equivalent slide for POA/VDL with Bottom Antenna A/C | Zbig | RC IMS and SITAONAIR | 2016-11-01
239 | Proposed EUROCAE TOR and requirements /schedule for MOPS authorization | Stephane and WG92 | RC and EUROCAE | 2016-11-01
240 | Proposed RTCA TOR and and requirements /schedule for MOPS authorization | Dongsong and VDLGG | The MITRE Corporation and VDLSG | 2016-11-01
241 | Schedule next Conference call | Jose Godoy | ARINC IA | 2016-11-01 | Closed | Scheduled for Nov 29, 2016
| Schedule next ATS WindsConference call | Jose Godoy | ARINC IA | 2016-11-01 | Closed | Scheduled for Nov 30, 2016
242 | Tom / Christine to submit A622 white paper | Tom McGuffin | Honeywell | 2016-11-01 | Closed | replace CMU with CMS (federated architecture)
243 | Stephane to modify AOC A/C Tracking FID to include 24B ICAO Address Code | Stephane | Rockwell Collins France | 2016-11-02
244 | Stephane to contact ELSA (ATLYS) and request how T2 simulated | Stephane | Rockwell Collins France | 2016-11-01
245 | Stephane to contact ELSA (ATLYS) and request how early (8%) and late HO simulated | Stephane | Rockwell Collins France | 2016-11-01
246 | Can Test Cases be added to A631 as an appendix? | Jose Godoy | ARINC IA | 2016-11-02 |  | 18Nov2016: Yes, If the Subcommittee concurs that it adds value (improves interoperability), Test Cases may be added as an Appendix
247 | Subcommittee to decide if Test Cases are for Supplement 7 or 8 | DLK Systems Subcommittee | DLK Systems Subcommittee | 2016-11-18
248 | Subcommittee to review and discuss A631 APIM 10-013C, submitted by Mike (Boeing) | DLK Systems Subcommittee | DLK Systems Subcommittee | 2016-11-18
249 | Subcommittee to develop final draft of ARINC 758 APIM (Ethernet Ports for CMU) | DLK Systems Subcommittee | DLK Systems Subcommittee | 2016-11-18