## Sheet1
Action Item | Applicable Standard | Description | Responsible | Company | Date Opened | Due Date | Comments
June 11-14, 2019 - Joint VDL Meeting - Paris
1 |  | DSPs to advise if anyone else should be sent the Avionics Response Survey | Zbig and Butch | SITAOnAir and Collins Aerospace IMS | 2019-06-11 | 2019-06-18 | Anyother suppliers that are qual tested by DSPs
2 |  | DSPs to advise desired CU downlink format | Zbig and Ron | SITAOnAir and Collins Aerospace IMS | 2019-06-11 | 2019-07-16 | RR of last CU, average CU, average over how long. Include aircraft position (Lat/Long) and 24 bit ICAO address? 23July2019: DSP to advise by Sept 19 meeting in DUB. SITA: requires Lat/Long/Alt of A/C, not crazy about using RR frames; frequency discussed (how often). A/C preseption is critical if accurate (could have a 400 mile error). Collins IMS: using XID is not prefered. 20Sept2019: Gnd to send Test Request. In A631 but removed from MASPS. ONGOING DSPs: Please send white papers - how you would like to see the Channel Utilization Data formated. 07Oct2019: Open and OnGoing. 6Nov2019: Collins Aerospace IMS provided white paper (using RR). SITAOnAir to advise their preference. See items 69 and 70. 6Feb2020: Still Open; also need input from other DSPs (IMS/SITAOnAir not, e.g., AVICOM...). How to express (average, last 2 seconds)
3 |  | DSPs to advise reason for GND sending DISC request | Zbig and Butch | SITAOnAir and Collins Aerospace IMS | 2019-06-11 | 2019-07-16 | 23July2019: SITA DISC is a CMD. DM is a status. 20Sept2019: Ongoing
4 |  | DSPs to advise expected airborne response to Ground transmission of a DISC command | Zbig and Butch | SITAOnAir and Collins Aerospace IMS | 2019-06-11 |  | Companion Doc Paragraph: 2.1.1.2
5 |  | Share new wording in Companion Dosument, Paragraph 2.1.1 | Stephane | Collins Aerospace | 2019-06-11
6 |  | Share new wording in Companion Dosument, Paragraph 2.1.1.1 | Stephane | Collins Aerospace | 2019-06-11
7 |  | On Companion, Paragraph 2.1.1 Add ARINC 618 section that specifies switching to POA | Stephane Pelleschi | Collins Aerospace | 2019-06-11 | 2019-07-16 | 23July2019: ATN connection, then Gnd issues autotune to POA. SITA implelements when approaching POA area. Collins: we don't support. Add to Companion. 07Oct2019: Stephane provided wording, group to review and provide inputs if needed.
8 |  | On Companion, Paragraph 2.1.1 , DSPs to advise how ACARS autotune will be used | Zbig and Butch | SITAOnAir and Collins Aerospace IMS | 2019-06-11 | 2019-07-16 | See above : SITA to provide for the companion
9 |  | On Companion Paragraph 2.1.1, add reference to Tech Manual state diagram (ground and/or avionics state diagram) | Tom McGuffin | Honeywell | 2019-06-11 | 2019-07-16 | Ongoing
10
11 |  | Peter Muraca to brief the VDL Standards group on Tech Manual coordination (with ICAO WG) | Peter Muraca | FAA | 2019-06-11 | 2019-07-16 | Ongoing. 07Oct2019: Add to Melbourne December Joint meeting, have a plan/schedule to update ICAO Tech Manual. 24Feb2020: Goal is to align VDL documents after connectionless VDL2 is defined (End of 2022),
12 |  | On Companion DISC sent from Air, review off line and add clarification on DISC during an HO… | Tom McGuffin | Honeywell | 2019-06-11 | 2019-07-16 | 07Oct2019: Ongoing
13 |  | DSPs to advise how they handle action 12, since State diagram was created after initial inplementation | Zbig and Butch | SITAOnAir and Collins Aerospace IMS | 2019-06-11 | 2019-07-16 | Ongoing
14 |  | Service Providers to explain if there is a specific expectation for DM (2.1.2.2.2.2. or just prior to 2.1.3) | Zbig and Butch | SITAOnAir and Collins Aerospace IMS | 2019-06-11 | 2019-07-16 | Zbig to advise. 23July2019: SITA: Status indication when GND sends DM (same for both DSPs). Universal, what if DM is received. Collins: if we see them, we appreciate them and disconnect. 07Oct2019: Progress but ONGOING (First input from SITA then Collins IMS.
15 |  | EC and maybe DSPs to advise frequency of FRMR occurance | Christophe Visee, Butch and Zbig (work with Ken, Tom and Lynn) |  | 2019-06-11 | 2019-07-16 | If not often, then remove 2.1.3 - FRMR. 23July2019: SITA Rare, mainly 1/3 from 1 sick aircraft. Collins: we don't see many downlink FRMR (we see mostly uplink FRMR). 20Sept2019: Occurs ofthen enough (add to doc) add new action item to add commentary to companion. 6Nov2019: Categorize for beter analysis.
16 |  | Review 2.1.5 GRAIHO Usage when SITAOnAir is available |  |  | 2019-06-11
17 |  | Discuss section 2.1.5.3 with SDM to ensure consistency |  |  | 2019-06-11
18 |  | On Companion Paragraph 2.1.7 Air FSL , DSP to advise how long to stay on FSL | Zbig and Butch | SITAOnAir and Collins Aerospace IMS | 2019-06-11 | 2019-07-16 | After how long before switching to CSC? Review when DSPs are available. 23July2019: Collins: we do not support FSL
19 |  | Arrange next Joint Web Conference | Jose Godoy | ARINC IA | 2019-06-12 | 2019-06-14 | Scheduled for 23 July 2019
20 |  | Review proposed changes to ISO 5 Character set for 618, 619, 620 | Butch and all | Collins Aerospace and all | 2019-06-14 | 2019-07-16 | Ongoing, Ken to report
21 |  | Add Transmission/Re-Transmission changes to A618 | Jose Godoy | ARINC IA | 2019-06-14 | 2019-07-16
22 |  | Schedule Leadership WebEx for scheduling | Jose Godoy | ARINC IA | 2019-06-14 | 2019-06-14 | Scheduled by Stephane for 15 July 2019
July 23, 2019 Web Conference
25 |  | Review Draft 2 of Supplement 9 to ARINC 618 | ALL | ALL | 2019-07-23
26 |  | Review Draft 2 of Supplement 8 to ARINC 631 | ALL | ALL | 2019-07-23
27
28 |  | Review Latest version of EUROCAE Companion Document | ALL | ALL
29 |  | Schedule next Joint WebEx (scheduled foe September 12) | Jose Godoy | ARINC IA
30 |  | Schedule Leadership WebEx (scheduled TBD) | Jose Godoy | ARINC IA |  |  | Leadership Team will conference 1/2 hour prior to scheduledSept 12t webex
31
32 |  | Schedule Joint December 2-5, 2019 Meeting |  |  |  |  | L3Harris Technologies will host meeting in Melbourne, FL
33 |  | Post A618 D2S9
34 |  | Post A631 D2S8
September 12, 2019 - Web Conference
35 |  | Announce that Collins Aerospace IMS) will submit an ARINC 620 white paper | DLK Systems Subcommittee | DLK Systems Subcommittee
September 19, 2019 - VDL Standards Meeting - Dublin
40 |  | Paragraph 2.1.1 (DISC Usage) SITAOnAir and Collins Aerospace IMS to provide list of scenarios where services are changing and their associated meaning. | Zbig and Ken | SITAOnAir and Collins Aerospace IMS | 2019-09-19 |  | 07 Oct 2019: Zbig and Luc from Airbus have confirmed they will provide input. See item 61.
41 |  | Compare SITA and Collins Aerospace IMS Scenarios | VDL Standards Group | VDL Standards Group | 2019-09-19
42 |  | Stephane will propose wording to explain that the aircraft use a different criteria for accepting the autotune i.e., IDRP or TP4 link) | Stephane Pelleschi | Collins Aerospace | 2019-09-19 | 2019-10-01 | POA CMDed when in ATN environment. Conmpleted by Stephane, group to review and accept
2019-09-19
44 |  | Section 2.1.2.1 - DM Sent and DM received by Gnd Sta: Stephane to propose test decribing that LE and HO are acceptable after the DM with any available ground station. Also Update Tech Manual | Stephane Pelleschi | Collins Aerospace | 2019-09-19 |  | Ongoing
45 |  | GIHO usage (2.1.4): IMS to implement GIHO; if it’s a long term solution what is needed in the short term |  |  | 2019-09-19 |  | IMS to research when and if, GIHOs will start being implemented. 07Oct2019: Ongoing, No changes to Avionics to remove support for GIHO
47 |  | Review Collins Aerospace IMS ARINC 620 proposal | DLK Systems Subcommittee | DLK Systems Subcommittee | 2019-09-19 | 2019-09-20
48 |  | Request that L3Harris present the list of operational issues (with corrective actions) so standard can be reviewed to address gaps) | Dan Klemfuss | L3Harris Technologies | 2019-09-19 |  | In progress, Mid to late October, review during Nov WebEx. 6Nov2019: Dan provided white paper during Web conference.
49 |  | Request that Harris present what behavior have been observed with the various trials (e.g., less N2 events by varying the T4 timer? Implementing GIHO ? | Dan Klemfuss | L3Harris Technologies | 2019-09-19 |  | In progress, Mid to late October, review during Nov WebEx. 6Nov2019: Dan provided white paper during Web conference.
50 |  | Add section in paragraph INFO frames before a/c receive HO RSP | Stephane Pelleschi | Collins Aerospace | 2019-09-19
51 |  | Stephane to propose text on number of GRAIHO before giving up | Stephane Pelleschi | Collins Aerospace | 2019-09-19
52 |  | Consider how long to keep FSL | Stephane Pelleschi |  | 2019-09-19 |  | SITA recommends use of the FSL frequencies in the PECT
53 |  | Make Lifetime FSL section a note under FSL (2.1.7.1 and 2.1.7.2) | Stephane Pelleschi | Collins Aerospace | 2019-09-19
September 20, 2019 - VDL Standards Meeting - Dublin
55 |  | Add Airbus proposed text - on loss of adjancey with the air-gnd router |  |  | 2019-09-20 |  | Verify with Satcom, review wording added, check VHF
56 |  | What does it mean when the CMU/SDU is "logged ON" Linked available or not (SDU Label 270, bits 17 and 9). Need input from IRIS Precurser | Zbig to lead effort, Jiri, AirTel ATN |  | 2019-09-20 |  | ATN link broken? Air-Gnd router. How to re establish link, how do we know there's been a reset. Ongoing. Jiri to attend Inmarsat meeting with AirTel and advise SC. 24Feb2020: Coordination with IRIS so standardization process can commence.
57 |  | Create ARINC 620-10 APIM | DLK Systems Subcommittee | DLK Systems Subcommittee | 2019-09-20 | 2019-09-20 | APIM Developed on September 20th
58 |  | Send APIM to AEEC Director for Executive Committee Consideration | Jose Godoy | ARINC IA | 2019-09-20 | 2019-09-20 | APIM Sent and will be reviewed at SAI and AEEC Mid-Term Session in Renton, Washington
59 |  | Send SAI and AEEC Mid-Term Session SMAs to interested parties | Jose Godoy | ARINC IA | 2019-09-20 | 2019-09-20 | Sent to FAA, Collins Aerospace IMS, L3Harris and Honeywell
60 |  | Schedule October Joint Conference Calls | Jose Godoy | ARINC IA | 2019-09-20 |  | October 7 and November 6, 2019
October 7, 2019 - Web Conference
61 |  | DSPs and Airbus to provide DISC usage scenarions (See Item 40) |  |  |  |  | See items 40 and 41
62 |  | Confirm GIHO recommendation in Companion Document | Stephane Pelleschi |  | 2019-10-07
63 |  | Schedule November 6th Web Conference | Jose Godoy | ARINC IA | 2019-10-07 |  | October 7 and November 6, 2019
November 6, 2019 - Web Conference
65 |  | Review and complete A620-10 APIM | DLK Systems Subcommittee | DLK Systems Subcommittee | 2019-11-06 | 2019-11-06
66 |  | Submit ARINC 620-10 APIM to SAI Subcommittee | Jose Godoy | ARINC IA | 2019-11-06
67 |  | Decide if A631-8 APIM (17-002A) should be revised to add Supplement 9 | DLK Systems Subcommittee | DLK Systems Subcommittee | 2019-11-06 |  | 6Nov2019: APIM to be completed at December meeting in Melbourne
68 |  | Review and further develop EUROCAE Companion Document
69 |  | Review ARINC 631-8 Channel Utilization White Paper (Collins Aerospace IMS) | DLK Systems Subcommittee | DLK Systems Subcommittee | 2019-11-06 |  | 6Nov2019: CU will be discussed and developed at Dec 2019 meeting in Melbourne. Jose will reach out to SITAOnAir and request how they would like to see perceived CU provided by the avionics (Collins Aerospace IMS prefers using RR frames). See item 2 and 70.
70 |  | Request that SITAOnAir provide CU preference | Jose Godoy | ARINC IA | 2019-11-06 |  | See items 2 and 69.
71 |  | Review L3Harris Technologies white paper | DLK Systems Subcommittee | DLK Systems Subcommittee | 2019-11-06
72 |  | L3Harris to share actual VHF and Satcom performance data versus requirements | Dan | L3Harris Tecnologies | 2019-11-06
75 |  | Schedule next Web Conference (Admin / Schedule) | Jose, Stephane, Dongsong, Thomas | ARINC IA, Collins Aerospace, MITRE, FAA | 2019-11-06
December 3-6, 2019 - Meeting at L3Harris
80 |  | Collins IMS to provide further FRMR spike information | Ken | Collins Aerospace IMS | 2019-12-03 |  | To be analyzed by DCIT
81 |  | L3Harris to provide Operational Issue | Dan | L3Harris Tecnologies | 2019-12-03
82 |  | Stephane to start Operational Issue Matrix | Stephane | Collins Aerospace Avionics | 2019-12-03
83 |  | Merge inputs into Companion Doc | Stephane | Collins Aerospace Avionics | 2019-12-03
84 |  | Send ICAO VDL Tech Doc to Jiri/Jose | Peter Muraca | FAA | 2019-12-03
85 |  | Complete inputs to Companion Doc | All | All | 2019-12-03
86 |  | How does the Avionics behave when VSDA is removed from GSIF to which the avionics is connected to, Is the IDRP and 8208 link maintained. Avionics Suppliers to advise their behaviour. | Lynn, Tom Judd, Mitchell, Claire, Stephane/Jim | Avionics Suppliers | 2019-12-03 |  | Garmin responded, Universal provided, Honeywell responded
87 |  | Provide Call request wording without contradictiong MASP 3.2.3.6.4 (para. 2) | Stephane | Collins Aerospace Avionics | 2019-12-03
88 |  | review updated Companion Document | All | All | 2019-12-04 |  | Stepahane to Lead discussion
|  | Review inputs provided by Tom McGuffin | All | All | 2019-12-04
90 |  | Review ToR schedule change Presentation |  |  | 2019-12-04 |  | Stepahane, Dongsong and Thomas Mustach to Lead discussion. 24Feb2020: Ongoing - Stephane and Dongsong to brief the group
91 |  | Resurrect Connectionless VDLM2 topic |  |  | 2019-12-04 |  | Stepahane and Mike Matyas to Lead discussion. 24Feb2020: White papers and feedbacks (from Collins and others) are requested to restart discussion
92 |  | Resurrect Broadcast VDLM2 topic |  |  | 2019-12-04 |  | Zbig (SITAOnAir) to Lead discussion
93 |  | MOPS review (are they harmonized) | Stephane | Collins Aerospace Avionics | 2019-12-06 |  | Add to VDL Issues List?
94 |  | Add ACARS Character corrections to A620 | Jose | ARINC IA | 2019-12-06
95 |  | L3Harris and DSP to evaluate if Media Advisory guidance needed and in which standard | Dan, Ken and Zbig |  |  |  | 12March2020: Collins Aerospace IMS submitted Media Advisory Inputs for ARINC 620 D3S10
96 |  | Schedule DLUF side meeting in Feb
100
101 |  | Propose when to HO to destination airport | ALL |  |  |  | 29Jan2020: Inwork, being reviewed. 24Feb2020: Dan provided requirements; Ongoing - important issue. Include DLS Operation Issues from NM.
102 |  | Schedule next WebEx (8Jan2020) | Jose | ARINC IA | 2019-12-04
103 |  | Schedule next WebEx (29Jan2020) | Jose | ARINC IA | 2019-12-04
8 January 2020 - WebEx
110 |  | Add FRMR guidance…to avoid excessive spikes | Stephane | Collins Aerospace | 2020-01-08
111 |  | Stewart west to provide "FRMR Sequence/window)…ref to ISO doc | Stewart West | Honeywell | 2020-01-08 |  | Stewart to send to Stephane
112 |  | Zbig to provide updated VGS environment image | Zbig | SITAOnAir | 2020-01-08
113 |  | AIR FSL - add gnd validity lifetime section --- Not needed already in ARINC 631 | Stephane | Collins Aerospace | 2020-01-08 |  | Add reference note to vallidity timeline in ARINC 631. Consider moving to 2.1.7 , not 2.1.7.1
114 |  |  |  |  | 2020-01-08
115 |  | send INFO Frame before HO_RSP | Stewart West | Honeywell | 2020-01-08 |  | Stewart to send to Stephane
116 |  | Add autotune to POA scenarion comment (when in ATN environment | Zbig | SITAOnAir | 2020-01-08
117 |  | Review Collins IMS inputs for ARINC 620; |  |  | 2020-01-08 |  | Add 220
118 |  | Share/get input from Oceanic Program Group | Peter Muraca | The FAA | 2020-01-08 |  | June 2020 implementation deadline
119 |  | A620: Add Uplink Icing Section or remove "Up" from H3 table |  |  | 2020-01-08 |  | Uplink not used by Collins IMS, waiting for SITAOnAIr
120 |  | DSPs to advise if H3 Icing Report is used | Mark / Zbig | Collins IMS / SITAOnAir | 2020-01-08
29 January 2020 - WebEx
125 |  | Create matrix with Issues to be standardized | Stephane / Dan | Collins Aerospace L3Harris | 2020-01-29 |  | See Items 81 and 82; Start "Operational Issues" Matrix
126 |  | Review IDRP (to set timer/s appropiately) | Brian / Brian | AirTel ATN | 2020-01-29
127 |  | For ARINC 620 is a change needed to support MIAM Message routing | Mark/Stephane | Collins Aerospace | 2020-01-29
128 |  | From DCIT, review VDLM2 Timers and Counters (ARINC 631). L3Harris to advise which items to review | Dan | L3Harris | 2020-01-29 |  | 24Feb2020: Request clarification from L3Harris, what timers and countrers
February 6-7, 2020 - Meeting at L3Harris
130 |  | Complete Companion Document | VDL Group | VDL Group | 2020-02-06
131 |  | Insert diagram | Stephane | Collins Aerospace | 2020-02-06
132 |  | Insert Companion Doc into ARINC 631-8 | Jose | ARINC IA | 2020-02-06
133 |  | DSPs to Review Proposed ARINC 618 Timers and Counter for Connectionless | Zbig and Ron | Collins Aerospace and SITAOnAir | 2020-02-06
134 |  | Assign Doc Numbers to Companion Doc | Karan and Anna | EUROCAE and RTCA | 2020-02-06
135 |  | Collins IMS to provide wording for Incomplete Downlink | Zbig and Ron | Collins Aerospace and SITAOnAir
136 |  | DSP to review satcom presentation (airbus proposal) | Zbig and Ron | Collins Aerospace and SITAOnAir |  |  | Send presentation to DSPs; ask Luc what Standards would be affected?
137 |  | Schedule Next Web Conference/s | Jose | ARINC IA | 2020-02-07 |  | Schedule next Web Ex for 24 Feb 2020
138 |  | Comment on 620 Codes | Zbig and Ron | Collins Aerospace and SITAOnAir | 2020-02-07 |  | 24Feb2020: Waiting on commentary and formating from Collins IMS. Overall OK
139 |  | Schedule next meeting | Jose | ARINC IA | 2020-02-07 |  | EUROCONTROL in Brussels on July7-10, 2020
|  | Review wording for Attachment 2, Table 2-2 and -3 (Untransmiable and Undeliverable) | DLK | DLK
141 |  | Discuss DISC after DM
16March 2020 - WebEx
145 |  | Review inputs to ARINC 620 - 10 Strawman
146 |  | Review inputs to ARINC 631 - 8 Strawman
147 |  | Change July DLK Systems Subcommittee meeting to virtual | Jose | ARINC IA | 2020-03-16 |  | Changed from EUROCONTROL in Brussels to virtual July 6-10, 2020
148 |  | DSPs to review comments column on A620-10 Attachment 2 tables for reason codes
149 |  | Distribute updated VDL Standards Development schedule | Jose | ARINC IA | 2020-03-16
150 |  | A620-10 Section 3.2.3 - Review note 3 and add AoIP, NET description |  |  |  |  | AoIP, Gatelink, NET, Cell, satcom description might be needed,in this setion or where appropriate in the document
151 |  | A620-10 Section 5.3.51 Media Advisory; Review note 3 and commentary add AoIP and Gatelink clarifications. Reword Commentary for Codes N and G
152 |  | Advise Dan (L3Harris) of rewording for reason code 336
153 |  | Review A620-10 wording for TEI TP (Appendix B TEI Codes)
2April2020 - WebEx
160 |  | Zbig to provide CU proposal for A631-8 | Zbig | SITAOnAir | 2020-04-02
161 |  | Review SITAOnAir Channel utilization Proposal | DLK Subcommittee | DLK Subcommittee | 2020-04-02 |  | Discuss at April 3, 2020 WebEx; for A631-9 D1
162 |  | Tom McGuffin to provide A631 wording (GRAIHO) | Tom | Spectralux | 2020-04-02
163 |  | Revise A631-8 to standardize ATN/IPS instead of IPS; and ATN/OSI | Jose | ARINC IA | 2020-04-02
Submit fo Adoption ARINC 620 D3S10
Submit fo Adoption ARINC 631 D4S8
|  | Stephane to update FRAC with DISC updated figure | Stephane | Collins Aerospace | 2020-04-03
|  | Harmonize MASPS with with Destination Airport wording added in A631-10 Section 4.3 | Dongsong | The MITRE Corp | 2020-04-03 |  | Update MASP (Paragraph 3.2.2.4.7.2) Note 1. If the aircraft is able to establish a reliable link with a ground station having coverage at it destination airport, this station should be given preference above all other stations. However, it should be noted that the aircraft can begin its descent near the RF boundary of the destination airport and care should be taken to prevent the handoff from occuring too early and the aircraft flying “under” the coverage of the destination airport. 11Sept2020: Jose: Send to Stephane
|  | Harmonize MASPS with with Destination Airport wording added in A631-10 Section 4.3 | Dongsong | The MITRE Corp | 2020-04-03 |  | Update MASP (Paragraph 3.2.2.5.4.6.2 - Site Selection Preference) Note: If an aircraft has commenced approach to its destination airport and its current link is with a ground station that does not offer service at that airport, it should handoff to a ground station which indicates in its Airport Coverage Indication parameter that it offers service at that airport. Proposed: “If the aircraft receives GSIFs from the destination airport ground station with good signal strength and the connected ground station’s GSIF does not include the destination airport in the Airport Coverage Indication parameter, then the ground station whose Airport Coverage Indication parameter contains the destination airport should be preferred when the aircraft performs a handoff.” or something similar…
|  | Harmonize MASPS with with Destination Airport wording added in A631-10 Section 4.3 | Dongsong | The MITRE Corp | 2020-04-03 |  | Update MASP (Paragraph 3.2.2.5.4.6.1 - Aircraft Handoff) The aircraft LME shall initiate a Handoff to a new ground station if any of the following events occur: 12..., 8. destination airport detected and aircraft logic indicates that the likelihood of maintaining connectivity with the destination ground station is good. The aircraft logic may consider factors such as signal strength, aircraft location, aircraft altitude, aircraft type, aircraft datalink antenna location etc.??
Sept 8-11, 2020 Virtual Meeting
200 |  | Evalute Security Approach for VDL2 Support of IPS | VDL Standards Group | VDL Standards Group | 2020-09-11 |  | Use IPS Requirements List
201 |  | Resend IPS Requirements List | Stephane Pelleschi | Collins Aerospace (Avionics) | 2020-09-11
202 |  | Based on Requirements List determine what to specify | VDL Standards Group | VDL Standards Group | 2020-09-11 |  | Number of protocols, what is feasible versus what is reasonable. Connectionless only for IPS? Security including MIC
203 |  | Create Part 15 Survey (include VDR OEMs) Gather comments/questions | Dongsong Zeng | The MITRE Corporation | 2020-09-11 |  | Gather comments/question and send to distribution and Include VDR OEMs
204 |  | IMS to investigate UBI implementation (ARINC 618-7) | Ron Dlouhy | Collins Aerospace (IMS) | 2020-09-11
205 |  | Revise Channel Utilization Wording | Zbig Jasiukajc | SITAOnAIr | 2020-09-11
206 |  | Add Boeing Connectionless v13 material to ARINC 618 S9 Strawman | Jose Godoy | ARINC IA / SAE ITC | 2020-09-11
207 |  | Add Boeing Connectionless v13 material to ARINC 631 D1S9 Strawman | Jose Godoy | ARINC IA / SAE ITC | 2020-09-11
208 |  | Add connectionless diagram to new A631 S9 Attachment 5 | Christophe Visee | Eurocontrol | 2020-09-11
209 |  | Consider a similar diagram for connection oriented |  |  |  |  | Ask Mike Matyas if he can create
210 |  | Eurocontrol to provide updated PR list for Standardization Consideration | Christophe Visee | Eurocontrol | 2020-09-11 |  | Provided at January joint meeting (items added to VDL Issues list)
211 |  | Schedule next VDL Standards Group Web Conference | Jose Godoy | ARINC IA / SAE ITC | 2020-09-11 |  | 2020-10-08
October 8, 2020 Web Conference
213 |  | Brief Group on Collins VHF enhancement presentation at SAI Subcommittee
214 |  | Schedule next VDL Admin Conference |  |  |  |  | 2020-11-06
215 |  | Post ARINC 631 D1S9 | Jose Godoy | ARINC IA / SAE ITC
November 16-20, 2020 Virtual Meeting
220 |  | CSP/DSPs to advise what data is required/desired from Avionics (e.g., position provided via XIDs, perceived Channel Utilization) so DSPs can be proactive and enhance network management | Ron/Steve and Zbig | Collins Aeropsace IMS and SITA |  |  | what stations look good or bad, DLK capabilities (satcom type)
221 |  | Channel Sensing Session - Results - what next (from Survey responses) | VDL Standards Group | VDL Standards Group
222 |  | Advanced VHF Session - Results - what next | VDL Standards Group | VDL Standards Group
223 |  | Why is MIC suitable at VDL level but not for end to end IPS
224 |  | Does VDL (low bandwidth) have the bandwidth to support IPS?
225 |  | Madhu to provide MIC security analysis | Madhu | Collins Aerospace
226 |  | SITA to advise status of Broadcast - what next | Zbig | SITA
227 |  | Zbig to provide draft specification of VDL2 Broadcast | Zbig | SITA
228 |  | Connectionless Decision for AOA, ATN/OSI, IPS with Orange what next | VDL Standards Group | VDL Standards Group
229 |  | Insert applicable sections of Boeing Connectionless Standards Impact WP V14 into draft (e.g., MASPS, ARINC 631, ARINC 618 | Stephane, Dongsong and Jose
230 |  | Review Sita Channel Utilization input (Inserted into A631 Strawman, Section 7.15) | VDL Standards Group
231 |  | Insert Channel Utilization into MASP/MOPS | Stephane and Dongsong
232 |  | Develop and Insert Connection Oriented Frequency Management diagram into ARINC 631-9 Strawman, Attachment 5 (next to Connectionless flow diagram - developed by Boeing).
233 |  | Add GIHO/GRAIHO guidance to Interoperability (Companion) Document EUROCAE ED-276/RTCA DO-383 | RTCA / EUROCAE
234 |  | Dan's (L3Harris Technologies) OPRs List (review and add new iitems to VDL Issues List)
235 |  | Update VDL Items List / Reason for the list (what to standardize and tool to communicate with Jessie and DCIT)
236 |  | Dan (L3Harris to advise CRC in OP-Issue-12 - CRC on Airbus aircraft
237 |  | Update Orange (IPS) Requirements Matrix |  |  |  |  | To be updated further during December 1st conference call
238 |  | Draft Connectionless Strategy decission and include clearly in minutes/report (AOA first (foundation) and IPS in parallel)
239 |  | Add AIRBUS proposed 8208 re-establish timer into ARINC 631, MOPS and MASPs |  |  |  |  | Added to A631D2S9 Strawman
240 |  | Stephane and Jiri to draft text for immediate Call Request / Retry
241 |  | Collins IMS and SITA to comment on 8208 inputs (ARINC 631 Section 8.2/8.6 (60 seconds re-establish timer)
242 |  | Is a decision on use/non-use of IDRP needed? After Dual presentation from Jiri Byrda (HI)
243 |  | Stephane/Luc action to present dual link management with non use of IDRP |  |  |  |  | Presented at January 29, 2021 Meeting
244 |  | Review schedule and update schedule |  |  |  |  | Cliare Robinson - updated during meeting
245 |  | Next Meeting being scheduled for January 26 to 29, 2021 - Admin Conference being scheduled for Monday, Jan 25, 2021
246 |  | RTCA to schedule Dec 1st Conference |  |  |  |  | Next Web Conference (Update VDL Items spreadsheet)
247 |  | Update ARINC 618 APIM (17-003); update deliverable schedule |  |  |  |  | Not needed; Mature Draft date pushed till Apr2022; could be Sept 2021
January 26-29, 2021 Virtual Meeting
250 |  | Christope to provide a copy of presented slide | Christophe | Eurocontrol |  |  | Provided to Stephane and group
251 |  | Add Eurocontrol Operational Issues to the VDL Items List | Stephane | Collins Aerospace
252 |  | Request that CSP provide complete log (to complement log sent by Dan (L3) to Tom (Spectralux) to furher analyze Qx rejection | Ron/Mark Collins IMS
253 |  | FRMR Spikes: Christophe to confirm no update since Nov 2020; hope to make decision by next joint meeting Feb 22nd | Christophe | Eurocontrol
254 |  | FRMR Spikes: Avionics Suppliers to help find root cause | Avionics Suppliers | Avionics Suppliers |  |  | Collins, Garmin, Honeywell, Spectralux, Thales, Universal
255 |  | OPS Item XX _ Item 2. Claire to gather TG2 information in Standards (e.g, ARINC 631) so group can determine if guidance or requirements are needed. | Claire Robinson | Spectralux
256 |  | GRAIHO: Mark,Ron, Stephane to propose wording in InterOp document to consolidate aircraft position with the xisting sources to avoid "poor VGS" | Ron/Mark and Zbig | Collins Aerospace
257 |  | GRAIHO: DSPs to provide input for InterOp document by next meeting (sugest what type of infomation would help provide awareness). SITA collect sample of GRAIHO and analyze why it failed | Ron/Mark and Zbig | Collins Aerospace IMS and SITA
258 |  | Check if it's legal to use "Orange" for connectionless…any copyright issues? | Dongsong, Stephane, Jose | RTCA, EUROCAE and ARINC IA
259 |  | Brian to investigate 8202 Reject ; provide of possible option to run ATN/OSI over connectionless (w and w/o Orange?) | Brian Hurley | AirTel ATN |  |  | not really an 8202 reject
260 |  | CSPs and DSPs to evaluate and advise on use of XID_CMD_LEs for establishing DSP connection and XID_CMD_HO for connectionless frequency changes. | Ron/Mark and Zbig | Collins Aerospace IMS and SITA
261 |  | Stephane to gather architecture information (BRU and Paris) | Stephane | Collins Aeropace
262 |  | Review VDL Issues Matrix and address your action item | All | All
263 |  | Op Issue 31: requesting DSP to propose wording for Companion document (in VDL spread sheet) | Ron/Mark and Zbig | Collins Aerospace IMS and SITA |  |  | Zbig: this is taken careoff; no ATN in field operation is recommended. "holding on to ATM
264 |  | When a GIHO is received in the middle of a AIHO, continue with AIHO (prefereable or immediately switch (add clarification) Already in A631 4.3 - Handoff Management? Stephane to provide proposal (in VDL spread sheet) | Stephane | Collins Aeropace |  |  | Zbig: normally we defer to aircraft as it has better preception but when FM and the gnd issues a GRAIHO is normally for a reason; we prefer the ground
265 |  | How to provide Installer a/c position for VDL (in VDL spread sheet) |  |  |  |  | How to proceed if value is not available; different when info is not valid
266 |  | Destination Airport - add to "companion document" (in VDL spread sheet) | Stephane | Collins Aeropace
267 |  | Clarify Valid Data; what ALT should be provided? Consequence of absence of valid data | Tom McGuffin | Spectralux
268 |  | CSPs to look into reducing VGT1_ui, VAT7_ui to support RCP130 (ARINC 618-9 11.4.1) | Ron/Mark and Zbig | Collins Aerospace IMS and SITA
269 |  | SITA to provide data on how often AIHO/GIHO collisions occur | Zbig | SITA
270 |  | IMS will check how often destination airport is not included in the XIDs | Ron/Mark | Collins Aerospace IMS |  |  | See 257
271 |  | Check values lsited for GNSS values are consistant in the Standards
272 |  | Compose survey for radio suppliers to confirm they do not object to complying to ED-92 stringent Requirements and not against DO-281 | VDL Leadership | RTCA, EUROCAE and ARINC IA |  |  | Garmin believes they test to both standards (most stringent); Spectralux to advise; Universal tests to different for both Upper Band (Lynn: we also analyze all standards and use most stringent) will provide compete answer at later date
273 |  | Discuss further VDL Interference and how to apply (optional or mandatory in future radios) continue dicussion | All | All
274 |  | Add V15 items to ARINC 631-9 | Jose | ARINC IA/SAE ITC
275 |  | Schedule dedicated "Connectionless Meeting" 2 hours (frequency: once a month) Feb 22nd | Jose | ARINC IA/SAE ITC
276 |  | Add IPS Security requirements and other dependencies to VDL Schedule (when dates are available)
277 |  | Mike Matyas (The Boeing Compay) to review VGT2 and suggest value (ARINC 618-9 11.4.1) | Mike Matyas | The Boeing Company
278 |  | CSP to review IDRP data and brief Subcommitte/WorkGroup/SpecialCommittee (IDRP keep alive) traffic volume statistics; forcast benefit in changing timer | Ron/Mark and Zbig | Collins Aerospace IMS and SITA
279 |  | Where to define routing in case of ATN/OSI multilink; what to standardize and in which standard | Stephane | Collins Aerospace |  |  | Coordinating with ICAO
280 |  | Group leadership to discuss with AEEC/RTCA/EUROCAE documents that are beyond VDL; if VDL not the multimedia | Leadership Team | RTCA, EUROCAE and ARINC IA
281 |  | Should OSI over Satcom be defined? And where? What is the impact in this group and other industry standard
285 |  | Send Feb 22nd connectionless conference invitation / send request to access DLK Teams Folders | Jose | ARINC IA/SAE ITC |  |  | Sent on 8Feb2021
286 |  | Next Virtual Meeting 1-4June2021 | All | All
Feb 22, 2021 Connectionless Conference Call
290 |  | Review Collins Aerospace Architectural Diagrams - Provided by Stephane
291 |  | Review V16 Connectionless/Standardization white Paper and Clarify terminology
292 |  | Stephane to update Visio Diagrams (e.g., add IPS + 8208 slide + (security?)), add scenarios? Which applies to Europe |  |  |  |  | Clarify of ATN B2 is supported inly by IPS… by OSI in Europe; Stephane coordinating with ICAO
293 |  | Decide if IPS supports AOA (in the future?)
294 |  | Will Orange require additional features to support AOA, is Orange only for IPS
295 |  | Continue security to support IPS, is a requirement at VDL level?
296
297 |  | Schedule the next Connectionless Conference (March 11, 2021 from 10:00 AM to 12:00 PM EST USA)
March 11, 2021 Connectionless Conference Call
300 |  | Review updated Collins Aerospace Architectural Diagrams - Provided by Stephane | VDL Standards Group | VDL Standards Group
301 |  | Review V16 Connectionless/Standardization white Paper (provided by Mike Matyas (Boeing) and Clarify terminology | VDL Standards Group | VDL Standards Group
302 |  | Review A618 D3S9 with v16 inputs | VDL Standards Group | VDL Standards Group
303 |  | Review A631 D2S9 with v16 inputs | VDL Standards Group | VDL Standards Group
304 |  | Review VDL Enhancement WP (Protocol Requirements) | VDL Standards Group | VDL Standards Group
305 |  | Stephane to update Enhancement WP | Stephane Pelleschi | Collins Aerospace
307 |  | Submit A618 D3S9 for posting | Jose | ARINC IA / SAE ITC |  |  | Posted
308 |  | Review A631 D2S9 for posting | Jose | ARINC IA / SAE ITC |  |  | In work
310 |  | Schedule the next Joint Online Conference (March 30th and April 6th) | Jose | ARINC IA / SAE ITC
311 |  | Schedule the next Joint Meeting (June 1-4, 2021) | Jose, Stephane, Dongsong | Leadership Team |  |  | Dongsong and Stephane to schedule RTCA and EUROCAE Call Notice
March 30 and April, 2021 - Conference Call
Discuss terms ATN/IPS and IPS -- and how to make clear to all
315 |  | Review updated VDL Enhancement List (Requirements - Provided by Stephane
Review updated Collins Aerospace Architectural Diagrams - Provided by Stephane
May 3, 2021 - Conference Call
320 |  | Reviewed RTCA SC-214 ToR as presented by Thomas Mustach
321 |  | Consider if Air/ to Ground VDLM2 Interoperability to be added to ToR
322 |  | Thomas Mustach to distribute ToR an
323 |  | Reuest VDR Sensing Mitigattion Option preferences from Boeing and ICAO
324 |  | Stephane (EUROCAE) / Christophe (Eurocontrol) to contact EASA Inquire/Coordinate their opinion on VDR Sensing mitigation option
325 |  | Schedule June Meeting preparatory Admin Session - May 21st 10:00 AM to 12:00PM
May 4, 2021 Connectionless Conference Call
340 |  | Review VDL Exhancement Working Paper updates - Honeywell Consolidated diagram combining option
341 |  | Contact ICAO and IPS Group for Information on A/C being declared "secure"
342 |  | Update Diagram/s adding Centralized VDL (for the right hand side)
May 21, 2021 Connectionless Conference Call
345 |  | Review Updated VDL Enchancement WP - maintained by Stephane - Collins Aerospace
Distribute June 1-4, 2021 Meeting Agenda
Review and update Claire's VDL Enhancement Comparison doc due by May 28, 2021 !
June 1-4, 2021 Virtual Joint Meeting
350 |  | Submit ToR with Condition (A or B) depending if EUROCAE Council authorized WG-78 on June 17th (PMC). Claire to brief groups | Claire Robinson
351 |  | Radio Experts to recommend Message Length Value (acceptable, average, too long threshold) for Radio Suppliers (send Tom's questions) | Tom, Jose, Stephane and Dongsong
352 |  | Next step in Radio Decision (Make optional, for all forward fits only, include in 224E, bundle w other features (e.g., advance vdl)
353 |  | Tom McGuffin (Spectralux) to update proposal based on meeting results (Radio see 351) | Tom McGuffin
354 |  | Schedule VDR Session _ TBD |  |  |  |  | Date is stil TBD
355
356
357 |  | Stephane to provide slides (Radio how it will impact cert in existing radios) Stephae to coordinate with Thomas Mustach (FAA) | Stephane | Collins Aerospace
358 |  | Distribute June 22nd VDL/IPS Teams Invitation Meeting at IPS Subcommittee Meeting | Jose, Stephane, Dongsong
359 |  | Prepare Requirements document for review before VDL Group submits to IPS Groups (coordinate with Luc and Greg for IPS session w/ VDL) | Stephane | Collins Aerospace
360 |  | IPS Group to provide Security and other requirement for VDL to support ATN/IPS _ by end of Sept 2021
361 |  | Claire to update VDL Comparison with the Table in today's Honeywell Presentation | Claire Robinson | Universal Avionics
362
363
364 |  | SITA to provide proposal for Companion Document (Ref VDL Items Matrix) | Zbig | SITA
365 |  | SITA to provide proposal update on Cenralized/Super VG Station (Lab to trial ) | Zbig | SITA
366 |  | Revive L3 / Tom contact to complete L3 CMU/FMS invetigation by Dan/Tom (now Joel) Q5 or Qx issues. I send email to L3 more data | Joel | L3Harris Technologies
367 |  | Airframers to provide their input CMU / FMS transfer issue | Luc and Kareem | Airbus and Boeing
368 |  | Can Tech Center perform test with real LRUs setup (FMS') ask Peter Muraca | Peter Muraca | The FAA
369 |  | Collect and distribute meeting presentations | Jose, Stephane, Dongsong
370 |  | Honeywell and Collins Aerospace to compare Orange Protocal with RFC 1356 | Stewart and Stephane
371 |  | DSP to provide info on GSIF, Sould be dynamic was last update (dynamic GSIF handling) | Zbig / Ron | SITS/Collins IMS
372 |  | Collins IMS (Ron) will inverstigate and report FRMR spikes incidets
373 |  | Provide DLUF info (Monday and Tuesday, September 13 and 14, from 9 AM to 12 PM), Airlines Only meeting (Wednesday, Sept 15 9-10AM) | Jose Godoy | ARINC IA / SAE ITC |  |  | SMA Available
374 |  | Schedule next Joint Conference Calls June 24th for addressing and June 29th for Orage and other protocols discusson | Jose Godoy | ARINC IA / SAE ITC
June 22, 2021 VDL/IPS at IPS Meeting
375 |  | Greg Siccone (Boeing) presented the Airbus presentation on ARINC 858
376 |  | Stephane Pelleschi (Collins Aerospace) presented VDL/IPS Requirements Matrix; Sy=tephane to update the matrix with meeting results | Stephane Pelleschi | Collins Aerospace
377 |  | Risk Assessmnet Results expected at same time as Deliverables (MOPS, MASPS, ARINC 631)
378 |  | VDL & SATCOM, should be treated the same? (IPS/AGCS (SATCOM) Conference on August 4th (Jose and Paul to Arrange Teams Meeting) | Jose and Paul | ARINC IA / SAE ITC |  |  | Conference on August 4th (Jose and Paul to Arrange Teams Meeting
June 24, 2021 - Addressing
380 |  | Present and Review SITA white paper (Supers VGS _ IPS Support _ Vs Orange) - Jocelyn
381 |  | Present and Review Collins Aerospace white paper (VDL Enhancement - Addressing) Stephane/Ron
June 29, 2021 - VDL Protocols
385 |  | Review IP / VDL Interface options
386 |  | Present and Review Honeywell white paper (RFC 1356 (8208) Vs Orange - Tom Judd _ HI Potential Solution
387 |  | Present and Review Collins Aerospace white paper (Original Orange + Selective Retransmission ) - Stephane/Madhu |  |  |  |  | How does Air and Gnd synchronize with the Orange Protocol ? / UI or INFO frames for IPS support ?
388 |  | Modify the Collins white paper = add sequencing | Stephane Pelleschi | Collins Aerospace
389
390 |  | Schedule next Conference Calls July 21st
July 21, 2021 - Protocols
391 |  | Present and Review MITRE white paper (VDLM2 IO Support Options - ComparisonDr. Dongsong Zeng
392 |  | Present and Review SITA white paper (Supers VGS _ IPS Support _ Vs Orange) - Jocelyn
393 |  | Present and Review Collins Aerospace white paper (Orange Over INFO Frames) Stephane/Ron
394
395
396 |  | Schedule next Joint Conference Call TBD | Jose Godoy | ARINC IA / SAE ITC
July 29, 2021 - Joint Conference
400 |  | Present and Review Collins Aerospace new white paper - Ron
401 |  | Present and Review MITRE white paper (VDLM2 IO Support Options - ComparisonDr. Dongsong Zeng
402 |  | Distribute and Fill out Technology Preference Survey , Feedback needed prior to September meeting (Decision/s will be made)) | Dongsong
403 |  | Surveys required by August 6th (with Conference arranged by RTCA) and Survey Review on Sept 23rd | ALL |  |  |  | Return edited Surveys (your company suggestions) by August 6th -
404 |  | Next Meeting on Sept 15-17, 2021 (after DLUF) | Jose Godoy or RTCA
405 |  | Schedule Augus 6th Meeting (WebEx by RTCA) | Claire/Dongsong
406 |  | Schedule Augus 23rd Meeting (Teams Meeting or WebEx) | Jose Godoy or RTCA
September 15-17, 2021 Virtual Joint Meeting
410 |  | Request HI (Michal) presentation and others from IPS / VDL Session
411 |  | Is an APIM needed for A758?
412 |  | Update A618 with Brasilian freq inputs (IMS DLUF freq presentation and TomMcGuffin inputs (StectraLux)
413 |  | Request SITA presentation - with Three Options - Super VGS/IPS Support/Test - trials @ Honeywell Lab
414 |  | MOPS and MASPS updates per Tom's (StectraLux) slides
415 |  | Next Joint Meeting - October 4 - VDL Certification - Stephane WebEx
416
November 19, 2021 - Joint Conference
420 |  | Avionics Suppliers to provide analysis of oprion 1, such as the availability of the air ground status to the CMU. What is assumed if it is not present (defaults to in air condition ?) REQUIRED BY END OF WORK THURSDAY, DECEMBER 2 SO DECISION MAY BE MADE ON FRIDAY, DECEMBER 3, 2021 | Avionics Suppleiers | Avionics Suppleiers
421 |  | Avionics Suppliers to provide if the CMU can detect if the data for the Air Ground status is not available - REQUIRED BY END OF WORK THURSDAY, DECEMBER 2 SO DECISION MAY BE MADE ON FRIDAY, DECEMBER 3, 2021 | Avionics Suppleiers | Avionics Suppleiers
422 |  | Collins Aerospace IMS and SITA to cuantify the number of aircarft reporting incorrect air ground status - REQUIRED BY END OF WORK THURSDAY, DECEMBER 2 SO DECISION MAY BE MADE ON FRIDAY, DECEMBER 3, 2021 | Steve and Zbig | Collins Aerospace IMS and SITA
423 |  | Claire to check MOPS to vefiy if the Air/Gnd requiremnts (per Richard's wmail) are tested and incuided in the MOPS - REQUIRED BY END OF WORK THURSDAY, DECEMBER 2 SO DECISION MAY BE MADE ON FRIDAY, DECEMBER 3, 2021 | Claire | Universal Avionics
424 |  | Christophe (Eurocontrol) to provide presentation on impact of mixed frequency (providing ground and air services) - REQUIRED BY END OF WORK THURSDAY, DECEMBER 2 SO DECISION MAY BE MADE ON FRIDAY, DECEMBER 3, 2021 | Christophe | EUROCONTROL