## README
A658 Appendix D - Updates
IPS Standardization Gap Analysis
INTRODUCTION |  | Industry stakeholders who participated in the development of the ARINC 658 roadmap document conducted a detailed analysis to understand and assess ATN/IPS-related standardization activities. In particular, the analysis identified gaps where the industry stakeholders believe that a standard is required but an associated standardization activity is not yet identified. The primary objective of the analysis was to identify the need for new ATN/IPS-related ARINC Standards and to identify existing ARINC Standards that may require modification to support ATN/IPS. However, having a comprehensive picture of ATN/IPS-related standardization efforts across standards organizations also helps to minimize duplication of effort and facilitates the identification of topics that might benefit from cross-organization coordination.
WORKBOOK TABS
| README | This tab, which provides an overview of the IPS Standardization Gap Analysis workbook
| IPS Gap Analysis | Latest version of the IPS Standardization Gap Analysis
| IPS Gap Analysis- changes | Latest version of the IPS Standardization Gap Analysis highlighting (in purple) entries that are changed from the prior version.
| List Items | Drop-down menu items used in the analysis -- DO NOT CHANGE
IPS GAP ANALYSIS COLUMNS
A | Work Area | Together, these columns organize the standardization activities with respect to the ATN/IPS work areas and sub-work areas identified in Sections 3 and 4 of the ARINC 658 Roadmap Document.
B | Sub-work Area
C | Work Type | Activity work type, which may take one of the following values (using a pull-down menu):
|  |  | STD | Standard / Specification
|  |  | GM | Guidance Material
|  |  | ANA | Analysis
|  |  | PRO | Prototype Implementation
|  |  | VAL | Validation
|  |  | VER | Verification
|  |  | V&V | Verification and Validation
|  |  | OPR | Operations
D | Work Status | Status of the work activity, which may take on one of the following values (using a pull-down menu):
|  |  | Complete | Work activity is complete
|  |  | In-Progress | Work activity is started and in-progress
|  |  | Planned | Work activity is planned, but not yet started
|  |  | Proposed | Work activity is proposed, but not yet planned or started
|  |  | *GAP* | Identified work activity gap
|  |  | *TBD/TBS* | Work activity to be determined / scheduled (e.g., future activity based on need and business case)
E | A658 Section where gap is addressed | A reference to the section in the A658 Roadmap Document where potential actions to address an identified gap are described. The following color coding is used:
|  |  | # | A658 section in which a gap is described; the gap still exists at the time of this update
|  |  | # | A658 section in which a gap is described; work activity to address the gap has been initiated, per the status in Column D
No gap; a work activity was already initiated prior to the publication of A658
F | Standards Organization | Taken together, these Columns F&G identify the Standards Development Organization and the associated working group and sub-working group (optional) associated with the specified standardization activity. The Standards Development Organization is selected using a pull down menu, and the working group / sub-group entry is free text.
G | Working Group / Sub-group
H | Activity Description | Description of the standardization activity (normal font, black text) OR a description of an identified gap (italicized font, red text)
I | Artifact | A document number, if known, for the planned output of the work activity.
J | Planned Completion Date | Date, if known, when the output of the work activity is expected to be completed.
L, M, N | Input Dependency | Other activities/artifacts on which the standardization activity in Col H is dependent. Includes a need date and current availability date. Availability Date > Need Date is a gap.
O, P, Q | Output Dependency | Other standardization activities that are dependent on the activities in Col H. Includes a need date and current availability date. Availability Date > Need Date is a gap.
R | Additional Comments | Additional commentary, clarification, or observations offered by industry participants

## IPS Gap Analysis 03-OCT_changes
A658 Appendix D - Updates
IPS Standardization Gap Analysis | [6 empty] | Note: Ú indicates a pull-down menu selection |  |  | Columns L-Q are new since M07. This info reflects results of coordination telecons among ICAO, RTCA, EUROCAE, AEEC
Last Update: | 2018-10-03
A | B | C | D | E | F | G | H | I | J | L | M | N | O | P | Q | R
2018-10-03 C: IPS-related Standardization Activities | Dependencies
Work Area | Sub-work Area | Work Type Ú | Work Status Ú | A658 Section where Gap is Addressed | Standards Organization Ú | Working Group / Sub-group | Activity Description / Gap Description | Artifact |  | Activity/Artifact has a Dependency on (needs input from) |  |  | There is a Dependency on the Activity/Artifact (is an output to)
2018-10-03 I: Document No.; 2018-10-03 J: Planned Completion Date (MMM-YYYY) | Input Dependency FROM | Input Need Date | Input Availability Date | Output Dependency TO | Output Need Date | Output Availability Date | Additional Comments
Application Interfaces | DSI (legacy) |  | In-Progress |  | ICAO | WG-I | ATNPKT definition for backward compatibility with existing dialog service-based OSI applications | Doc. 9896 | Nov-2020 | Doc. 9880 |  | Available Now | ICAO WG-I internal |  | Available Now | Job Card: CP-DCIWG.006.01
|  | STD | *GAP* | 5.4.4 | ICAO | WG-I | Mapping between OSI addresses and IPS address (see comment) Updates to DSI -- application level (CM), overall format, dependence on mobility | Doc. 9896 | TBD | ICAO WG-I MSG (IPS addressing and mobility solution) |  |  | RTCA/EUROCAE AEEC IPS | 2Q-2019 | TBD (pending output of DCIWG meeting Oct 2018) | 1. Consider multi-phased approach, where initial deployments use address mapping from OSI to IPS, but future deployments may be IPS addresses only. 2. May start in ICAO and move to RTCA/EUROCAE (SC-214/WG-78)
| ACARS (legacy) | STD | *GAP* | 5.4.1.1, 5.4.4 | ICAO | WG-I | Encapsulation of FANS (e.g., A618) for IPS (e.g., mapping of FANS to IPS DS), including what parts of the ACARS message are included (e.g., SMI) | Doc. 9896 GM | TBD | AEEC IPS | 1Q-2019 |  | RTCA/EUROCAE | 2Q-2019 |  | Current thinking is that this topic is covered under existing job card; pending output of DCIWG Oct 2018 meeting
|  | STD | *TBD/TBS* | 5.4.1.2.7 | AEEC | DLK | Standardization of air-ground messaging layer for AOC (A620 non-safety) applications over IP (MIAM over IPS) | ARINC 841 | TBD | A858; Doc. 9896 ATNPKT format | TBD (future APIM, see comment) | End-2019 | None |  |  | The need date for updating the ARINC 841 MIAM Standard is TBD
| Native IP (future) | STD | In-Progress | 5.4.4 | AEEC | IPS | Support for native IP applications | ARINC 858 | Dec-2019 | Doc. 9896 ATNPKT format | TBD (future APIM, see comment) | TBD (future APIM, see comment) | None |  |  | Note that this may be addressed in a future supplement to A858 and not the initial release
Mobility | Inter-subnetwork | ANA | In-Progress |  | ICAO | WG-I / MSG | Mobility sub-group to analyze Multi-link mobility options (e.g.,MIPv6, AERO, LISP) and recommend a candidate | Working Papers |  | LISP - SESAR 15.2.4 AERO - IETF RFC
|  | STD | Planned |  | ICAO | WG-I / MSG | Mobility technical provisions | Doc. 9896 | Nov-2020 |  |  |  | RTCA/EUROCAE AEEC IPS (?) | 3Q-2018 (RFCs) |  | FRAC for Profiles in Dec-2018. But, final Profiles to be published jointly with MASPS in Dec-2019.
| Inter-region | STD | Planned |  | ICAO | WG-I / MSG | Mobility technical provisions | Doc. 9896 | Nov-2020 |  |  |  | RTCA/EUROCAE MASPS | 1Q-2019 |  | Job Card: CP-DCIWG.006.01
Upper Layers | Transport Options | ANA | In-Progress |  | ICAO | WG-I | Further refinement of transport options, whether UDP/TCP/etc. should both be supported, and including reliability extensions | Working Papers | [7 empty] | During WG-I/27, Airbus presented proposal to specify UDP for DS-based apps (i.e., use ATNPKT). Group agreed; Airbus to prepare AP
|  | STD | In-Progress |  | ICAO | WG-I | Document IPS transport provisions | Doc. 9896 | Nov-2020
| Supporting Services Identification | STD | In-Progress |  | ICAO | WG-I WG-I / MSG | Identify additional services necessary to support IPS, e.g. ICMP, local BGP, etc. | Doc. 9896 | Nov-2020 |  |  |  | RTCA/EUROCAE Profiles (If other RFCs are mandated) | 1Q-2019 (RFCs) See Comment |  | FRAC for Profiles in Dec-2018. But, final Profiles to be published jointly with MASPS in Dec-2019.
| Profile | STD | In-Progress |  | EUROCAE + RTCA | WG-108 / SC-223 | IPS profile | ED-TBD DO-TBD | Dec-2018 (see comment) | [6 empty] | FRAC for Profiles in Dec-2018. But, final Profiles to be published jointly with MASPS in Dec-2019.
| E2E Guidance | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | IPS End-to-End interop guidance (MASPS) | ED-TBD DO-TBD | Dec-2019 | Doc. 9896 inputs for upper layers | 1Q-2019
Lower Layer Interfaces | AeroMACS | STD | Complete |  | ICAO | WG-S | AeroMACS SARPS | Annex 10 | Complete
|  | STD | Complete |  | ICAO | WG-S | AeroMACS Technical Manual and Guidance | Doc. 10044 | Complete
|  | STD | Complete |  | RTCA | SC-223 | AeroMACS Profile | DO-345 | Complete
|  | STD | Complete |  | RTCA | SC-223 | AeroMACS MOPS | DO-346 | Complete
|  | STD | Complete |  | AEEC | AeroMACS | AeroMACS Transceiver and Installation | ARINC 766 | Complete
|  | STD | *TBD/TBS* | 5.4.1.2.4 | AEEC | AeroMACS | AeroMACS architecture concepts (for segregation) to support IPS may not be defined adequately for developers | ARINC 766 | TBD | A858 (I/F with IPS Core functions, multi-link) Doc. 9896 (multi-link technical provisions TBC) | TBD (future APIM, see comment) | End-2019 | EUROCAE/RTCA MASPS? | ? | TBD (future APIM, see comment) | AEEC is monitoring AeroMACS ground station development, installation, and critical mass. The need date for updating the ARINC 766 Standard is TBD if dual connectivity with ACD and AISD is required in the radio for IPS.
| LDACS | STD | In-Progress |  | ICAO | WG-T | LDACS SARPS | Annex 10, Vol III | 2018-12-01 | [6 empty] | Job Card: CP-DCIWG.010.01
|  | STD | In-Progress |  | ICAO | WG-T | LDACS Technical Manual | Doc. TBD | 2018-12-01 | [6 empty] | Job Card: CP-DCIWG.010.01
|  | GM | Planned |  | ICAO | WG-T | LDACS Guidance Material | Doc. TBD | 2022-12-01 | [6 empty] | Job Card: CP-DCIWG.010.01
|  | STD | Planned |  | EUROCAE | WG-82 | Development of MOPS/MASPS | Doc. TBD | TBD
|  | STD | *TBD/TBS* | 5.4.1.2.5 | AEEC | TBD | LDACS transceiver and interfaces | ARINC TBD | TBD | A858 (I/F with IPS Core functions, multi-link) Doc. 9896 (multi-link technical provisions TBC) | TBD (future APIM, see comment) | End-2019 | EUROCAE/RTCA MASPS? | ? | TBD (future APIM, see comment) | AEEC member airlines have yet to discuss the LDACS concept, potential benefits, timing, and other factors that might drive the need for standardization.
| SATCOM (current) - Performance Class B | STD | Planned |  | ICAO | WG-T | Update SARPs (generic) and Technical Manual, including technology-specific parts (e.g., INMARSAT and Iridium) | Doc. 9925 (new part) Annex 10 Vol3 Ch4 | TBD
|  | STD | Planned |  | EUROCAE | WG-82 | MOPS / MASPS updates for IPS | ED-TBD | TBD
|  | STD | Planned |  | RTCA | SC-222 | MOPS / MASPS updates for IPS | DO-262x / DO-343x | TBD
|  | STD | In-Progress |  | AEEC | AGCS | MK3 Aviation SATCOM Systems Form/Fit/Function - additional work currently in progress to focus on ACARS (which may support accommodation) | ARINC 771 ARINC 781 | TBD | None
|  | STD | *GAP* | 5.4.1.2.6 | AEEC | AGCS | Updates (as necessary) and architecture concepts to support IPS | ARINC 771 ARINC 781 | TBD | A858 (I/F with IPS Core functions, multi-link) Doc. 9896 (multi-link technical provisions TBC) | TBD (future APIM, see comment) | End-2019 | EUROCAE/RTCA MASPS? | ? | TBD (future APIM, see comment) | Some initial placeholder text in planned next versions (2018), but future update expected to fully address IPS.
| SATCOM (future) - Performance Class A | STD | Proposed |  | ICAO | WG-T | SATCOM Class A Technical Manual and Guidance and SARPS | Doc. TBD | TBD | [6 empty] | Proposal presented by Eurocontrol during ICAO CP/2 in October 2016. Draft Job Card presented during ICAO CP/2 in WP02.
|  | STD | In-Progress |  | EUROCAE | WG-82 | MOPS / MASPS updates for IPS | ED-TBD | TBD
|  | STD | *TBD/TBS* | 5.4.2 | RTCA | SC-222 | Extension of current MOPS/MASPS to accommodate future SATCOM and IPS | DO-TBD | TBD
|  | STD | *TBD/TBS* | 5.4.1.2.6 | AEEC | AGCS | Updates (as necessary) and architecture concepts to support IPS | ARINC TBD | TBD | A858 (I/F with IPS Core functions, multi-link) Doc. 9896 (multi-link technical provisions TBC) | TBD (future APIM, see comment) | End-2019 | EUROCAE/RTCA MASPS? | ? | TBD (future APIM, see comment) | See SATCOM Performance Class B. Current SATCOM Performance Class B will evolve and are expected to serve airline needs for the foreseeable future.
| Non-safety SATCOM | STD | Complete |  | AEEC | KSAT | Track non-safety SATCOM activities to ascertain whether there are concepts/techniques that can be leveraged for IPS | ARINC 791 ARINC 792 | Complete
| VDLm2 | STD | In-Progress | 5.4.1.2.3 | AEEC | Joint VDL Group | Updates for VDLm2 support of IPS, e.g., modifications to VDL Tech Manual to address connectionless VDLm2 exchange, and accommodate IP packets in VDLm2 as a result of analyses including e.g., reliability mechanisms, access network security, etc. | ARINC 631-8 Doc. 9776 input | Dec-2020 | WG-I SSG Security Risk Analysis | 4Q-2018 |  |  |  |  | APIM 17-002A (Per Paul P., APIM 17-002A in progress to extend date to Dec-2020)
[10 empty] | A858 (I/F with IPS core functions, multi-link) | 4Q-2018 | 4Q-2018 (A858 functions) End-2019 (A858 interface/multi-link), | EUROCAE/RTCA MASPS? | ? | 3Q-2020 | bar: 2018-10-03 J
|  | STD | Planned | 5.4.4 | ICAO | WG-M | Updates for VDLm2 support of IPS, e.g., modifications to VDL Tech Manual to address connectionless VDLm2 exchange, and address IP packets in VDLm2. | Doc. 9776 | TBD-2021 | WG-I SSG Security Risk Analysis | 4Q-2018 |  |  |  |  | Expected 6 months after MASPS/MOPS updates
[10 empty] | A858 (I/F with IPS core functions, multi-link) | 4Q-2018 | 4Q-2018 (A858 functions) End-2019 (A858 interface/multi-link), | bar: 2018-10-03 J
|  | STD | In-Progress | 5.4.2 | RTCA | SC-214 / VDLSG | Updates for VDLm2 support of IPS, e.g., modifications to VDL Tech Manual to address connectionless VDLm2 exchange, and address IP packets in VDLm2. | DO-224E (MASPS) DO-281D (MOPS) | Apr-2019 | WG-I SSG Security Risk Analysis | 4Q-2018 |  |  |  |  | Current dates per TOR 5/31/18. May shift to Dec-2020 to align with revised A631 date.
[10 empty] | A858 (I/F with IPS core functions, multi-link) | 4Q-2018 | 4Q-2018 (A858 functions) End-2019 (A858 interface/multi-link), | bar: 2018-10-03 J
|  | STD | In-Progress | 5.4.2 | EUROCAE | WG-92 | Updates for VDLm2 support of IPS, e.g., modifications to VDL Tech Manual to address connectionless VDLm2 exchange, and address IP packets in VDLm2. | ED-92D (MOPS) | Apr-2019 | Doc9896 for security | 4Q-2018 |  |  |  |  | Current dates per TOR 4/26/18. May shift to Dec-2020 to align with revised A631 date.
[10 empty] | A858 (I/F with IPS core functions, multi-link) | 4Q-2018 | 4Q-2018 (A858 functions) End-2019 (A858 interface/multi-link), | bar: 2018-10-03 D; 2018-10-03 J
| Distributed Radio Architecture | STD | In-Progress | New M07 | AEEC | SAI | Focus is mainly hardware, but there may be impact on the overall architecture and interfaces with respect to IPS (e.g., radios on a network) | ARINC TBD | Apr-2020 | A858 (I/F with IPS Core functions, multi-link) Doc. 9896 (multi-link technical provisions TBC) | 1Q-2019 | End-2019 | EUROCAE/RTCA MASPS? | ? | ? | APIM 18-003 The initial activity in AEEC SAI will produce hardware architecture recommendations. Any GAP is TBD pending that recommendation.
Naming and Addressing | Naming | STD | In-Progress |  | ICAO | WG-I | Define naming convention and DNS requirements | Doc. 9896 | Nov-2020 | INNOVA TF (prefix size) and Coordination with RTCA/EUROCAE | 1Q-2019 |  | RTCA/EUROCAE MASPS | 2Q-2019 |  | Job Card: CP-DCIWG.006.01
| Addressing | STD | In-Progress |  | ICAO | WG-I | Define addressing | Doc. 9896 | Nov-2020 | INNOVA TF (prefix size) and Coordination with RTCA /EUROCAE | 1Q-2019 |  | RTCA/EUROCAE MASPS | 3Q-2019 |  | Job Card: CP-DCIWG.006.01
| IPv6 Transition Ph1 | ANA | In-Progress |  | AEEC | NIS | Roadmap for IPv6 transition in aviation | ARINC 686 | Oct-2019 | None | [5 empty] | APIM 17-001
| IPv6 Transition Ph2 | STD | Proposed |  | AEEC | NIS | Updates to standards for IPv6 transition as identified during the roadmap activity | ARINC 664pX(other parts and/or new part) | TBD | A858 | TBD (future APIM) | End-2019 | None |  |  | APIM 17-001 (proposed Phase 2)
[10 empty] | RTCA/EUROCAE Profiles | TBD (future APIM) | End-2020
| Administration | OPR | *GAP* | 5.4.4 | ICAO | INNOVA (?) | Processes for on-going administration of IP names and addresses IP database management/translations | TBD | TBD |  |  |  | Name/Address Management Entities | 4Q-2020 | 4Q-2020 | This will need to be determined for mobility
|  | OPR | *GAP* | 5.4.5 | OTHER | IATA | Same as above but for AOC | TBD | TBD |  |  |  | Name/Address Management Entities | 4Q-2020 | 4Q-2020 | This isn't really WG-I but does need to be done consistently with ICAO or else AOC applications may end up with completely different routing logic
Security | Risk Analysis | ANA | In-Progress |  | ICAO | WG-I SSG | Notional end-to-end risk analysis for IPS | Working Papers | Dec-2018 |  |  |  | AEEC IPS/ AEEC Joint VDL | 4Q-2018 | TBD | I think this would be necessary in final determination of use of network-level security (or not)
|  | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | Use the results of the ICAO risk analysis to identify other requirements (e.g., regional constraints) on IPS as part of MASPS | ED-TBD DO-TBD | Dec-2019 | ICAO WG-I Risk Analysis | 1Q-2019 |  | Feedback to other Groups (ICAO, AEEC) | 2Q-2019
| Architecture | GM | Planned |  | ICAO | WG-I & Sec. Panel |  | Doc. 10090 | Nov-2020 | Doc. 10044 |  | Available Now |  |  |  | Job Card: CP-DCIWG.007.01
| End-to-End - Dialogue Service | STD | Complete |  | ICAO | WG-I / SSG | Secure Dialog Service (SDS), end-to-end Dialogue Service application-layer security applicable to both OSI and IPS | Doc. 10094, Part I | Complete | [6 empty] | Complete without validation; complete with validation by Dec-2019
|  | GM | In-Progress |  | ICAO | WG-I / SSG | Secure Dialog Service (SDS) Concept of Operations | Doc. 10094, Part II | Dec-2018
|  | GM | In-Progress |  | ICAO | WG-I / SSG | Secure Dialog Service (SDS) guidance material | Doc. 10094, Part III | Jun-2019
|  | VAL | In-Progress |  | FAA | WJHTC | SDS validation | Validation Report | Dec-2019
| Security Framework | GM | In-Progress |  | ICAO | WG-I / SSG | Overall security framework | Doc. 10090 | Dec-2020 | Doc. 10044 |  | Available Now | RTCA/EUROCAE MASPS | 2Q-2019
| Ground-Ground | STD | In-Progress |  | ICAO | WG-I / SSG | Ground-ground IPS security | Doc. 9896 | Dec-2020 | Doc. 10044 |  | Available Now | RTCA/EUROCAE MASPS | 2Q-2019
| PKI | STD | Complete |  | ICAO | WG-S | AeroMACS PKI Certificate Policy, which includes certificate/CRL profiles. Expected to be reusable for SDS. | Doc. 10044 | Complete | ATA Spec 42 WMF Certificate Profile & Certificate Policy |  | Available Now
|  | VAL | Complete |  | WMF | AWG | AeroMACS test certificates | N/A | Complete
|  | STD | Planned | 5.4.4 | ICAO | WG-I / SSG | PKI Policy for Aeronautical Communications | Doc. 10095 | Dec-2019 |  |  |  | AEEC IPS | 2Q-2019 | TBD | Does some of this have an impact on IPS security?
|  | VAL | Planned | 5.4.4 | ICAO | WG-I / SSG | Public Key Infrastructure Validation | Doc. 10095 | Sep-2020
|  | STD | In-Progress |  | ICAO | SecP / iNNOVA | Security requirements for air-ground | Doc. TBD | TBD |  |  |  | AEEC IPS | 2Q-2019 | TBD | Does some of this have an impact on IPS security?
|  | GM | *GAP* | 5.4.1.2.8 | AEEC | TBD | Key loading and key management necessary for LRU installation and maintenance (e.g., key replacement) -- updates necessary for IPS (all systems) | ARINC TBD | TBD | A858 ICAO tech manual | TBD (future APIM, see comment) | ? | EUROCAE/RTCA MASPS (ground) & Profiles (new RFCs for PKI?) | ? | ? | A Security Concept of Operation is expected to provide focus in terms of standards, scope, and timing.
| Network Layer Security | STD | In-Progress |  | ICAO | WG-I | Definition of the security solution for the network level, including for AOC traffic (VPN) | Doc. 9896 | Dec-2020 | RTCA / EUROCAE Profiles | 4Q-2018 | 4Q-2018
| Aircraft Security Reliance on Ground Security | GM | In-Progress |  | EUROCAE + RTCA | WG-72 / SC-216 | Airworthiness Security Methods and Considerations - Trustworthiness considerations in the security environment | ED-203A DO-356A | Sep-2018
|  | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | IPS End-to-End guidance supporting certification (MASPS) | ED-TBD DO-TBD | Dec-2019 | ICAO WG-I AEEC IPS | 1Q-2019 |  | AEEC IPS | 4Q-2018 | 4Q-2018
|  | GM | *GAP* | 5.2 ? | OTHER | ARAC (?) | Address this topic and provide recommendations to FAA/EASA | TBD | TBD
|  | GM | *GAP* | 5.2 | FAA |  | FAA/EASA regulation update or new process?? Impact on certification if aircraft has reliance on the ground | TBD | TBD
|  | GM | *GAP* | 5.2 ? | EASA |  | FAA/EASA regulation update or new process?? Impact on certification if aircraft has reliance on the ground | TBD | TBD
| Security Management | STD | *GAP* | 5.4.2 | OTHER | TBC | Overall security processes regarding incident management, logging/analysis, Aviation ISAC, etc. | TBD | TBD
| Security Policy | STD | Planned |  | ICAO | WG-I / SSG | ICAO Overall Security Policy Requirements | Doc. TBD | TBD | [6 empty] | Job Card: CP-DCIWG.007.01
Performance | QoS | STD | Planned |  | ICAO | WG-I / MSG | Map ATN QoS to IPS DIFFSERV (should be defined as an end-to-end mechanism) | Doc. 9896 | Nov-2020 | Doc. 9880 Doc. 10044 |  | Availabe Now |  |  |  | Doc 9880 is done, so think this is already available?
|  | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Detailed QoS mechanisms for segregating ATS and AOC traffic (part of ATN/IPS router form factor / architecture??) | ARINC 858 | Dec-2019 | Doc. 9880 Doc. 10044 | 4Q-2018 | Availabe Now | EUROCAE/RTCA MASPS? | ? | ? | Doc 9880 is done, so think this is already available?
| Compression | STD | In-Progress |  | ICAO | WG-I | ATNPKT update to include compression provisions | Doc. 9896 | Nov-2020 | RC-IMS Proposal | [5 empty] | Do we need to move all this to Doc. 9896, or would this stay in A858?
|  | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Standardization of proposed compression techniques | ARINC 858 | Dec-2019 | Doc. 9896 | 4Q-2018 | TBD |  |  |  | Assumes compression will be standardized at ICAO level
| RCP (B2) | STD | Complete |  | EUROCAE + RTCA | WG-78 / SC-214 | SPR | ED-228A / DO-350A ED-122 / DO-306 | Mar-2016 Oct-2007 |  |  |  | EUROCAE/RTCA MASPS? | ? | ?
| RCP (Beyond B2) | STD | *TBD/TBS* | NEW M06 | ICAO | ODLWG | RCP/RSP updates for beyond B2 | Doc. 9869 | TBD
|  | STD | *TBD/TBS* | 5.4.3 | EUROCAE | WG-78 | SPR update for beyond-B2 services | ED-TBD | TBD
|  | STD | *TBD/TBS* | 5.4.3 | RTCA | SC-214 | SPR update for beyond-B2 services | DO-TBD | TBD
| Multi-link | STD | Planned |  | ICAO | WG-I / MSG | Multi-link technical provisions | Doc. 9896 | Nov-2020 | SESAR PJ14.2.4 |  |  | EUROCAE/RTCA MASPS? | ? | ?
|  | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Detailed definition of multi-link based on ICAO definition. | ARINC 858 | Dec-2019 | ICAO WG-I MSG | 1Q-2019 | ? | EUROCAE/RTCA MASPS? | ? | ? | The CMU standard would need to refer to the IPS router standard for the specification of the multilink functional specification, I.e., the CMU is one instance of an IPS router.
| MASPS | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | IPS End-to-End guidance supporting certification (MASPS) | ED-TBD DO-TBD | Dec-2019 | ICAO WG-I AEEC IPS | 1Q-2019
Form / Fit / Interfaces | CMU | STD | *GAP* | 5.4.1.2.2 | AEEC | DLK | CMU specification updates to support IPS (e.g., including segregation, new interfaces, data logging, traffic shaping/filtering, etc.) | ARINC 758 | TBD | A858 | TBD (future APIM, see comment) | End-2019 | None |  |  | Although A758 is open, the current APIM 17-003 addresses Ethernet interface but does not include IPS; a future APIM will be necessary
| IPS Router | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Specification for an IPS-specific router or router function (e.g., including segregation, new interfaces, etc.) | ARINC 858 | Dec-2019 | Doc. 9896 RTCA / EUROCAE Profiles | 1Q-2019 | ? | EUROCAE/RTCA MASPS? | ? | ? | AEEC IPS should review A758 document as a reference for structure and content for current CMF
Ground Systems | OSI/IPS and ACARS/IPS Gateway | GM | In-Progress | 5.4.4 | ICAO | WG-I | Technical definition of what needs to maintained between OSI and IPS in order to maintain application correlation. (Ground requirements RTCA/EUROCAE involvement?) | Doc. 9896 and/or ARINC 858 (see comment) | Nov-2020 | [6 empty] | This could be the gateway definition level, and may be either in A858 or Doc 9896
|  | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Definition of ACARS-IPS gateway function | ARINC 858 | Dec-2019 |  |  |  | ICAO WG-I | 2Q-2019 | 1Q-2019
|  | STD | Planned | 5.4.4 | EUROCAE + RTCA | WG-108 / SC-223 | Ground system considerations for IPS end-to-end interoperability and performance as part of MASPS | ED-TBD DO-TBD | Dec-2019 | AEEC IPS | 1Q-2019
| IPS NW Topology | ANA | Planned |  | ICAO | WG-I | Discuss network topologies and proposals (e.g., DSP-centric solution) | Working papers |  |  |  |  | EUROCAE/RTCA MASPS? | ? | ?
[13 empty] | AEEC IPS | 1Q-2019
|  | GM | *GAP* | 5.4.5 | OTHER | Regional CAAs | Regional implementation of IPS based on the ICAO standard | TBD | TBD | [6 empty] | A858 "guidance" since that’s where the gateway will be?

## IPS Gap Analysis 21-JUN (OLD)
A658 Appendix D - Updates
IPS Standardization Gap Analysis | [6 empty] | Note: Ú indicates a pull-down menu selection
Last Update: | 2018-06-21
A | B | C | D | E | F | G | H | I |  | J | R
IPS-related Standardization Activities
Work Area | Sub-work Area | Work Type Ú | Work Status Ú | A658 Section where Gap is Addressed | Standards Organization Ú | Working Group / Sub-group | Activity Description / Gap Description | Artifact | Dependencies | Planned Completion Date (MMM-YYYY) | Additional Comments
Application Interfaces | DSI (legacy) |  | In-Progress |  | ICAO | PT-I | ATNPKT definition for backward compatibility with existing dialog service-based OSI applications | Doc. 9896 | Doc. 9880 | Nov-2020 | Job Card: CP-DCIWG.006.01
|  | STD | *GAP* | 5.4.4 | ICAO | PT-I | Mapping between OSI addresses and IPS address (see comment) Updates to DSI (?) | Doc. 9896 | Doc. 9896 (IPS addressing) |  | 1. Consider multi-phased approach, where initial deployments use address mapping from OSI to IPS, but future deployments may be IPS addresses only. 2. May start in ICAO and move to RTCA/EUROCAE (SC-214/WG-78)
| ACARS (legacy) | STD | *GAP* | 5.4.4 | ICAO | PT-I | Provisions for accommodation of FANS messages | Doc. 9896
|  | STD | *GAP* | 5.4.1.1 | ICAO | PT-I | Encapsulation of FANS (e.g., A618) for IPS (e.g., mapping of FANS to IPS DS), including what parts of the ACARS message are included (e.g., SMI) | Doc. 9896 | Doc. 9896 (above)
|  | STD | *GAP* | 5.4.1.2.7 | AEEC | DLK | Standardization of air-ground messaging layer for AOC (A620 non-safety) applications over IP (MIAM over IPS) | ARINC 841
| Native IP (future) | STD | In-Progress | 5.4.4 | AEEC | IPS | Support for native IP applications | ARINC 858
Mobility | Access Network | ANA | In-Progress |  | ICAO | PT-I / MSG | Mobility sub-group to analyze Mobility options for the Access Sub-Networks (Terrestrial (VDL-2 and LDACS), AeroMACS, and Satellite) and protocols (e.g. PMIPv6, other) | Working Papers | AeroMACS, L-DACS, SATCOM, and VDL Standards |  | Note that intra-subnetwork mobility is not part of PT-I responsibility. PT-I may review what is offered by each subnetwork. Otherwise, this is out of scope
| Inter-subnetwork | ANA | In-Progress |  | ICAO | PT-I / MSG | Mobility sub-group to analyze Multi-link mobility options (e.g.,MIPv6, AERO, LISP) and recommend a candidate | Working Papers | LISP - SESAR 15.2.4 AERO - IETF RFC
|  | STD | Planned |  | ICAO | PT-I / MSG | Mobility technical provisions | Doc. 9896 |  | Nov-2020
| Inter-region | STD | Planned |  | ICAO | PT-I / MSG | Mobility technical provisions | Doc. 9896 |  | Nov-2020 | Job Card: CP-DCIWG.006.01
Upper Layers | Transport Options | ANA | In-Progress |  | ICAO | PT-I | Further refinement of transport options, whether UDP/TCP/etc. should both be supported, and including reliability extensions | Working Papers
|  | STD | In-Progress |  | ICAO | PT-I | Document IPS transport provisions | Doc. 9896 |  | Nov-2020
| Supporting Services Identification | STD | In-Progress |  | ICAO | PT-I PT-I / MSG | Identify additional services necessary to support IPS, e.g. ICMP, local BGP, etc. | Doc. 9896 |  | Nov-2020
|  | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | MASPS | ED-TBD DO-TBD |  | Dec-2019
| Profile | STD | In-Progress |  | EUROCAE + RTCA | WG-108 / SC-223 | IPS profile | ED-TBD DO-TBD |  | 2018-12-01
| E2E Guidance | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | IPS End-to-End interop guidance (MASPS) | ED-TBD DO-TBD | ICAO WG-I AEEC IPS | Dec-2019
Lower Layer Interfaces | AeroMACS | STD | Complete |  | ICAO | PT-S | AeroMACS SARPS | Annex 10 |  | Complete
|  | STD | Complete |  | ICAO | PT-S | AeroMACS Technical Manual and Guidance | Doc. 10044 |  | Complete
|  | STD | Complete |  | RTCA | SC-223 | AeroMACS Profile | DO-345 |  | Complete
|  | STD | Complete |  | RTCA | SC-223 | AeroMACS MOPS | DO-346 |  | Complete
|  | STD | Complete |  | AEEC | AeroMACS | AeroMACS Transceiver and Installation | ARINC 766 |  | Complete
|  | STD | *GAP* | 5.4.1.2.4 | AEEC | AeroMACS | AeroMACS architecture concepts (for segregation) to support IPS may not be defined adequately for developers | ARINC 766 |  |  | If dual connectivity with ACD and AISD is required in the radio.
| LDACS | STD | In-Progress |  | ICAO | PT-T | LDACS SARPS | Annex 10, Vol III |  | 2018-12-01 | Job Card: CP-DCIWG.010.01
|  | STD | In-Progress |  | ICAO | PT-T | LDACS Technical Manual | Doc. TBD |  | 2018-12-01 | Job Card: CP-DCIWG.010.01
|  | GM | Planned |  | ICAO | PT-T | LDACS Guidance Material | Doc. TBD |  | 2022-12-01 | Job Card: CP-DCIWG.010.01
|  | STD | Planned |  | EUROCAE | WG-82 | Development of MOPS/MASPS | Doc. TBD
|  | STD | *GAP* | 5.4.1.2.5 | AEEC | TBD | LDACS transceiver and interfaces | ARINC TBD
| SATCOM (current) - Performance Class B | STD | Planned |  | ICAO | PT-T | Update SARPs (generic) and Technical Manual, including technology-specific parts (e.g., INMARSAT and Iridium) | Doc. 9925 (new part) Annex 10 Vol3 Ch4 |  | TBD
|  | STD | Planned |  | EUROCAE | WG-82 | MOPS / MASPS updates for IPS | ED-TBD |  | TBD
|  | STD | Planned |  | RTCA | SC-222 | MOPS / MASPS updates for IPS | DO-262x / DO-343x |  | TBD
|  | STD | In-Progress |  | AEEC | AGCS | MK3 Aviation SATCOM Systems Form/Fit/Function - additional work currently in progress to focus on ACARS (which may support accommodation) | ARINC 771 ARINC 781 |  | TBD
|  | STD | *GAP* | 5.4.1.2.6 | AEEC | AGCS | Updates (as necessary) and architecture concepts to support IPS | ARINC 771 ARINC 781 |  |  | Some initial placeholder text in planned next versions (2018), but future update expected to fully address IPS.
| SATCOM (future) - Performance Class A | STD | Proposed |  | ICAO | PT-T | SATCOM Class A Technical Manual and Guidance and SARPS | Doc. TBD |  | TBD | Proposal presented by Eurocontrol during ICAO CP/2 in October 2016. Draft Job Card presented during ICAO CP/2 in WP02.
|  | STD | In-Progress |  | EUROCAE | WG-82 | MOPS / MASPS updates for IPS | ED-TBD |  | TBD
|  | STD | *GAP* | 5.4.2 | RTCA | SC-222 | Extension of current MOPS/MASPS to accommodate future SATCOM and IPS | DO-TBD
|  | STD | *GAP* | 5.4.1.2.6 | AEEC | AGCS | Updates (as necessary) and architecture concepts to support IPS | ARINC TBD
| Non-safety SATCOM | STD | Complete |  | AEEC | KSAT | Track non-safety SATCOM activities to ascertain whether there are concepts/techniques that can be leveraged for IPS | ARINC 791 ARINC 792
| VDLm2 | STD | In-Progress | 5.4.1.2.3 | AEEC | Joint VDL Group | Updates for VDLm2 support of IPS, e.g., modifications to VDL Tech Manual to address connectionless VDLm2 exchange, and accommodate IP packets in VDLm2 as a result of analyses including e.g., reliability mechanisms, access network security, etc. | ARINC 631-8 Doc. 9776 input |  | Jun-2019
|  | STD | *GAP* | 5.4.4 | ICAO | PT-M (?) | Updates for VDLm2 support of IPS, e.g., modifications to VDL Tech Manual to address connectionless VDLm2 exchange, and address IP packets in VDLm2. | Doc. 9776
|  | STD | *GAP* | 5.4.2 | RTCA | SC-214 / VDLSG | Updates for VDLm2 support of IPS, e.g., modifications to VDL Tech Manual to address connectionless VDLm2 exchange, and address IP packets in VDLm2. | DO-224E (MASPS) DO-218D (MOPS) |  |  | EUROCAE WG-92 (responsible for ED-92) meets jointly with RTCA SC-214 VDLSG.
|  | STD | *GAP* | 5.4.2 | EUROCAE | WG-92 | Updates for VDLm2 support of IPS, e.g., modifications to VDL Tech Manual to address connectionless VDLm2 exchange, and address IP packets in VDLm2. | ED-92D (MOPS)
| Distributed Radio Architecture | STD | *GAP* | New M07 | AEEC | SAI | Focus is mainly hardware, but there may be impact on the overall architecture and interfaces with respect to IPS (e.g., radios on a network) | ARINC TBD |  | Apr-2020 | APIM 18-003
Naming and Addressing | Naming | STD | In-Progress |  | ICAO | PT-I | Define naming convention and DNS requirements | Doc. 9896 | Coordination with RTCA SC-223 | Nov-2020 | Job Card: CP-DCIWG.006.01
| Addressing | STD | In-Progress |  | ICAO | PT-I | Define addressing | Doc. 9896 | Coordination with RTCA SC-223 | Nov-2020 | Job Card: CP-DCIWG.006.01
| IPv6 Transition Ph1 | ANA | In-Progress |  | AEEC | NIS | Roadmap for IPv6 transition in aviation | ARINC 686 |  | Oct-2019 | APIM 17-001
| IPv6 Transition Ph2 | STD | Proposed |  | AEEC | NIS | Updates to standards for IPv6 transition as identified during the roadmap activity | ARINC 664pX(other parts and/or new part) |  |  | APIM 17-001 (proposed Phase 2)
| Administration | OPR | *GAP* | 5.4.4 | ICAO | PT-I (?) | Processes for on-going administration of IP names and addresses IP database management/translations
|  | OPR | *GAP* | 5.4.5 | OTHER | IATA | Same as above but for AOC
Security | Risk Analysis | ANA | In-Progress |  | ICAO | PT-I | Notional end-to-end risk analysis for IPS | Working Papers |  | Dec-2018
|  | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | Use the results of the ICAO risk analysis to identify other requirements (e.g., regional constraints) on IPS as part of MASPS | ED-TBD DO-TBD | ICAO PT-I Risk Analysis | Dec-2019
| Architecture | GM | Planned |  | ICAO | PT-I & Sec. Panel |  | Doc. 9896 | Doc. 10044 | Nov-2020 | Job Card: CP-DCIWG.007.01
| End-to-End - Dialogue Service | STD | Complete |  | ICAO | PT-I / SSG | Secure Dialog Service (SDS), end-to-end Dialogue Service application-layer security applicable to both OSI and IPS | Doc. 10094, Part I |  | Complete | Complete without validation; complete with validation by Dec-2019
|  | GM | In-Progress |  | ICAO | PT-I / SSG | Secure Dialog Service (SDS) Concept of Operations | Doc. 10094, Part II |  | Dec-2018
|  | GM | In-Progress |  | ICAO | PT-I / SSG | Secure Dialog Service (SDS) guidance material | Doc. 10094, Part III |  | Jun-2019
|  | VAL | In-Progress |  | FAA | WJHTC | SDS validation | Validation Report |  | Dec-2019
| Security Framework | GM | In-Progress |  | ICAO | PT-I / SSG | Overall security framework | Doc. 10090 |  | Dec-2020
| Ground-Ground | STD | In-Progress |  | ICAO | PT-I / SSG | Ground-ground IPS security | Doc. 9896 |  | Dec-2020
| PKI | STD | Complete |  | ICAO | PT-S | AeroMACS PKI Certificate Policy, which includes certificate/CRL profiles. Expected to be reusable for SDS. | Doc. 10044 | ATA Spec 42 WMF Certificate Profile & Certificate Policy | Complete
2018-06-21 C: VAL; 2018-06-21 D: Complete; 2018-06-21 F: WMF; 2018-06-21 G: AWG; 2018-06-21 H: AeroMACS test certificates |  | Complete
|  | STD | Planned | 5.4.4 | ICAO | PT-I / SSG | PKI Policy for Aeronautical Communications | Doc. 10095 |  | Dec-2019
|  | VAL | Planned | 5.4.4 | ICAO | PT-I / SSG | Public Key Infrastructure Validation | Doc. 10095 |  | Sep-2020
|  | STD | In-Progress |  | ICAO | SecP / iNNOVA | Security requirements for air-ground | Doc. TBD |  | TBD
|  | GM | *GAP* | 5.4.1.2.8 | AEEC | TBD | Key loading and key management necessary for LRU installation and maintenance (e.g., key replacement) -- updates necessary for IPS (all systems) | ARINC TBD |  |  | Requires future APIM
| Network Layer Security | STD | In-Progress |  | ICAO | PT-I | Definition of the security solution for the network level, including for AOC traffic (VPN) | Doc. 9896 | RTCA SC-223 / EUROCAE 108 Profile Activity
| Aircraft Security Reliance on Ground Security | GM | In-Progress |  | EUROCAE + RTCA | WG-72 / SC-216 | Airworthiness Security Methods and Considerations - Trustworthiness considerations in the security environment | ED-203A DO-356A |  | Sep-2018
|  | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | IPS End-to-End guidance supporting certification (MASPS) | ED-TBD DO-TBD | ICAO WG-I AEEC IPS | Dec-2019
|  | GM | *GAP* | 5.2 ? | OTHER | ARAC (?) | Address this topic and provide recommendations to FAA/EASA
|  | GM | *GAP* | 5.2 | FAA |  | FAA/EASA regulation update or new process?? Impact on certification if aircraft has reliance on the ground
|  | GM | *GAP* | 5.2 ? | EASA |  | FAA/EASA regulation update or new process?? Impact on certification if aircraft has reliance on the ground
| Security Management | STD | *GAP* | 5.4.2 | OTHER | TBC | Overall security processes regarding incident management, logging/analysis, Aviation ISAC, etc.
| Security Policy | STD | Planned |  | ICAO | PT-I / SSG | ICAO Overall Security Policy Requirements | Doc. TBD |  | TBD | Job Card: CP-DCIWG.007.01
Performance | QoS | STD | Planned |  | ICAO | PT-I / MSG | Map ATN QoS to IPS DIFFSERV (should be defined as an end-to-end mechanism) | Doc. 9896 | Doc. 9880 Doc. 10044 | Nov-2020
|  | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Detailed QoS mechanisms for segregating ATS and AOC traffic (part of ATN/IPS router form factor / architecture??) | ARINC 858
| Compression | STD | In-Progress |  | ICAO | PT-I | ATNPKT update to include compression provisions | Doc. 9896
|  | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Standardization of proposed compression techniques | ARINC 858
| RCP (B2) | STD | Complete |  | EUROCAE + RTCA | WG-78 / SC-214 | SPR | ED-228A / DO-350A ED-122 / DO-306 |  | Mar-2016 Oct-2007
| RCP (Beyond B2) | STD | *GAP* | NEW M06 | ICAO | ODLWG | RCP/RSP updates for beyond B2 | Doc. 9869
|  | STD | *GAP* | 5.4.3 | EUROCAE | WG-78 | SPR update for beyond-B2 services
|  | STD | *GAP* | 5.4.3 | RTCA | SC-214 | SPR update for beyond-B2 services
| Multi-link | STD | Planned |  | ICAO | PT-I / MSG | Multi-link technical provisions | Doc. 9896 | SESAR PJ14.2.4 RTCA SC-223 / EUROCAE 108 Profile Activity | Nov-2020
|  | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Detailed definition of multi-link based on ICAO definition. | ARINC 858 | SESAR PJ14.2.4 Doc. 9896 RTCA SC-223 / EUROCAE 108 Profile Activity |  | The CMU standard would need to refer to the IPS router standard for the specification of the multilink functional specification, I.e., the CMU is one instance of an IPS router.
| MASPS | GM | Planned |  | EUROCAE + RTCA | WG-108 / SC-223 | IPS End-to-End guidance supporting certification (MASPS) | ED-TBD DO-TBD | ICAO WG-I AEEC IPS | Dec-2019
Form / Fit / Interfaces | CMU | STD | *GAP* | 5.4.1.2.2 | AEEC | DLK | CMU specification updates to support IPS (e.g., including segregation, new interfaces, data logging, traffic shaping/filtering, etc.) | ARINC 758 |  |  | Although A758 is open, the current APIM 17-003 addresses Ethernet interface but does not include IPS; a future APIM will be necessary
| IPS Router | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Specification for an IPS-specific router or router function (e.g., including segregation, new interfaces, etc.) | ARINC 858 |  |  | AEEC IPS should review A758 document as a reference for structure and content for current CMF
Ground Systems | OSI/IPS and ACARS/IPS Gateway | GM | In-Progress | 5.4.4 | ICAO | PT-I | Technical definition of what needs to maintained between OSI and IPS in order to maintain application correlation. (Ground requirements RTCA/EUROCAE involvement?) | TBD
|  | STD | In-Progress | 5.4.1.1 | AEEC | IPS | Definition of ACARS-IPS gateway function | ARINC 858
|  | STD | Planned | 5.4.4 | EUROCAE + RTCA | WG-108 / SC-223 | Ground system considerations for IPS end-to-end interoperability and performance as part of MASPS | ED-TBD DO-TBD |  | Dec-2019
| IPS NW Topology | ANA | Planned |  | ICAO | PT-I | Discuss network topologies and proposals (e.g., DSP-centric solution) | Working papers
|  | GM | *GAP* | 5.4.5 | OTHER | Regional CAAs | Regional implementation of IPS based on the ICAO standard

## List Items
Drop down menu items (heavy outline indicates current list size)
Applies to | List Name | Item | Item Description
Work Type | WIPtype | STD | Standard / Specification
|  | GM | Guidance Material
|  | ANA | Analysis
|  | PRO | Prototype Implementation
|  | VAL | Validation
|  | VER | Verification
|  | V&V | Verification and Validation
|  | OPR | Operations
TBD
TBD
Work Status | Status | Complete
In-Progress
Planned
Proposed
*GAP*
*TBD/TBS*
Organization | Org | AEEC | AEEC
|  | EUROCAE | EUROCAE
|  | EUROCAE + RTCA | EUROCAE&RTCA (joint)
|  | ECTL | Eurocontrol
|  | FAA | FAA
|  | ICAO | ICAO
|  | INDUSTRY | Industry - insert OEM/supplier company name(s) in WG/SG field
|  | OTHER | Other
|  | RTCA | RTCA
|  | EASA | EASA
|  | WMF | WiMAX Forum