## PP858
AEEC IPS PP858 -- RAIL
Item # | Open Closed Deferred | Topic | Section | Action | Assigned Date | Assigned To | Due Date | Revised Due Date | Closed Date | Status/Comments
1 | Closed | E2E Architecture | 2.1.2 | Add security implications and pointer to Section 4 | 2019-06-26 | M.Olive - HON | 369127 |  | 2019-07-29
2 | Open | Security Layers | 2.3.2 | Align bullets headings with terminology in Section 4, possibly covering both dimenstions (data, control) | 2019-06-26 | M.Olive - HON | 369127
3 | Open | IPS Functional Overview / IPS Architecture | 3.1.2 / 3.1.3 | Revisit host vs router based on implementation discussions in Section 6. | 2019-01-29 | TBD | 369127
4 | Closed | Transport Security | 3.3.1.4 | Transport layer security text | 2019-07-25 | J.Graefe - Collins-IMS | 369127 |  | 369127
5 | Open | IPv6 Layer | 3.3.2 | Update Figure 3-5 to shown IPv6 packet w/ DTLS | 2019-06-27 | J.Graefe - Collins-IMS | 369127
6 | Open | IPv6 Header | 3.3.2.1 | Re-review section; remove figure; add pointer to IPS Profiles | 2019-07-25 | J.Graefe - Collins-IMS | 369127
7 | Open | Aircraft Addressing | 3.3.2.3.1 | Review / propose text to resolve comments | 2019-07-25 | M.Skorepa - HON | 369127
8 | Closed | Packet Filter Firewall | 3.3.3 | Coordinate with Laurent regarding whether some text should be moved to Section 4 | 2019-07-25 | M.Olive - HON | 369127 |  | 2019-08-13 | 7/29: E-mail sent 8/2: Timo suggestion 8/13: Laurent suggestion
9 | Open | Address Acquisition | 3.3.4.1 | Re-write this section to reflect acquisition of the subnetwork CoA address (using terminology in IPS Profiles) | 2019-07-25 | J.Graefe - Collins-IMS | 369127
10 | Closed | ICMPv6 | 3.3.4.2.1 | Add reference to IPS Profiles | 2019-07-25 | M.Olive - HON | 369127 |  | 2019-07-29
11 | Open | Mobility & Multilink Signaling | 3.3.4.4.1 | Re-write based on results of WG-I MSG discussions. Emphasis on the impact on the airborne solution and common A-G interface (RS/RA), regardless of the ground-based mobility solution. à Discussion concluded that it may still be premature to do significant edits on this section until A-G interface is decided in ICAO. | 2019-07-25 | M.Skorepa - HON | 369127
12 | Open | Routing Decision Engine | 3.3.5 | Add content to describe interactions between RDE and Mobility/Multilink Signaling function. | 2019-07-25 | M.Skorepa - HON | 369127
13 | Closed | Routing Decision Engine | 3.3.5 | Clarify text regarding multiple links simultaneously but not same message over simultaneous links | 2019-07-25 | M.Olive - HON | 369127 |  | 2019-07-29
14 | Closed | QoS | 3.3.6 | Review initial bullets to ascertain whether current text is sufficient OR whether additional text is necessary to address bulleted thoughts. | 2019-07-25 | T.Bauge - Thales | 369127 |  | 2019-08-16 | 8/16: Update provided, review in progress
15 | Open | Datalink Adaptation: Inmarsat, Iridium, AeroMACS | 3.4.1 3.4.2 3.4.3 | Propose text for these sections. (Madhu has some thoughts and materials) | 2019-07-25 | M.Niraula - Collins | 369127
16 | Open | Non-Core Functions | 3.5.x | Coordinate with Greg to resolve comments | 2019-07-25 | M.Olive - HON | 369127
17 | Open | Core IPS Interfaces | 3.6.x | Coordinate with Luc to address bullets | 2019-07-25 | M.Olive - HON | 369127
18 | Open | Ground Architecture | Appendix A | Implement M10 recommendations | 2019-06-27 | R.Dlouhy - Collins-IMS M.Olive - HON | 369127
19 | Open | AICF | Attachment 3 | Integrate AirTel suggestions | 2019-07-23 | M.Olive - HON | 2019-08-30 |  |  | 8/15: Sent to Ron/Fryd for review
20 | Closed | RFC References | All | Remove specific RFC references and point to RTCA/EUROCAE IPS Profiles, where RFCs applicable to IPS are referenced. | 2019-08-26 | M.Olive - HON | 2019-08-26 |  | 2019-08-26
Deleted
Deferred
Closed
Open