## A858P1_s1
AEEC IPS A858P1 Supplement1 -- RAIL
# | Item # | Open Closed Deferred | Topic | Section | Action | Assigned Date | Assigned To | Due Date | Revised Due Date | Dependency | Closed Date | Source | Status/Comments (Follow-up Action)
1 | P1-S01-01 | Open | Document References | 1.4 (figure) 1.4.2 | Update references for ICAO and RTCA/EURCAE documents that are in draft status. | 2021-01-21 | M.Olive - HON | 3Q2022 |  | ICAO RTCA/EUROCAE |  | PP858 | 14-Nov: Expect by Feb meeting Editorial
2 | P1-S01-02 | Closed | Naming | 3.3.2.x | For naming, address aircraft-side response to non-nominal conditions (e.g., name resolution failure) | 2021-01-21 | M.Niraula - COL | 2021-09-14 | 2022-02-22 | ICAO WG-I |  | Gap Analysis | M22: Supp1 material reviewed; action closed. Feb-22: Move material to Supp1 for Apr meeting discussion M21: Merge with Greg's text and put in 3.5.1.5 M19: Continue to update. a) Removed ACK, update the sequence without ACK b) State clearly that ground shall respond to each request individually even if multiple request is received for same name c) Trsp time should be determined based on the current operation to be long enough to avoid crossing scenario that eliminate the unnecessary re-transmission d) Provide input to MASPS for the timing, performance and safety requirements e) Provide updated paper to the DOC 9896 update M18: Initial discussion. Next step to document use cases and then consider options for name syntax and name resolution.
3 | P1-S01-03 | Open | IPv6 Addresses | 3.3.2.2 3.3.2.2.x | Keep in sync with ICAO decisions | 2021-01-21 | Group | A/R |  | ICAO WG-I and WG-I MSG |  | PP858
4 | P1-S01-04 | Closed | Link Local Addresses | 3.3.2.2.2 | Keep in sync with ICAO decisions | 2021-01-21 | Group | A/R |  | ICAO WG-I and WG-I MSG | 2022-09-26 | PP858 | M16 – Madhu has text for this section Nov-15 - The highlighted text is an acceptable proposal. Similarly, static configurations, SLAAC and EUI-64, etc. are all acceptable alternatives. I suggest that for a/g interface we either use SLAAC (RFC 4862) with RFC 4941 or the AERO RFC (highlighted text here). For on-board side of the interface we use the standard Profiles or leave it to the airframers or the new APIM that is being worked by AEEC. M14 – Already changed in most recent version of IETF doc, which proposes an update to Section 2.5.6 of RFC4291. Need to re-sync this text once ICAO mobility discussions stabilize. Pre-M13 – Text adopted from draft-templin-atn-aero-interface-21.pdf (https://datatracker.ietf.org/doc/draft-templin-atn-aero-interface/)
5 | P1-S01-05 | Closed | Functional Requirements | 3.3.x 3.4.x | Address Airborne IPS System-specific implications (e.g., interfaces, performance, handling non-nominal conditions, implementation, etc.). Include linkages to the other documents and how to navigate to get the needed info. | 2021-01-21 | S.Pelleschi - COL (wrt MASPS) | 2021-09-14 | 2022-09-26 | RTCA/EUROCAE IPS MASPS | 2022-09-26 | Formerly M12-04 / -05 plus Gap Analysis | 31-Aug: Reviewed material and proposal to create new Section 3.9. Agreed to include in Supp1 material for Sep meeting. 27-Jul: Reviewed updated material; Stephane and Mike to coordinate on material placement in A858P1 and propose to the group. M22: Reviewed proposed text and discussed options. Continue refining for next meeting. Mar-22: Currently integrating comments; preliminary text for April meeting Feb-22: Reviewed proposed material. Continue to work. NOTE - See material attached below from IPS Profiles. M21: Continue to address cases per notes taken. M20: Reviewed revised approach to focus on common behaviors for non-nominal conditions that are not covered by protocol definitions. Continue to populate the non-nominal cases for 858; consider including these behaviors in the Health Mgmt. section. M19: Suggestion to have organizations doing validation identify the non-nominal cases based on lessons-learned. Then present to larger group during a future telecon/meeting. M18: Plan to look at each sub-section and identify non-nominal case handling and further guidance for implementors.
6 | P1-M17-06 | Closed | Header Compression | 3.3.4.3 | Harmonize header compression with SC-223/WG-108 (as necessary) | 2021-03-18 | J. Graefe - COL-IMS (wrt Profiles) | 2021-09-14 | 2022-12-05 | RTCA/EUROCAE IPS Profiles |  | Gap Analysis | M24: COL and HON to conduct offline telecon regarding options. M23, May-27: Reviewed current status. Revisit A858 text for next meeting, including whether to add a statement that ROHC use may be based on the subnetwork being used. Possibly add to the Configuration Setting section (implementation-specific?) M22: Revisit whether to add a statement that ROHC use may be based on the subnetwork being used. Possibly add to the Configuration Setting section. Mar-22: Reviewed material presented to 223/108, working a few outstanding issues; report status at next meeting M20: Reviewed results of COL testing. Continue to review and decide what (if anything) needs to change in 858 M19: Still under discussion. Open technical and non-technical (complexity, certification) issues. To be discussed further during SC-223/WG-108 meeting - report status at next telecon. M18: Still under discussion. Update planned for next meeting.
7 | P1-S01-06 | Closed | QoS | 3.3.5 | Update QoS consistent with decisions in Doc. 9896 | 2021-01-21 | G.Saccone - Boeing (wrt 9896 updates) | 2021-09-14 | 2022-03-22 | ICAO WG-I | 2022-03-22 | Gap Analysis | Mar-22: Text is generic enough as-is and points the reader to 9896 for details. Greg (as 9896 editor) will continue to monitor for any changes.
8 | P1-S01-07 | Closed | Mobility and Multilink | 3.3.6.x | Update multi-link consistent with A-G mobility concept and interface definition in Doc. 9896 (e.g., air-ground signaling and signaling to onboard radios) | 2021-01-21 | M. Skorepa - HON | 2021-09-14 | 2022-09-26 | ICAO WG-I and WG-I MSG | 2022-09-26 | Gap Analysis | M21: Continue to track WG-I multilink; expect progress by June.
9 | P1-S01-08 | Closed | Mobility and Multilink | 3.3.6.2 (Commentary) | Resolve "Commentary" related to A-G signaling interface specification in Doc. 9896 | 2021-01-21 | M. Skorepa - HON | 2021-09-14 | 2022-01-25 | ICAO WG-I and WG-I MSG | 2022-01-26 | PP858 | M22: Supp1 material reviewed; action closed. M21: Move material to Supp1 for next meeting discussion
10 | P1-S01-09 | Closed | Radio Interfaces | 3.3.6 3.5.3 5.3.2 | Updates to 858, as necessary, if there are changes to radio specs to accommodate IPS multi-link. Revisit the specific parameters (e.g., real-time link quality to enhance the performance of multilink operations) and the impact on other radio specs. | 2021-01-21 | S.Pelleschi - COL M. Skorepa - HON (P3) | 2021-09-14 | 2022-12-05 | ICAO WG-I |  | Gap Analysis | M24: Revisit section introducing IPS-enabled radios (e.g., SATCOM is being updated for IPS by AGCS) M23: From ARINC perspective (APIMS), nothing on the horizon, so recommend suspending or closing action. (Plan to close at M24.). M22: Feedback from DLK group on CIRI proposal.
11 | P1-S01-10 | Closed | Address Configuration | 3.5.1.4 | Additional guidance regarding destination address configuration and storage | 2021-01-21 | G.Saccone - Boeing | 2021-07-31 | 2021-12-07 |  |  | Gap Analysis | M21: Supp1 material reviewed; action closed. M20: Move material to Supp1 for Jan meeting discussion M19: Proposed text reviewed. Further consideration of partitions and certification implications.
12 | P1-S01-11 | Open | Security (General) | 4.x | Airborne IPS System security requirements traced to high-level provisions in Doc. 9896 | 2021-01-21 | G.Saccone - Boeing (wrt 9896 updates) | 2021-09-14 | 2023-02-28 | ICAO WG-I and WG-I SSG |  | Formerly M12-08 plus Gap Analysis | 14-Nov: Greg and Mike to re-review before Feb meeting M19: Trace matrix reviewed. Maintain in sync with Doc. 9896, and add trace to Doc. 10095, when available. M18: Initial trace. Greg/Mike to take next step and create a trace matrix that compares in both directions.
13 | P1-S01-12 | Supp1 | Security Architecture | 4.2 | Once Doc. 10145 is available, additional security requirement detail and/or cross-references will be included in a future supplement to ARINC 858 | 2021-01-21 | T.Warns - Airbus | 2021-09-14 | 2023-02-28 | ICAO WG-I and WG-I SSG |  | PP858 | M25: Since 858 will be published before 10145, recommendation to leave the comment for now. Current draft of 10145 is not recommending additional security requirements, so risk is low at this point. M24, M23, Mar-22: Continue to monitor ICAO documents M25: Since 858 will be published before 10145, recommendation to leave the comment for now. Current draft of 10145 is not recommending additional security requirements, so risk is low at this point.
14 | P1-S01-13 | Closed | Numbers of Sessions | 4.3.1.2 | Security dimensioning (i.e., how many simultaneous DTLS sessions does the avionics need to support); per ongoing discussions in WG-I SSG. Revisit commentary and reference to planned guidance in ICAO Doc. 9896 | 2021-01-21 | M.Olive - HON | 2021-09-14 | 2022-02-22 | ICAO WG-I and WG-I SSG RTCA/EUROCAE IPS MASPS |  | Gap Analysis | M22: Supp1 material reviewed; action closed. Feb-22: Move material to Supp1 for Apr meeting discussion M21: Presented relationship with number of ports, which is being addressed in ICAO. Timo recommended specifying a rule for number of sessions based on ports, but without having to know the precise number of ports. Develop text for next meeting. M20: Material reviewed. Coord with 223/108; determine number for 858 M18: Initial review of problem.
15 | P1-M17-01 | Closed | Filtering | 4.3.2.1.x | Revisit firewalling for ingress / egress | 2021-03-17 | T.Warns - Airbus | 2021-07-31 | 2021-12-07 |  |  | PP858 (M17) | M21: Supp1 material reviewed; action closed. M20: Move material to Supp1 for Jan meeting discussion M19: Proposed text for ingress/egress. Consider egress for Native IP apps only (i.e., not B1/B2, ACARS-based apps); add example of egress security policy. Continue to a) sync with ICAO/RTCA/EUROCAE discussions on stateful vs. stateless; b) add additional filtering criteria (e.g., ROHC?); c) check relevance of new RFC 9099 (Operational Security Considerations for IPv6) M18: Initial review of problem.
16 | P1-S01-14 | Closed | Key Management (General) | 4.4.1 | Once ICAO Doc. 10095 is available, additional key management detail and/or cross-references will be included in a future supplement to ARINC 858. | 2021-01-21 | T.Warns - Airbus | 2021-09-14 | 2022-06-27 | ICAO WG-I and WG-I SSG | 2022-06-28 | PP858 | M23: Supp1 material reviewed; action closed. Mar-22: Reviewed presentations to ICAO and 223/108. Propose changes to 858 for next meeting. M21: Discuss during Mar telecon; ICAO considering EST/TCP vs EST/COAP M20: Keep on the agenda for Jan meeting; revisit EST M19: Proposed text capturing key management life cycle and EST protocol reviewed and discussed, including partitioning of material between 858 and Doc. 9896 and issues with EST (e.g., uses HTTPS/TCP and not UDP). Keep on agenda - identify first how much material will be in Doc. 9896.
17 | P1-S01-15 | Closed | Trust Anchor | 4.4.1.1.4 | Revisit ATA Spec 42 reference with respect to ICAO DOC 10095 guidance. | 2021-01-21 | L.Leonardon - COL (coord w/ Timo - Airbus & Daniel/Brandon - Boeing) | 2021-09-14 | 2022-09-26 | ICAO WG-I and WG-I SSG | 2022-09-27 | Formerly M14-18 | M23: Proposal to reference 10095 (with the expectation that 10095 would reference Spec42 if appropriate)
18 | P1-S01-16 | Closed | Cert Revocation Check | 4.4.1.1.5 | Revisit text with respect to use of short-lived ground certificates as specified in ICAO Doc. 10095 | 2021-01-21 | M.Niraula - COL (coord w/ Timo - Airbus and Daniel -- Boeing) | 2021-09-14 | 2022-04-26 | ICAO WG-I and WG-I SSG |  | PP858 | M22: Supp1 material reviewed; action closed. 11-Mar: Timo recommends deleting the text associated with the action item.
19 | P1-M17-02 | Supp1 | Cert Revocation Check | 4.4.1.1.5 | Need to add the details for provision and mechanism to support cert validation related to CRL. Propose some of this requirement to be moved to DOC 9896 and MASPS and develop the needed box level detail in Supplement 1 of PP858. | 2021-03-17 | Rob Segers - FAA | 2021-09-14 | 2022-12-05 | ICAO WG-I and WG-I SSG |  | PP858 (M17) | M24: Pivot to trusted OCSP Responder. Rob Segers is working revised text. M23: Timo presented background and suggested way forward. Re-review during next meeting.
20 | P1-M17-03 | Closed | Cert Revocation Check | 4.4.1.1.5 | Define what happens if OSCP does not work within time. Fail-Safe or Fail-Secure -> meaning still use the last valid public-key (certificate) for ongoing traffic or stop communication | 2021-03-17 | L.Leonardon - COL (coord w/ Timo - Airbus & Daniel/Brandon - Boeing) | 2021-09-14 | 2022-09-26 | RTCA/EUROCAE IPS MASPS | 2022-09-27 | PP858 (M17) | M23: Timo presented background and suggested way forward. Do not include SCVP (not yet a standard) and revisit need for OCSP (based on COL request).. May-27: Propose removing OCSP stapling, and add SCVP stapling once further defined in ICAO -- see also P1-M17-03. Mar-22: Revise text to address use of short-lived ground certs and no CRLs on aircraft. Use of SCVP still being discussed. | Rob Segers: IETF TSL Group has accepted proposal to work on SCVP and move from draft to standards track. Plan to discuss timing wrt to IPS Standards during AEEC and ICAO meetings in Sept.
21 | P1-S01-17 | Supp1 | Certificate Validation | 4.4.1.1.6 | Refine certificate validation with respect to Doc. 10095 | 2021-01-21 | Rob Segers - FAA | 2021-09-14 | 2022-12-05 | ICAO WG-I and WG-I SSG |  | Gap Analysis | M24: Pivot to trusted OCSP Responder. Rob Segers is working revised text. M23: Keep bullet list and continue to monitor 10095
22 | P1-S01-18 | Deleted | Aircraft Security Reliance on Ground | 4.5.x | Additional security implementation guidance with respect to aircraft security reliance on ground security | 2021-01-21 | (See comment) | A/R |  | RTCA/EUROCAE IPS MASPS |  | Gap Analysis | M21 : Decision to move to MASPS M19: May be a topic more appropriate for MASPS, and add pointer in 858
23 | P1-S01-19 | Closed | Airborne IPS System Security Policy | 4.5.x | Additional guidance regarding security policy with respect to implementation, maintenance, and operation of the Airborne IPS System. | 2021-01-21 | S.Pelleschi - COL | A/R | 2022-09-26 | RTCA/EUROCAE IPS MASPS | 2022-09-27 | Gap Analysis | M22: Reviewed proposed text. Agreed to add MASPS pointer in 4.5.1 and update new text as necessary in 4.5.3. M21: Both 858 (box level) and MASPS M19: May be a topic more appropriate for MASPS, and add pointer in 859
24 | P1-S01-20 | Closed | Dataloading | 4.5.2 | Further guidance on FLS from a security perspective (e.g. security-relevant parts should be field loadable to allow patching) -- if existing text is insufficient | 2021-01-21 | G.Saccone, Daniel - Boeing | 2021-07-31 | 2021-12-07 |  |  | Gap Analysis | M21: Supp1 material reviewed; action closed. M20: Move material to Supp1 for Jan meeting discussion Consider adding similar text to cover functions other than security M19: Continue to update - Greg and Timo to coordinate offline and consider the "patching agility" aspects. Also consider where reference to DO-178 should be added.
25 | P1-S01-21 | Deleted | A-G Access Network Guidance | 5.x | Update Section 5 to include statements regarding preferred deployment options for air-ground access networks (e.g., similar technology shared among multiple providers) | 2021-01-21 | (See comment) | TBD |  |  |  | Gap Analysis | M21 : Decision to move to MASPS
26 | P1-M17-04 | Closed | Implementation Examples | 5.2 | Figures assume that all communication between the AICF and legacy application has to be managed via "External Comm Manager", this give just one implementation depiction. It is quite possible to route message from AICF directly to legacy applications or peripherals without going through the external manager. | 2021-03-17 | M.Olive - HON (figures) (coord. with Madhu/Stephane - COL) | 2021-07-31 | 2021-12-07 |  |  | PP858 (M17) | M21: Supp1 material reviewed; action closed. M20: Move material to Supp1 for Jan meeting discussion. M19: Reviewed proposed alternatives, added additional option 2b; agreement on proposed disposition. Next step is to create white paper for Section 5.4 to capture/describe alternatives.
27 | P1-S01-22 | Deleted | Radio Management I/F | 5.3.2.2 | Revisit the specific parameters (e.g., real-time link quality to enhance the performance of multilink operations) and the impact on other radio specs | 2021-01-21 | (See comment) | Deleted |  | ICAO WG-I and WG-I MSG (?) |  | PP858 | 13-APR: Consolidated with P1-S01-09, which is similar
28 | P1-M17-07 | Closed | Interfaces | 5.5 5.3.2.3 | Consider guidance on interfaces other than 429 and Eth (e.g., fiber, other OEM-specific) | 2021-03-18 | M.Olive - HON | 2021-09-14 | 2021-01-27 |  |  | Gap Analysis | 13-APR: Add note that other options are possible but likely OEM-driven and implementation-specific
29 | P1-S01-23 | Closed | Airborne Applications | 6.x | Common notional interface for Native IP applications | 2021-01-21 | G.Saccone - Boeing | 2022-06-27 | 2022-09-26 |  | 2022-09-26 | Gap Analysis | M23: Proposed text based on similar text in Doc. 9896
30 | P1-S01-24 | Closed | Security Event Log | Att4 | Revisit security log format based on feedback from Airbus regarding preferred use of Structured Data (SD) element rather than Message (MSG) element | 2021-02-23 | T.Warns - Airbus | 2021-09-14 | 2022-03-22 |  |  | Airbus e-mail | M22: Supp1 material reviewed; action closed. Mar-22: Move material to Supp1 for April meeting discussion Feb-22: Circulate formatted text for review by AEEC IPS M21: Decision to replace existing approach with SD approach; existing text shown as redline to alert readers. M20: Re-reviewed material, good support. Need input from Madhu and other IPS participants. M19: Initial proposal to use SD. If current approach is maintained, need to expand delimiter escaping. Continue to discuss at next meeting.
31 | P1-M17-05 | Deleted | Common Radio I/F | AttX (Part 3) | 1. Define a common control-plane format and protocol for all airborne radios 2. Provide a comparison between proposed features and what is provided by current airborne radios. | 18-Mar-201 | M.Skorepa - HON | 2021-09-14 | 2022-05-27 |  |  | M17 - Michal's Proposal | Moved to P3-M17-05 --> see tab "PP858P3"
32 | P1-S01-25 | Closed | D-ACK ATNPKT Format | AppxA, A-4 (Bullet 5) | Revisit whether to include high-watermark behavior in sequence number description, with respect to Doc. 9896 amendment proposal: "which acknowledges all messages received up to but not including that number (i.e., 3 indicates that messages 0, 1, and 2 have been received successfully)" | 2021-01-21 | M.Olive - HON | 2021-07-31 | 2022-03-22 | ICAO WG-I |  | Formerly M13-03 | M22: Supp1 material reviewed; action closed. Mar-22: Move material to Supp1 for April meeting discussion; keep open comments re: SC214/WG78 coordination. M21: Additional updates to address comments, and track WG-I on Selective ACK M20: Deferred to M21 18-JUN (Fryd): The wording “acknowledges all received ATNPKTs up to, but excluding N(R)” is correct, regardless of whether HWM is used or not, but if HWM is not used, it would be much clearer to say: “acknowledges last received ATNPKT”. 17-JUN (Ron): Keep the wording unchanged for the next expected to be received, since that is the definition of the field. Add a note that the N (R) effectively acknowledges all unacknowledged messages up to but not including that number. Change the note that for D-ACK, the N(S) part of the sequence number is optionally used for selective acknowledgement or is set to 0 if not used (assuming the selective ack is accepted - I remember there was some concern about the complexity of it at the last meeting).
33 | P1-M18-01 | Closed | Radio Terminology | Figure 3-1 (and similar) | Finalize name for FCI (non-legacy) radios | 2021-06-21 | M-Olive - HON | 2021-07-31 |  |  | 2021-09-14 |  | M19: Agreed on "IPS-enabled" noting that this is not a perfect word, but the best option of the words considered. Definition refined. M18: General agreement to change IP-enabled to IPS-XXX, where there are several options for XXX - to be discussed at next telecon.
34 | P1-M18-02 | Closed | Datalink Adaptation - Non-IP Radios | Figure 3-11 | During joint DLK discussion, suggestion to add security (DTLS) to protocol figure OR a note that security is not shown for simplicity. | 2021-06-22 | M-Olive - HON | 2021-09-14 |  |  | 2021-09-14 |  | M19: To minimize changes to the figure, agreed to change UDP to "UDP + DTLS" and change TCP to "TCP + TLS". (Suggestion to stretch UDP+DTLS halfway thru Native IP apps)
35 | P1-E01-01 | Closed | Document References | All | References to DO-379 and ED-262 (IPS Profiles) appear ~32 times in the document. In anticipation of future revisions to the profile documents, either minimize the number of times the document numbers are referenced or have a statement about using latest version. (Similar discussion in SC-223/WG-108) | 2021-09-28 | M.Olive - HON | 2021-12-07 | 2022-01-25 |  | 2022-01-26 | Industry Editor | M22: Supp1 material reviewed; action closed. M21: Decision to reference the latest version in Section 1.4.2 AND in the text (e.g., DO-379A and ED-262A). AND include a note in Section 1.4.2 to refer to "the latest applicable version" M20: Coordinate with 223/208
36 | P1-M19-01 | Closed | IPS Background | AppxC (new) | Include relevant IPS background material from A658 as a new appendix in 858P1 | 2021-09-28 | L.Emberger - Airbus | 2021-12-07 |  |  |  |  | M21: Supp1 material reviewed; action closed. M20: Move material to Supp1 for Jan meeting discussion.
38 | P1-M21-01 | Closed | Ground IPv6 Address Unavailable | 3.5.1.4 (?) | Consider the use case where the aircraft is not able to resolve a ground IPv6 address -- it may be because the SNL service is not available OR it may be because the ground entity does not support IPS (either directly or via an IPS GW), in which case the Airborne IPS Systems may need to drop back to ACARS (for FANS). | 2022-01-25 | S.Pelleschi - COL | 2022-06-27 | 2022-09-26 | P1-S01-05 | 2022-09-26 |  | M22: Integrate with P1-S01-05 M21: Action derived from non-nominal use case discussion. Initial thoughts at next telecon
39 | P1-M21-02 | Closed | ATNPKT Fields for AICF | Att3, 3.1.3 | Revisit relationship to mandatory/optional parameters in Doc, 9896 Table II-1-6 and clarify any exceptions for AICF. | 2022-01-26 | M.Olive - HON |  | 2022-02-22 |  | 2022-02-22 |  | Feb-22: Modified/clarified Doc.9896 note; no changes to A858. Changes acceptable to COL. M21 - Collins SW developer feedback; need for clarification
40 | P1-M21-03 | Closed | ATN/IPS Background | AppxC, C-4.1.2 | Update LDACS standards timing | 2022-01-26 | M.Olive - HON | 2022-06-27 | 2022-09-26 |  | 2022-09-26 |  | M21:Update mid-year when ICAO work is further along.
41 | P1-M21-04 | Closed | Security Event Log | 4.4.2.x | Address log-level compression, and note that implementer needs to provide guidance on compression in addition to log format. | 2022-02-22 | T.Warns - Airbus | 2022-03-22 | 2022-06-27 |  | 2022-06-28 |  | M23: Supp1 material reviewed; action closed. May-27: Reviewed changes. Re-review during next meeting. M22: Revisit this text with Timo and Tim. Is this really necessary as part of the Airborne IPS System spec, or can this e removed and left to the system implementer. Mar-22: Reviewed text; move to Supp1 for April meeting discussion.
42 | P1-M21-05 | Closed | Security Event Log | 4.4.2.x | Address centralized logging | 2022-03-22 | T.Warns - Airbus | 2022-04-26 | 2022-06-27 |  | 2022-06-28 |  | M23: Supp1 material reviewed; action closed. May-27: Reviewed changes. Re-review during next meeting.
43 | P1-M22-01 | Closed | ATNPKT Diagrams | Appx A | Update ATNPKT diagrams as necessary to reflect changes to the ATNPKT fixed field to accommodate port simplification. | 2022-04-15 | M.Olive - HON | 2022-09-26 | 2022-09-26 | ICAO WG-I | 2022-09-26 |  | Apr-15: Identified during CAO 9896 Editor's meeting
44 | P1-M22-02 | Closed | AICF Ports / ATNPKT | Att3 | Update AICF text/diagrams as necessary to reflect changes to accommodate port simplification. | 2022-04-15 | M.Olive - HON | 2022-09-26 | 2022-09-26 | ICAO WG-I | 2022-09-26 |  | Apr-15: Identified during CAO 9896 Editor's meeting
45 | P1-M22-03 | Closed | Mobility and Multi-link | 3.3.6.2 | Ensure that the text is harmonized with ICAO doc regarding the specific port used for mobility signaling. | 2022-04-26 | M.Skorepa - HON | 2022-09-26 | 2022-09-26 | ICAO WG-I MSG | 2022-09-26
46 | P1-M22-04 | Closed | Security Log Format | 4.4.2.2 | Confirm with Timo whether there is (or should be) any linkage to A852 | 2022-04-26 | T.Warns - Airbus | 2022-06-27 | 2022-06-27 |  | 2022-06-28 |  | M23: Supp1 material reviewed; action closed. May-27: Reviewed history. Agreed that A852 is not applicable, and should state that in commentary. Timo to review text and provide suggested commentary rewording.
47 | P1-M22-05 | Closed | IPS Performance | 3.8 | SC-223/WG-108 and SC-214/WG-78 are investigating how to measure RCTP, where to monitor, and what is required to facilitate the monitoring. Coordinate whether there is something that needs to be specified in Airborne IPS System | 2022-04-27 | S.Pelleschi - COL | 2022-09-26 | 2022-09-26 | RTCA/EUROCAE IPS MASPS | 2022-09-26 |  | M23: To be discussed during joint meeting in Sep (DC)
48 | P1-M22-06 | Closed | IPS-over-AVLC Term | 3.4.2 5.x | Revisit how IPS-over-VDLm2 is referenced to align with the DLK activity. [AR] Consider using IPS-over-VDLm2 rather than IPS-over-AVLC, which is the current term. | 2022-04-27 | L.Emberger - Airbus | 2022-06-27 | 2022-09-26 | AEEC DLK | 2022-09-26 |  | M23: Reviewed changes. Re-review during next meeting. May-27: Reviewed history. Luc to review text and provide suggested terminology based on DLK discussions.
49 | P1-M22-07 | Closed | Radio Interfaces | 3.7.1 5.3.2.1, 5.3.2.2 | Add cross-references to A858 Part 3 (CIRI protocol for radio interfaces) | 2022-05-27 | M. Skorepa - HON | 2022-06-27 | 2022-08-31 |  | 2022-09-26 |  | M23: Reviewed initial proposal. Continue to work in combination with P1-M23-01
50 | P1-M23-01 | Closed | IPS Arch Diagrams | 3.x | Revisit architecture figures/text with regard to IF-3 (and IF-4) and distinguish between legacy and IPS-enabled radios. Are there two types of IPS-enabled radios (i.e., with and without CIRI capability)? | 2022-06-28 | M. Skorepa / M.Olive - HON | 2022-09-26 | 2022-08-31 |  | 2022-09-26
51 | P1-M23-02 | Open | OSI to IPv6 Addresses | 3.3.2.2 | How will ATN/OSI NET addresses (still the format used to manage addresses by the CM application) be translated into ATN/IPS addresses (and when). | 2022-06-29 | F.Wrobel - Airtel | 2022-09-26 | 2023-02-28 | ICAO WG-I |  |  | M24:Discuss with Aloke how to reflect IPv6 address (/16 or ./20) M23: Formerly Luc comment s1 d01-04 #05. Under discussion in WG-I. Reference final approach in 858 (may be in both Parts 1 and 2).
52 | P1-M24-01 | Supp1 | AICF | Att3 | Changes to AICF text/figures driven by the results of action item P2-M23-02 (FlightID, Tail No., or both) | 2022-09-26 | M.Olive - HON | 2022-12-05 | 2023-02-28 | P2-M23-02
53 | P1-M24-02 | Supp1 | ATNPKT Format | Appx A | Changes to ATNPKT format examples driven by the results of action item P2-M23-02 (FlightID, Tail No., or both) | 2022-09-26 | M.Olive - HON | 2022-12-05 | 2023-02-28 | P2-M23-02
54 | P1-M25-01 | Open | AICF | Att3 | Given the port number simplification implemented in Doc. 9896, revisit how secure sessions are initiated and terminated. | 2022-12-10 | T.Warns - Airbus / M.Olive - HON | 2023-02-28 |  | Doc. 9896
55
56
57 |  | Deleted
58 |  | Deferred
59 |  | Closed
60 |  | Supp1
61 |  | Open
Next
P1-E01-02
P1-S01-26
P1-M17-08
P1-M18-03
P1-M19-02
P1-M21-06
P1-M22-08
P1-M23-03
P1-M24-03
P1-M25-02
Related to P1-S01-05 -- Material for A858 being removed from IPS Profiles --> (S.Pelleschi) Alerts are already in 858, and the reqs below are more BITE specific and already covered in other avionics standards and are not specific to IPS

## A858P2_s1
AEEC IPS A858P2 Supplement1 -- RAIL
# | Item # | Open Closed Deferred | Topic | Section | Action | Assigned Date | Assigned To | Due Date | Revised Due Date | Dependency | Closed Date | Source | Status/Comments (Follow-up Action)
1 | P2-M17-01 | Closed | IPS Gateway Security (G-G) | 3.4.4 | Revisit whether there are any G-G security impacts on IPS GW | 2021-03-18 | G. Saccone - Boeing | 2021-09-14 | 2021-12-07 | ICAO WG-I RTCA/EUROCAE (MASPS) | 2022-01-26 | Gap Analysis | M20: Move material to Supp1 for Jan meeting discussion (DONE)
2 | P2-M17-02 | Closed | Message Examples | 4.4, 5.5 | Harmonize "D-ACK subsequent to D-START" with final provisions in Doc. 9896 (applies to both text and figures) | 2021-03-17 | M. Olive - HON | 2021-07-31 |  | ICAO WG-I | 2021-09-16 | PP858P2 | M19: As of 2-Sep Doc. 9896 editing meeting, current 858P2 text/figures are in sync with amendment proposal. Close but continue to monitor for additional changes. 18-JUN (Fryd): Included in official Doc 9896 Ed3 on ICAO Portal: Doc9896_Redline_3rd_Edition_Part_III_en_REFORMAT_10Mar2021.docx, Figure II-1-12 17-JUN (Ron): I am not fully sure if the optional ACK after D-START was accepted, I am sure the ACK after the D-STARTCNF was.
3 | P2-M17-03 | Closed | Proxy Address-General | 5.2.1 | Consider adding a diagram to help convey the concepts in Paragraph 5 | 2021-03-18 | F. Wrobel - Airtel | 2021-07-31 | 2021-12-07 |  | 2022-01-26 | PP858P2 | M20: Move material to Supp1 for Jan meeting discussion M19: Proposed text reviewed. Revisit during next telecon.
4 | P2-M17-04 | Closed | Duplicate Address Detection | 5.2.2 | Need to think about how to best detect (and prevent) erroneous/duplicate address. Putting the conversion on the ground should help to eliminate this problem. (With current OSI deployment, SITA has seen cases where aircraft are configured with the same NSAP addresses (and even the same 24-bit address, particularly when entered manually).) NOTE: This guidance may apply more broadly to all systems. | 2021-03-18 | G. Saccone - Boeing | 2021-11-16 | 2022-04-26 |  |  | PP858P2 | M22: Text reviewed with COL-IMS and SITA and integrated as Section 3.4.5. Mar-22: Reviewed text. Greg to coordinate with SITA for improvements to proposed process. M21: Circulate for review among DSP/CSP M20: Relocate to Section 3.x since duplicate addresses can apply to any type of IPS GW. Update text to reflect address cross-check with associated aircraft certificate. 13-APR: Consider addressing in Part 1 as part of P1-S01-10
5 | P2-M19-01 | Closed | ACARS Address Resolution | 4.1, 4.x | Add guidance/examples for how the IPv6 address is resolved for ACARS Hosts. (Point to high level guidance on name lookup in Doc. 9896, then add any additional ACARS-specific guidance in 858P2.) | 2021-09-16 | G. Saccone - Boeing | 2021-11-16 | 2022-02-22 | P1-S01-02 |  | M19 | M22: Supp1 material reviewed; action closed. 22-Feb: Add pointer to Part 2 once Part 1 section is determined. M21: Consider moving to Part 1 with pointer in Part 2 M20: Move material to Supp1 for Jan meeting discussion. Relocate to Section 3.7 since text applies to any type of IPS GW
6 | P2-M19-02 | Closed | FANS - ACARS MAS | 4.4.1 (4.5.1 in d0-01) | Fig 4-12 (4-13 in d0-01) show the interactions of the IPS Gateway with respect to synthesis of a Message Assurance Success MAS responses to FANS Host when MA TEI Request is contained in an FANS ACARS Host uplink. However what is not described are the MAS-Fail conditions and indications. MAS Fail codes useful to Datacom FANS1/a are split into two main series 2xx and 3xxx. If the CSP knows the uplink requesting MA has been attempted over the RF then a 3xx series code is generated in the MASF, while if no attempt has been made to transmit the uplink on a radio, then a 2xx series MAS code will be returned. Additionally the FANS 1/A for Datacomm uses the new Deliver-By DB TEI for uplinks for Enroute Aircraft. When the DeliverBy time is exceeded, the CSPs will not attempt to transmit this message and will return either a 200 series or 300 series as defined in A620. | 2022-08-09 | R.Dlouhy - COL-IMS | 2022-02-01 | 2022-02-22 |  |  | Pre-M19 | M22: Supp1 material reviewed; action closed. 22-Feb: Move material to Supp1 for Apr meeting discussion Pre-M19: Posted on AEEC IPS Teams chat.
7 | P2-M22-01 | Supp1 | Mapping A620 to AICF | 4.3.1, Figure 4-2 4.3.2, Figure 4-3 | Update Conversion Example figures to reflect changes to the ATNPKT fixed field to accommodate port simplification. (Interdependency with ICAO WG-I.) | 2022-06-01 | M.Olive- HON F.Wrobel - Airtel | 2023-02-28 |  | ICAO WG-I |  |  | 15-Apr: Identified during CAO 9896 Editor's meeting
8 | P2-M23-01 | Closed | Multi-GW Coordination | 5.2.1 | Need additional clarification that among multiple GWs it may be necessary to propagate aircraft address information. | 2022-06-27 | F.Wrobel - Airtel | 2023-02-28 |  |  | 2022-09-28 |  | M24: Additional text added after Figure 5-2, coordinated with Luc. M23: Add clarification possibly below Figure 5-2; also revisit bullets in Section 3.5
9 | P2-M23-02 | Supp1 | ACARS Gateway | 4.x | Consider what additional info (e.g., Tail No.) might be needed for ground correlation and role of the post authentication message, and address what happens when there is a mismatch (e.g., between FlightID and Tail No.) | 2022-07-27 | R.Dlouhy - COL-IMS Zbig/Stephane - SITA G.Saccone - Boeing | 2023-02-28 |  |  |  |  | 14-Nov: COL and SITA converging on FlightID+TailNo. 31-Aug: Reviewed potential options for tail number. COL & SITA discussions in progress. Discuss during Sep meeting. 27-Jul: Based on discussion of SITA (Jocelyn) comments
10 | [7 empty] | 2023-02-28
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36 |  | Deleted
37 |  | Deferred
38 |  | Closed
39 |  | Supp1
40 |  | Open
Next
P2-M17-05
P2-M19-03
P2-M22-02
P2-M23-03
P2-M24-01
P2-M25-01

## PP858P3
AEEC IPS PP858P3 -- RAIL
# | Item # | Open Closed Deferred | Topic | Section | Action | Assigned Date | Assigned To | Due Date | Revised Due Date | Dependency | Closed Date | Source | Status/Comments (Follow-up Action)
1 | P3-M17-05 | Closed | Common IPS Radio I/F | Part 3 (General) | 1. Define a common control-plane format and protocol for all airborne radios 2. Provide a comparison between proposed features and what is provided by current airborne radios. | 18-Mar-201 | M.Skorepa - HON Z.Jaron - HON | 2021-09-14 | 2022-05-27 |  | 2022-05-27 | Formerly P1-M17-05 | M22: Comments by 5/20 for discussion during the May telecon M21: Broadly circulate protocol requirements and proposed interface spec among AEEC SCs. Continue working material --> Decision to make Part 3 in lieu of an attachment. M20: Distribute white paper with additional detail for review during Jan meeting. M19: Reviewed/discussed initial text. Next step is to capture requirements and introductory material, as well as examples. M18: Reviewed proposal. Next step is to start preparing attachment outline/text.
2 | P3-M22-01 | Closed | CIRI Context Diagram | 3.1 Figure 3-1 | Clarify the diagram to indicate that it is an example, or abstract the diagram | 2022-04-27 | M.Skorepa - HON Z.Jaron - HON | 2022-06-27 |  |  | 2022-06-28 |  | M23: Diagram updated in d0-04 and reviewed
3 | P3-M22-02 | Closed | Protocol Operation | 5.1 | Add text about support of data-plane messages with payload of the 1280 bytes (refer to Req. 5 in Appx A) | 2022-04-27 | M.Skorepa - HON Z.Jaron - HON | 2022-06-27 |  |  | 2022-06-28
4 | P3-M22-03 | Closed | Flow Control | 5.5 | We may need an analysis/demonstration that the flow control mechanism as such does not degrade the performance allocated to the aircraft. | 2022-04-27 | M.Skorepa - HON Z.Jaron - HON | 2022-06-27 | 2022-09-26 |  |  |  | A recommendation in the spec, that this needs to be taken care of when implementing. Also, make Flow Control only for non-critical data --> no impact on safety critical data.
5 | P3-M22-04 | Closed | Radio Requirements | A-1 | State somewhere in the document that the radios do not need to implement ALL the features offered by the CIRI protocol (e.g. signaling status for multiple services vs. for a single service). | 2022-04-27 | M.Skorepa - HON Z.Jaron - HON | 2022-06-27 | 2022-09-26 |  |  |  | Section 4.3.1: An Airborne IPS System implementation does not have to support all possible valid CIRI protocol configurations, Section 4.4.1: Implementation do not have to support all possible valid configurations. For example, an Airborne Radio implementation might support only: Statements in section 2 that Dataplane and Flow control are optional.
6 | P3-M22-05 | Closed | Data Plane Requirements | A-1 Table A-2, Req 5 | Revisit the wording of Req. 5 to explain that 1280 is the minimum, not maximum | 2022-04-27 | M.Skorepa - HON Z.Jaron - HON | 2022-06-27 | 2022-09-26 |  |  |  | fixed by Mike: to exchange data-plane packets 1280 bytes or larger
7 | P3-M22-06 | Closed | Data Plane Requirements | A-1 Table A-2, Req 6 | Should Req 6 address a protocol requirement for a minimum number of services? Recommend including a note that currently we are considering Radios that support two services; add similar note Section 5.2. | 2022-04-27 | M.Skorepa - HON Z.Jaron - HON | 2022-06-27 | 2022-09-26
8 | P3-M23-01 | Closed | Options | 3.2 Table 3-3 | Consider making "O [2]" (optional with note) to "C [2]" (conditional with note) | 2022-06-28 | M.Skorepa - HON Z.Jaron - HON | 2022-09-26 |  |  |  |  | fixed by Mike
9 | P3-M23-02 | Closed | Link Instance | 3.3 | An example would be beneficial: -How the link instance ID is used (multilink, AGMI; ref to MDE in Part 1) -How the link instance ID is composed/what it looks like | 2022-06-28 | M.Skorepa - HON Z.Jaron - HON | 2022-12-05 |  |  |  |  | Reference to ICAO 9896, Part I, Section 2,5,11 for Link Instance ID values. Recommend against an example to avoid mismatch with ICAO
10 | P3-M23-03 | Closed | Services | 4.2 | Consider renaming "services" to "channels" and clarify the use of "transport channel" (possible reword as "transport means") | 2022-06-28 | M.Skorepa - HON Z.Jaron - HON | 2022-09-26
11 | P3-M23-04 | Closed | Services | 4.2 | Consider renaming "primary service" as "default service" (note that service may be renamed to channel per P3-M23-03) | 2022-06-28 | M.Skorepa - HON Z.Jaron - HON | 2022-09-26 |  |  |  |  | Preference to maintain "primary channel"
12 | P3-M25-01 | Part3 | Options | 3.3.x | Add new option to convey the payload type (e.g., IPv6 vs. RHOC compressed) contained in the Data Plane payload | 2022-12-06 | Z.Jaron - HON | 2023-01-23 |  |  |  |  | Post-M25: New text in d1-02
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36 |  | Deleted
37 |  | Deferred
38 |  | Closed
39 |  | Part3
40 |  | Open
Next
P3-M22-07
P3-M23-05
P3-M24-01
P3-M25-02

## %Complete
A858
| Part 1 | Part 2 | Part 3
Open | 3 | 0 | 0
Closed | 39 | 7 | 11
Supp1 | 3 | 2 | 1
Deferred | 0 | 0 | 0
Deleted | 4 | 0 | 0
TOTAL | 49 | 9 | 12
% Complete | 93.88% | 100% | 100% | Formula = | 1 - (Open / Total)

## PP858d2-d3 (HISTORY)
AEEC IPS PP858 -- RAIL
NOTE: M12-XX are actions resulting from joint Gap Analysis discussions during Dec-2019 BRU meeting
Item # | Open Closed Deferred | Topic | Section | Action | Assigned Date | Assigned To | Due Date | Revised Due Date | Dependency | Closed Date | Status/Comments
M12-05 | Deferred | IPS Profiles | 3.3.x | Address Airborne IPS System-specific implications. Include linkages to the other documents and how to navigate to get the needed info. | 2019-12-11 | S.Pelleschi - COL / M.Ollve - HON | 2020-06-10 |  | IPS Profiles and MASPS |  | Moved to Supp1 Action Items
M12-03 | Closed | Transport | 3.3.1 | Address Airborne IPS System-specific implications | 2019-12-11 | S. Pelleschi - COL | 2020-06-10 |  |  | 2020-05-28 | E-mail 26-May
M14-01 | Closed | IPv6 Packet | 3.3.2.1 | Reference to MIC |  | M. Olive - HON | TBD |  | ICAO WG-I SSG |  | 1-Sep - Proposed changes based on SSG decision to use standard DTLSv1.3. Waiting for SSG decision
M14-02 | Closed | IPv6 Packet | 3.3.2.1 | IPv6 layer fragmentation -- may change as a result of mobility discussions | 2020-06-23 | M. Olive - HON | TBD |  | ICAO WG-I MSG | 2020-12-07 | Waiting for MSG decision
M13-01 | Closed | IPv6 Addresses | 3.3.2.2, 3.3.2.2.x | Update text to remove detail and point to 9896. PP858 should explain how aircraft systems obtain IPv6 addresses and how fields in the Global address are configured in the aircraft. | 2020-05-19 | A. Roy - HON | 2020-06-10 | 2020-07-24 |  | 2020-07-24 | E-mail 26-May See detailed comments in text
M14-25 | Closed | IPv6 Addresses | 3.3.2.2, 3.3.2.2.x | The definition of the IPv6 addresses is still subject to approval within ICAO. Once approved (expected Oct-2020), this section will be updated accordingly, and material relevant to aircraft configuration will remain in 858. | 2020-07-28 | A. Roy - HON | 2020-11-11 | 2020-12-08 | ICAO WG-I Addressing | 2020-11-17 | 17-Nov: Updated text 28-Oct: Reminder e-mail sent 06-Oct: E-mail action item sent Waiting for WG-I decision
M14-03 | Closed | Packet Filter Firewall | 3.3.3 | Check IPS Profiles / MASPS for firewall requirements. | 2020-06-23 | R. Dlouhy, S. Pelleschi - COL | 2020-07-24 |  |  | 2020-08-06 | E-mail on 8/6 from COL -- Firewall requirements are not yet in the MASPS, but 858 Section 4.3.2 points to the MASPS when the material is provided there. Email sent 7/29
M12-04 | Deferred | Upper Layer Supporting Services (e.g., ICMP) | 3.3.4 | Address Airborne IPS System-specific implications | 2019-12-11 | M. Niraula / R. Dlouhy - COL | 2020-06-10 | 2020-12-08 |  |  | Moved to Supp1 Action Items
M14-04 | Closed | Carport for Prioritization from Airborne Radios | 3.3.5.2.2 | Document the impact on the data and system (e.g., the IPS protocol). (Also refer to Madhu’s paper on QoS, which has some info relevant to rate limiting). TBD should be in MASPS, coordinated with the link-specific standards. | 2020-06-23 | M. Skorepa - HON | 2020-07-24 |  |  | 2020-07-24 | New commentary added to address rate limiting.
M14-05 | Closed | Prioritization in Airborne Radios | 3.3.5.2.3 | Keep the generic requirement that the Airborne IPS System signal this information, and add a statement that the packet type will be identified in the radio-specific standards. | 2020-06-23 | M. Skorepa - HON | 2020-07-24 |  |  | 2020-07-24 | Commentary updated
M12-16 | Closed | Multilink | 3.3.6.x | Describe detailed mechanisms for implementing the multilink concept. (How much is implementation specific?) Preference configuration. | 2019-12-11 | M. Skorepa - HON | 2020-06-10 | 2020-07-24 |  | 2020-07-24 | See detailed comments in text Text updated
M14-06 | Closed | MDE | 3.3.6.1 | Michal to re-review to identify inter-dependencies, and replace with pointers (or TBD) where possible – but can’t all be generic. | 2020-06-23 | M. Skorepa - HON | 2020-07-24 |  |  | 2020-07-24 | Text updated
M14-07 | Closed | MDE | 3.3.6.1 | Multilink includes not just selecting a link, but also selecting the right link(s) to achieve performance; add detail of how this works from a box level (without being overly prescriptive). | 2020-06-23 | M. Skorepa - HON | 2020-07-24 |  |  | 2020-07-24 | Text updated
M13-02 | Deleted | Ext Comm Manager | 3.3.6.3 | Discuss scope of this section since primarily implementation-specific, and any potential enhancements to implementation guidance in Section 5 | 2020-05-19 | M. Olive - HON S. Pelleschi - COL | 2020-06-10 |  |  | 2020-06-23 | OBE - replaced by actions 14-08 thru 14-10
M14-08 | Closed | Ext Comm Manager | 3.3.6.3 | Move to a different section separate from the IP Comm Manager. Need to address, for example, how ACARS CM and IPS CM would coordinate use of shared links (e.g., VDLm2) – but just guidance since the solution will still be implementation specific. | 23-June-202 | M. Olive - HON S. Pelleschi - COL | 2020-07-24 |  |  | 2020-07-24
M14-09 | Closed | Ext Comm Manager | 3.3.6.3 | Capture some initial thoughts as bullet points. | 23-June-202 | L. Emberger - AIR S. Pelleschi - COL | 2020-07-24 |  |  | 2020-07-22 | E-mail text received 7/22
M14-10 | Closed | Ext Comm Manager | 3.3.6.3 | Create use case for requirement in second sentence: "Responses to application messages received over one network protocol stack (i.e., ACARS or IPS) will be sent over the same protocol." | 23-June-202 | M. Niraula - COL | 2020-07-24 |  |  | 2020-07-21 | E-mail text received 7/21
M15-01 | Closed | Address Acquisition | 3.3.4.1 | Propose text for empty section | 2020-08-25 | M. Niraula - COL T. Mcparland - BCI | 2020-09-08 | 2020-10-23 | ICAO WG-I MSG | 2021-03-17 | 23-Feb: Text provided by Madhu 26-Oct: Initial input recceived 06-Oct: E-mail action item sent 24-Sep: Revisited during M15 25-Aug: E-mail action item sent
M14-26 | Closed | Ext Comm Manager | 3.3.7 | Revisit this text considering the discussion and simpler approach, and associated requirements to avoid complicated cases. Separate switching of the stacks from the selection of the access network technology (based on preference). | 2020-07-28 | S. Pelleschi, M. Niraula- COL | 2020-09-08 | 2020-11-11 |  | 2020-11-12 | 12-Nov: Updated text 28-Oct: Reminder e-mail sent 06-Oct: E-mail action item sent 24-Serp: Revisited during M15 25-Aug: E-mail action item sent DRAFT2: New text in 3.3.7 and 5.4. See additional detailed comments in text.
M15-19 | Closed | Ext Comm Manager | 3.3.7 | Impact on Legacy Comm Manager | 2020-07-28 | S. Pelleschi, M. Niraula- COL | 2020-12-08 |  |  | 2020-11-19
M15-20 | Closed | Ext Comm Manager | 3.3.7 | Tie bullets to interfaces defined in Section 3.7 | 2020-07-28 | M. Olive - HON | 2020-12-08 |  |  | 2020-11-19 | 19-Nov: Coordinated with Michal S.
M13-03 | Closed | Non-Core IPS Functions | 3.5 | Review existing comments and propose resolutions | 2020-05-19 | M. Olive - HON G. Saccone - BOE | 2020-06-10 |  |  | 2020-05-29 | Telecon 29-May
M15-02 | Closed | Network Protocol Pref, | 3.5.1.1 | Revisit this section after completing 3.3.7 | 2020-09-24 | G. Saccone - BOE | 2020-10-23 |  |  | 2020-11-19 | 06-Oct: E-mail action item sent
M15-03 | Closed | Transport Protocol Pref. | 3.5.1.2 | Add whether application is client or server. More specificity about static configuration and relationship to application or source. | 2020-09-24 | G. Saccone - BOE | 2020-10-23 |  |  | 2020-10-16 | 16-Oct: Coordination call, BOE-HON 06-Oct: E-mail action item sent
M14-11 | Closed | Static Address Lookup | 3.5.1.4 | Need some detail about how the addresses are refreshed e.g., LIFO. | 2020-06-23 | G. Saccone - BOE | 2020-07-24 | 2020-09-08
M12-07 | Closed | Addressing | 3.5.1.4 | Address configuration and storage | 2019-12-11 | G. Saccone - BOE | 2020-06-10 |  |  | 2020-05-29 | Telecon 29-May
M12-11 | Closed | Security Management | 3.5.4 | Airborne IPS System level security event logging, log life cycle management, security configuration and tuning (e.g., firewall rules), crypto agility, continued airworthiness aspects | 2019-12-11 | G. Saccone - BOE M. Vanguardia - BOE | 2020-06-10 |  |  | 2020-05-29 | Telecon 29-May
M14-12 | Closed | Redundancy Support | 3.5.5 | Identify the metrics that would drive the need for redundancy. Add more information about what needs to be considered as part of synch, including what’s necessary for hot-vs-cold standby, key/cert sync. | 2020-06-23 | G. Saccone - BOE | 2020-07-24 |  |  | 2020-07-31 | Telecon 31-Jul
M14-13 | Closed | External Interfaces | 3.6.1 | I think it would be very helpful for standardization (e.g. A/G IF) if these interfaces are already specified. Are these interfaces individual for each airborne radio system? Over which interface the JOIN/LEAVE information will be exchanged? (link established link closed) | 2020-06-23 | M. Skorepa - HON | 2020-07-24 |  |  | 2020-07-24 | In D1-06, added clarification text with references to existing radio interfaces
M13-04 | Closed | Internal Interfaces | 3.6.2 | Review comment in light of updated text and suggest additional material as appropriate | 2020-05-19 | R. Dlouhy - COL | 2020-06-10 |  |  | 2020-06-08 | E-mail 8-June -> OBE
M12-15 | Closed | Performance Req | 3.7 | BRU meeting discussion recommended adding a reference to the MASPS for performance requirements. Should Table 3-1 be removed and replaced by a pointer to MASPS? | 2020-05-19 | G. Saccone - BOE L. Emberger - AIR | 2020-06-10 |  |  | 2020-07-08
M13-05 | Deleted | IPS Security | 4.x | Comment disposition -- some comments may be dependent upon ICAO discussion and decisions | 2020-05-19 | L. Leonardon - COL | 2020-06-10 |  |  |  | OBE - replaced by actions 14-14 thru 14-23
M15-04 | Closed | Static Address Lookup | 3.5.1.4 | Double-check the IPS Profiles regarding host naming requirements | 2020-09-24 | S. Pelleschi - COL | 2020-10-23 |  |  |  | 13-Oct: Text OK, but refer to MASPS instead of Profiles. 07-Oct: E-mail action item sent
M15-05 | Closed | Redundancy Support | 3.5.5 | Additional detail about what parameters need to be synch’d. Consider whether to keep high level here and put something more detailed in Section 5 as implementation guidance (OR an Appendix). | 2020-09-24 | G. Saccone - BOE | 2020-10-23 |  |  | 16-Oct-202 | 16-Oct: Coordination call, BOE-HON 06-Oct: E-mail action item sent
M15-06 | Closed | IPS Management App | 3.6 | new section that describes the function of the application and any message handling mechanisms (e.g., fragmentation, reliability, etc.) and how the ground providers of the service are selected (and IP address obtained). | 2020-09-24 | J. Graefe / R. Dlouhy - COL | 2020-10-23 | 2020-11-11 |  | 2020-11-12 | 12-Nov: Updated text 28-Oct: Edited text sent for updates 22-Oct: Preliminary text received 06-Oct: E-mail action item sent
M15-21 | Closed | IPS Management App | 3.6 Att4, 4.2.1 | Describe how the IPv6 address of the ground peer is known/discovered. Add that it’s optional for aircraft depending on how features are implemented (e.g., addresses stored onboard) | 2020-11-13 | J. Graefe / R. Dlouhy - COL | 2020-12-08 |  |  | 2020-12-16
M12-08 | Deferred | IPS Security | 4.x | Airborne IPS System security requirements traced to high-level provisions in Doc. 9896 | 2019-12-11 | L. Leonardon - COL M. Vanguardia - BOE | TBD |  | ICAO WG-I and SSG |  | Moved to Supp1 Action Items
M14-14 | Closed | Security Arch Overview | 4.2 | When available, point to cyber risk assessment as justification/rationale. | 2020-06-23 | L. Leonardon - COL | TBD |  | ICAO WG-I SSG |  | DRAFT2: Commentary added to capture dependency
M14-15 | Closed | Data Flow Segregation | 4.3.3 | Does the segregation need to be enforced within the Airborne IPS System also? The commentary highlights one onboard aspect, but it’s not explicit whether segregation within the Airborne IPS System is mandated also. | 2020-06-23 | L. Leonardon - COL | 2020-07-24 |  |  | 2020-08-04 | In D1-06 and D1-08, updated commentary and added a reference to Section 5 regarding Airborne IPS System segregation. Section 4.5 updated to reference NIST FIPS
M15-07 | Closed | Cryptographic Services | 4.3.1.3 | Include box-level details re: crypto services. NOTE – This section should reference the auth/integrity vs. auth/integrity/encryption services, but the specific ciphersuites are specified in Doc. 9896. | 2020-09-24 | M. Niraula - COL | 2020-10-23 |  |  | 2020-10-22 | 22-Oct: Input received 06-Oct: E-mail action item sent
M15-22 | Closed | Cryptographic Services | 4.3.1.3 | Revisit whether ground-initiated DTLS is necessary, or whether the ground can trigger the aircraft to initiate a session (to simplify airborne system implementation and reduce attack surface). | 2020-10-26 | M. Niraula - COL | 2020-12-08 |  |  | 2020-12-15 | Discussed and closed during telecon
M15-23 | Closed | Cryptographic Services | 4.3.1.3 | Confirm that specified cipher suite is applicable to DTLS v1.3 (may be different name and different binary value) | 2020-10-26 | M. Niraula - COL | 2020-12-08 |  |  | 2020-11-30 | 30-Nov: Updates from Timo
M14-16 | Closed | Crypto Key Management | 4.4.1 | Reference to ATA Spec 42 may be removed depending on ICAO DOC 10095 development. | 2020-06-23 | T. Warns - AIR | TBD |  | ICAO WG-I SSG Doc. 10095 |  | 5-Oct - Removed ATA Spec 42 reference since that should be included in Doc. 10095, if applicable.
M14-17 | Closed | CSR Export / Cert Import | 4.4.1.3.3 | The requirement for using a secure link to download the generated certificate can be relaxed. The certificate can be downloaded via an unsecure link (unlike uploading the CSR) since it is signed by a CA and since confidentiality of the public key certificate does not have to be ensured. | 2020-06-23 | T. Warns - AIR | 2020-07-24 |  |  | 2020-07-28 | Text updated
M14-18 | Deferred | Trust Anchor | 4.4.1.1.4 | Revisit ATA Spec 42 reference with respect to ICAO DOC 10095 guidance. | 2020-06-23 | T. Warns - AIR | TBD |  | ICAO WG-I SSG Doc. 10095 |  | Moved to Supp1 Action Items. DRAFT2: Commentary added to capture dependency
M14-19 | Closed | Cert Revocation Check | 4.4.1.1.5 | As further security controls may be needed for CRL provisioning (e.g. TCP security), it seems reasonable to have further details. There may be reduced need for OCSP/CRL in case of short-lived ground certificates | 2020-06-23 | T. Warns - AIR | 2020-07-24 |  |  | 2020-07-28 | Additional commentary was added
M14-20 | Closed | Cert Revocation Check | 4.4.1.1.5 | Revisit commentary -- as DTLS v1.3 likely supports this directly (tbc), it would be sufficient to handle this at RTCA/EURCAE level. | 2020-06-23 | T. Warns - AIR | 2020-07-24 |  |  | 2020-07-28 | New comment to clarify remaining action
M14-27 | Closed | Certificate Revocation Check | 4.4.1.1.5 | Multiple certificate status check to be confirmed with respect to DTLS v1.2 and 1.3 | 2020-06-23 | T. Warns - AIR | 2020-07-24 | 2020-09-08 |  |  | A comment had been added to PP858. 27-Aug: E-mail sent to RTCA/EUROCAE regarding remaining action to ensure that the IPS profile moves to DTLS v1.3 or, if keeping DTLS v1.2, adds RFC 6961.
M14-21 | Closed | Key Usage / Cert Validation | 4.4.1.1.6 | When the certificate profile is defined, validation checks can be made more precise. This may involve checks on tail ID, ICAO 24-bit address and operator code. | 2020-06-23 | T. Warns - AIR | TBD |  | ICAO WG-I SSG Doc. 10095 | 2020-09-24 | DRAFT2 - New comment to clarify remaining action
M14-22 | Closed | Key Destruction | 4.4.1.1.7 | Requires further consideration (addressing operator code changes). Operator code change will also affect airborne IPv6 address (given current addressing proposal). | 2020-06-23 | T. Warns - AIR | TBD |  | ICAO WG-I SSG Doc. 10095 | 2020-09-24 | DRAFT2 - New comment to clarify remaining action
M14-23 | Closed | Security Log Entries | 4.4.2.2 | Remove comment and provide what parameters to be used because syslog protocol is not applicable. Add some more specificity about the minimum content in the log. (Madhu has some additional items) | 2020-06-23 | L. Leonardon - COL M. Niraula - COL | 2020-07-24 |  |  | 2020-08-06 | Proposed field included in document E-mail sent 8/6 E-mail sent 7/30
M13-06 | Closed | Host vs. Router | 5.5 | Madhu to send Mike his RTCA paper on this topic | 2020-05-19 | M. Niraula - COL | 2020-05-26 |  |  | 2020-05-26 | Mike found it on RTCA site.
M13-07 | Closed | Host vs. Router | 5.5 | Mike to craft proposed text for this section using Madhu's paper as an input | 2020-05-19 | M. Olive - HON | 2020-06-10 |  |  | 2020-06-15
M15-02 | Closed | Security Log Format | 4.4.2.2 | Consider using the syslog framework (e.g., header) and then define IPS-specific entries. | 2020-08-25 | T. McParland - BCI | 2020-09-08 |  |  | 2020-09-02 | 2-Sep: Input received 25-Aug: E-mail action item sent See text for additional related comments.
M15-08 | Closed | Transfer/Export of Logs | 4.4.2.5 | Consider whether to add real-time log transfers to Attachment 4 OR treat as a Native IP app (but may not be a strong need to specify that detail in 858). | 2020-09-24 | M. Niraula, R. Dlouhy - COL | 2020-10-23 |  |  | 2021-02-23 | 23-Feb: Action moved to IPS Management App (material moved from 858 to 9896) 24-Jan: Recommendation from Timo
M16-01 | Closed | I/F with Airborne Radios | 5.3.2.1 | Add a comment to say that this interface is likely going to evolve to support multilink concepts (and same for IF-4) | 2021-01-04 | TBD | 2021-01-26 |  |  | 2021-01-19
M14-11 | Closed | Host vs. Router | 5.5.1 | Clarify comment regarding sharing neighbor discovery information (in Commentary) | 2020-06-23 | M. Niraula - COL | 2020-07-24 | 2020-10-23 |  | 2020-12-15
M16-02 | Closed | IPS Router | 5.5.1 | Capture bridging prevention in Section 4 (security) Or Section 3. (Or in 9896?) so that it’s a normative statement. | 2020-12-15 | TBD | 2021-01-26 |  |  | 2021-01-19
M15-01 | Closed | Host vs. Router | 5.5 | Update diagram to show non-IPS systems on left hand side of the diagram as well. | 2020-08-25 | M. Olive -HON | 2020-09-08 |  |  | 2020-08-25
M13-09 | Closed | Acronyms | Att 1 | Keep up to date wrt PP858 document | 2020-05-19 | M. Olive - HON | Ongoing
M13-09 | Closed | Glossary | Att 2 | Keep up to date wrt ICAO terminology activity | 2020-05-19 | M. Olive - HON | Ongoing |  |  |  | 12-Nov: Updated per ICAO Terms 3-Jun: Updated per ICAO terms
M13-10 | Closed | AICF | Att 3 3.3.2.1, 3.2.3.2 | Address Fryd's comments per discussion during 5/19 IPS telecon | 2020-05-19 | M. Olive - HON | 2020-06-10 |  |  | 2020-05-26
M14-24 | Closed | AICF | Att 3 3.4.3 | Is it necessary to maintain the dialog? (if we consider ATS, A623, AOC with different ground entities, I fear that we will have to maintain many dialogues). We should maybe be able to distinguish several types of dialogues (maintained and not maintained) | 2020-06-23 | M. Olive - HON | 2020-07-24 | 2020-09-08 |  | 2020-10-05 | 5-Oct: Per M15 discussion, added application inactivity time as additional means to close dialogue.
M12-02 | Deleted | IPS Management Messages | Att4 (all) | Potential need to address how to configure preferences that are communicated to the ground. | 2019-12-11 | J. Graefe / R. Dlouhy - COL | 2020-06-10 | 2020-09-08
M13-11 | Deleted | IPS Management Messages | Att4 (all) | Comment disposition (general) | 2020-05-19 | J. Graefe / R. Dlouhy - COL | 2020-06-10 | 2020-10-23 |  |  | 12-Nov - Proposed text to addrress some comments 1-Sep - Proposed changes based on SSG decision to use standard DTLSv1.3. 27-Jun. - Telecon COL, BOE, HON
M15.09 | Deferred | IPS Management Messages | Att4 (all) | Confer with RTCA/EUROCAE about whether the material in Att4 should be in Profiles or MASPS. | 2020-09-24 | S. Pelleschi - COL | 2020-10-23 |  |  |  | 13-Oct: General agreement to keep in 858 for first release and reassess during development of Supp1. 07-Oct: E-mail action item sent
M15-23 | Closed | IPS Management Messages | Att4, 4.new | Accumulate protocol material in one section (Mike to coordinate with Ron) | 2020-11-13 | M. Olive - HON / R.Dloughy - COL | 2020-12-08 |  |  | 2020-12-14 | 1-Dec: Provided reorganized Att4 to COL
M15-24 | Deleted | IPS Management Messages | Att4, 4.x | Consider examples (simular to SNL message) for other messages | 2020-11-13 | M. Olive - HON / R.Dloughy - COL | 2020-12-08
M15-10 | Closed | IPS Management Messages - Post Auth DL | Att4, 4.4.1 | Need more specificity about exactly what address is included. | 2020-09-24 | M. Niraula / R. Dlouhy - COL | 2020-10-23 |  |  | 2020-11-13 | 13-Nov: Clarified during telecon
M15-24 | Closed | IPS Management Messages - Post Auth DL | Att4, 4.4.1 4.3.11.1 (new org) | Add more context about the use cases where this is used, when sent, need when all-IPS, etc. | 2020-11-13 | M. Niraula / R. Dlouhy - COL | 2020-12-08
M15-11 | Closed | IPS Management Messages - Post Auth UL | Att4, 4.4.2 | Propose a new post-authentication uplink message | 2020-09-24 | M. Niraula / R. Dlouhy - COL | 2020-10-23 |  |  | 2020-11-12 | 12-Nov: Proposed text received
M12-09 | Closed | PKI | Att-4 4.11 | Define detailed key management messages | 2019-12-11 | J. Graefe / R. Dlouhy - COL | 2020-06-10 | 2020-08-06 |  | 2020-08-06 | 17-Jun: Telecon COL, BOE, HON
M13-12 | Closed | D-DATA | Appx A A-3 | User Data length definition updates (see comment) | 2020-05-19 | R. Dlouhy - COL F. Wrobel - Airtel | 2020-06-10 |  |  | 2020-07-24 | Discussions and agreement among BOE, COL, HON, Airtel
M15-12 | Closed | IPS Management Messages -Change FlightID | Att4, 4.10.1 4.6.1 (new org) | The highlighted text captures Jonathan’s comment from 8/7 version. Still need to address what happens next when this message fails (i.e., can’t Change FlightID). | 2020-09-24 | R. Dlouhy (in coord with J. Graefe) - COL | 2020-10-23 |  |  | 2021-01-08
M15-13 | Deleted | IPS Management Messages - Key Mgmt | Att4, 4.11 4.6 (new org) | Provide further detail on EST. | 2020-09-24 | T. Warns - AIR | 2020-10-23
M15-14 | Closed | IPS Management Messages - Key Mgmt | Att4, 4.11 Table 4-9 | Requirement that keys should be renewed for every certificate request should be captured in Section 4. | 2020-09-24 | M. Olive - HON | 2020-10-23 |  |  | 2020-10-07 | 11-Oct: Text improved and agreed 07-Oct: E-mail with proposed text sent
M15-15 | Deleted | IPS Management Messages - Key Mgmt | Att4, 4.11 4.7 (new org) Table 4-11 | Concept for temporary key should be captured in Section 4. | 2020-09-24 | R. Dlouhy (in coord with J. Graefe) - COL | 2020-10-23
M15-16 | Deleted | IPS Management Messages - Key Mgmt | Att4, 4.11 4.7 (new org) Table 4-11 | Concept for upload of aircraft public key cert should be captured in Section 4. | 2020-09-24 | R. Dlouhy (in coord with J. Graefe) - COL | 2020-10-23
M15-17 | Closed | Security Event Log Format | Att4, 4.11 4.7 (new org) Table 4-11 | Harmonize "Event Type" with Section 4.4.2.3 in main body. An alternative to enumerated list would be a text string. | 2020-09-24 | M. Niraula - COL | 2020-10-23 |  |  | 2020-10-22 | 22-Oct: Input received 06-Oct: E-mail action item sent
M16-03 | Deleted | Chang IP address | Att4, 4.7.8 | I am not convinced that the message to change the IP address is really necessary. Unless we explain the contrary, the new address may not survive to a switch power on/off of the IPS system... | 2021-01-06 | TBD | 2021-01-26
M15-18 | Closed | Security Event Log Format | Att5, 5.1.2 Table 5-1 | For blank cells in the “Details” column, add missing info. | 2020-09-24 | M. Niraula - COL | 2020-10-23 |  |  | 2020-10-22 | 22-Oct: Input received 06-Oct: E-mail action item sent
M13-13 | Deferred | D-ACK | Att5, 5.1.2 Table 5-1 | High-water mark acknowledgement (see comment) | 2020-05-19 | M. Niraula - COL F. Wrobel - Airtel | 2020-06-10 | 2020-09-08 | ICAO WG-I Doc. 9896 |  | Moved to Supp1 Action Items
M13-14 | Closed | UDP / IPv6 Background | Appx A A-4 | Re-review entire document to make sure that UDP/IPv6 descriptions in Appx B are not duplicated elsewhere in the document. | 2020-05-19 | M. Olive - HON M. Niraula - COL F. Wrobel - Airtel | 2020-06-10 |  |  | 2020-06-08 | Ed note: In main body, only references to IPS Profiles but no background detail like what is captured in Appx B.
M13-15 | Closed | IPS Gateway | Appx C | Comment disposition | 2020-05-19 | R. Dlouhy - COL | 2020-06-10 | 2020-10-23 |  | 2021-02-02 | 2-Dec: Text posted for review 1-Dec: Telecon COL, Airtel, HON, BOE 12-Nov: Some original text integrated 20-Oct: Telecon COL, Airtel, HON, BOE 1-Sep: Edited text sent for review 27-Jul: Fryd provided v0.2 27-May: Telecon COL, Airtel, HON & Boeing -> Fryd to propose updates.
Deleted
Deferred
Closed
Next
M16-04