## Sheet1
Action Item | ARINC 791 P1 | ARINC 791 P2 | ARINC 792 | Description | Responsible | Company | Date Opened | Due Date | Comments
1 | X |  |  | Review D1S3 to ARINC 791 P1 prior to next Web conference | KSAT Subcommittee | ALL | 2018-05-08 | 2018-06-14 | Draft 1 is in the AEEC AGCS SC SharePoint. Will be discussed during the June 14th conference call. See Item 15
2 | X | X | X | On AGCS SharePoint Create meeting directory under Libraries | Jose Godoy | ARINC IA / SAE ITC | 2018-05-08 |  | Completed
3 | X |  |  | Schedule 14June Conference Call | Jose Godoy | ARINC IA / SAE ITC | 2018-05-08 |  | Completed
4 | X |  |  | Accept Changes for A791P1 D1S3 | KSAT Subcommittee | ALL | 2018-05-08
5 | X |  |  | Post A791 D1S3 | Jose Godoy | ARINC IA / SAE ITC | 2018-05-08 |  | See Item 75
6 | X |  |  | Name a MIBs Section Editor | KSAT Subcommittee | ALL | 2018-05-08 |  | 1Aug2018: Mark to contact GoGo, they may be the MIBs editor. See item 20. 18Dec2018 - Possible Airbus person (Chris to confirm). See 6, 20, 145, 146, 147, 192 and item 202
14June2018 - Web Conference
7 |  |  |  | Reach out to (Domingo) Embraer for tail Mount Ant info | Peter Lemme | Totaport | 2018-06-14 | 2018-07-18 | Domingo Barbosa
8 | X |  |  | Provide strawman source document to Victor | Jose Godoy | ARINC IA / SAE ITC | 2018-06-14 | 2018-06-15 | Completed
9 |  |  |  | Victor to revise A791 P1 TMA Section add to new Attachment | Victor Gheorghian | Bombardier | 2018-06-14 |  | 1Aug2018: Target next web Conference
10 | X |  | X | Expand DeIcing Section (RTCA DO-160) on Radome | Mark Sorensen | Delta | 2018-06-14 |  | Include penetration info/spaying; DO-160 not adequate (to 792 in future). Add as commentary. Inputs welcomed. target July 18th. 1Aug 2018: Do not have the same environmental requirements, Antenna should be tested on its own for susceptibility - On Going (add supplementary test). 18Dec2018: On Going to be discussed at next meeting.
11 | X |  | X | Advise RTCA that DO-160 need revision to address Ant DeIcing | Mark Sorensen | Delta | 2018-06-14 | 2018-07-18 | Contact Brad Green (Section 10 (Waterproofness) and/or Section 11 (Fluids susceptibility). 1Aug 2018: On Going (See item 10). On Going (add supplementary test). 18Dec2018: On Going to be discussed at next meeting.
12 |  |  |  | What to do with Fiber (replace Coax Cables?) | Chris Schaupmann | Airbus | 2018-06-14 | 2018-07-18
13 |  | X | X | What to do with Cutting Power (not on essential Bus) | Chris Schaupmann | Airbus | 2018-06-14 |  | What power is consumed, - power for degraded mode 17Jan2019: Add A/C Input Pwr Magt to A792-1 APIIM
14 | X | X |  | Identify if there is an Attenuators issue (Design issue?) | Chris and Mark | Airbus and Delta Air Lines | 2018-06-14 |  | In ARINC 791 P2 determined attenuation power is adequate? 1Aug 2018: There are attenuators in the L-Band systems. 29Oct2019 - Waiting on Viasat analysis See items 138 and 200
15 | X |  |  | Review D1S3 to ARINC 791 P1 prior to next Web conference | KSAT Subcommittee | ALL | 2018-06-14 | 2018-07-18 | Draft 1 is in the AEEC AGCS SC SharePoint. Will be discussed during the next conference call. See Item 1
16 |  |  |  | Ad Hoc working group to develop common form factor and edge connector for MODEM (component of MODMAN) | Peter Lemme and Gary | Totaport | 2018-06-14 | 2018-07-18 | Isotropic Systems
17 | X | X | X | Schedule next Conference Call | Jose Godoy | ARINC IA / SAE ITC | 2018-07-18 |  | Schedule for July 18
18 | X | X | X | Schedule next Conference Call | Jose Godoy | ARINC IA / SAE ITC | 2018-07-18 |  | 2018-08-01
1 August 2018 - Web Conference
19 |  |  |  | Consider adding radome disturbance cautionary note |  |  | 2018-08-01 |  | 18Dec2018: review inputs if submitted
20 |  | X |  | Update MIB Section? | Mark Sorensen | Delta | 2018-08-01 |  | 1Aug2018: Mark to contact GoGo, they may be the MIBs editor. 18Dec2018 - Possible Airbus person (Chris to confirm). 29Oct2019: See Action 6, 20, 145, 146, 147, 192, and 202
21 | X | X | X | Work on the next meeting | Jose Godoy | ARINC IA / SAE ITC | 2018-08-01 |  | Oct 30, 31 and Nov 1st in Annapolis, MD
22 | X | X | X | Reach out to Embraer (Domingo) |  |  | 2018-08-01 |  | See action 7; Embraer states they are interested (TMA)
23 | X |  |  | Review D1S3 to ARINC 791 P1 prior to next Web conference | KSAT Subcommittee | KSAT Subcommittee | 2018-08-01 |  | See item 15
11 September 2018 - Web Conference
24 | X |  |  | Place A791 Strawman in SharePoint | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11 |  | Updated with Airbus' (Chris) Comments
25 | X |  |  | Review A791 Strawman (Airbus Comments) | KSAT Subcommittee | KSAT Subcommittee | 2018-09-11 |  | Be prepared to discuss during 16Oct2018 Web Conference. See item 25
26 | X |  |  | Victor to update TMA white paper | Victor Gheorghian | Bombardier | 2018-09-11 |  | Add Environmental Table and mechanicals (size, # of screws, loads). Oct 10, 2018: Submitted by Victor
27 | X |  |  | Place Bombardier Tail Mount Ant white paper in SharePoint | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11 |  | Victor presented white paper
28 | X |  |  | Review Bombardier TMA white paper; comment | KSAT Subcommittee | KSAT Subcommittee | 2018-09-11 |  | See Item 33
29 |  |  | X | What to do with pinout inconsistencies, why was it implemented |  |  | 2018-09-11 |  | A429/IRS/GPS/GNSS - Feedback from Peter. See item 35
30 |  |  | X | Distribute RC Comments and place on SharePoint | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11
31 | X | X | X | Schedule next meeting | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11 |  | Oct 30, 31, Nov 1 in Annapolis, MD
32 | X | X | X | Schedule next web conference | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11 |  | 2018-10-16
16 October 2018 - Web Conference
33 | X |  |  | Review/Discuss updated Bombardier TMA and Environmental Categories white paper | KSAT Subcommittee | KSAT Subcommittee | 2018-10-16 |  | 18Dec2018: Ongoing; contact bombardier for continuity after Victor's departure. See items 26 and 28. See item 86
34 | X |  |  | Review ARINC 791 Part 1 Strawman | KSAT Subcommittee | KSAT Subcommittee | 2018-10-16 |  | see items 23 and 25
35 |  |  | X | Clarify ARINC 792 inconsistencies | KSAT Subcommittee | KSAT Subcommittee | 2018-10-16 |  | see item 29
36 | X |  |  | Astronics to provide alternate TMA configuration diagram | Jonathan Epstein | Astonics | 2018-10-16 | 2018-10-29 | Send to Victor and Jose
37 | X |  |  | Propose tail mount antenna structural susceptibility (movement) note/comment | Jonathan Epstein | Astonics | 2018-10-16 | 2018-10-29 | High level comment/requirement/generic (awareness and/or guidance)
38
39 |  |  |  | create WishList for ARINC 792-1 APIM |  |  |  |  | See Item 74
40 | X | X | X | Schedule next web conference | Jose Godoy | ARINC IA / SAE ITC | 2018-10-16
30 Oct - Nov 1, 2018 - Annapolis Meeting
45 | X |  |  | Victor to revise Astronics provided TMA Block Diagram | Victor Gheorghian | Bombardier | 2018-10-30 | 2018-11-20 | Add justin and Dan to mailing list Contact Bombardier. See item 87
46 |  |  |  | ProvideTable 2-3 (SharePoint ) for modification (e.g., visio) | Jose Godoy | ARINC IA |  | 2018-11-20
47 | X |  |  | New TMA Configuration Figure that is equivalent to Figure 2-3 Topo distribution, with TMA topography with all options (all equipment that cab reside in the pressurized vessel) | Victor Gheorghian | Bombardier | 2018-10-30 | 2018-11-20 | Also revise Figure 2-3a name (rename) for FMA only. Contact Bombardier; See item 88
48 | X |  |  | Airbus to provide updated Cable Insertion Loss (Section 6.4) based on ARINC 792 | Chris Schaupmann | Airbus | 2018-10-30 | 2018-11-20 | 18dec2018 - OnGoing
49 | X |  |  | Review out dated Section 8 - | Greg Otto and KSAT SC | Thinkom Solutions | 2018-10-30 | 2018-11-20 | Greg and Chris have provided inputs for review. See Item 81
49 | X |  |  | Carlisle to provide cooling comment | Brad Purpus | Carlisle Interconnect | 2018-10-30
50 | X |  |  | Add 2nd drawing for TMA option for Figure 4-21 KANDU Interfaces | Peter Lemme | TOTAPORT | 2018-10-30 | 2018-11-20 | Create different attachment for interwiring. See item 89. 17Jan2019: No interwiring will be added for TMA.
51 | X |  |  | Victor ro revise TMA Qual Req (add columns for ea assy) | Victor Gheorghian | Bombardier | 2018-10-30 | 2018-11-20 | A792 Qual Notes 22 and 23 Applicale to A791 Qual ? (Co-route power & control cables). 18Dec2018: Contact Bombardier. See items 33 and 86
52 | X |  |  | Replace Qual test Table 2-2 with revised TMA Qual Table | Jose Godoy | ARINC IA | 2018-10-30 | 2018-11-20 | After Victor provides
53 |  |  |  | Request Gulfstream and Embraer input on their qual requirements if co-locating coax and power cables in TMA | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-20 | Like Note 23 in A792 18Dec2018: Contact Embraer and Gulfstream. See item 91
54 | X |  |  | Airbus to provide Attachment 1.1 (Figure 1-19) | Chris Schaupmann | Airbus | 2018-10-30 |  | Cutout zones (geometry)
55 |  |  |  | Airframers to inverstigate if they use/hacv access to European Norm EN3645 (size 8 connector) | Victor, John, Jorge | Bombardier, Boeing and Gulfstream | 2018-11-01 | 2018-11-20 | Change connector? European Norm EN3645 and Mil ST are not interchangeable
56 | X |  |  | Paul to send white paper with issue with arrangement 21-84 | Paul Ahlf | Carlisle Interconnect | 2018-10-30 |  | Replace arrangement 21-84 (Quadrax Conn Table 4-17
67 | X |  |  | Consider reducing number of Modem outputs | KSAT SC | KSAT SC | 2018-10-30 | 2018-11-20 | Per A792. Suppliers to comment if used or if they object. Airbus to check. Delta, Boeing and Bombardier: disagree, it could limit options.
58 | X |  |  | New drawing for option between KANDU and Modem (bulkhead penetration). Maybe other figures | Victor Gheorghian | Bombardier | 2018-10-30 | 2018-11-20 | Victor to requesdt source file/s (figure number/s). 18Dec2018: Contact Bombardier. See Item 92
59 | X |  |  | Clean up drawing with Quadrax connectors.(Figure 4-31) | Chris Schaupmann | Airbus | 2018-11-01 | 2018-11-20 | See A664P2 (ref line). Figure 4-31
60 | X |  |  | Qual Requirements for Cat 7 and 8 curves | Chris Schaupmann | Airbus | 2018-10-30 | 2018-11-20 | Airbus (Markus) to comment ; compare
61 | X |  |  | 5/1000 range comment | Chris Schaupmann | Airbus | 2018-10-30 |  | Origin of 5/1000
62 | X |  |  | Global Eagle to advise if Note 22 is required in Qual Test Table (Section 4), if so provide proposed Note wording | Antonio Campobasso | Global Eagle | 2018-10-30 | 2018-11-20 | Global Eagle: Level might be too high. See Global eagle email (Jose). 18Dec2018: See November 6, 2018 email from A. Campobasso (Global Eagle)m, stating no issue
63 | X |  |  | Verify the crash safety sustained impulses (Section 7, Category cange from E to B for all except OAE) | John Rodgers | Boeing | 2018-11-01 | 2018-11-20 | Airbus has confirmed (Ok to go to B). 18Dec2018: Boeing confirmed OK with B inside LRUs. See 12Dec2018 email from John Rodgers
64 | X |  |  | Verify the lighting requirement (>than DO-160?) | John Rodgers | Boeing | 2018-11-01 | 2018-11-20 | 18Dec2018: per 12Dec2018 email from John: Boeing ok as stated in attachment A. Specific Boeing requirements per Boeing documents.
65 |  |  |  | Verify Icing requirement (DO-160 section 24) | John Rodgers | Boeing | 2018-11-01 | 2018-11-20 | 18Dec2018: per 12Dec2018 email from John:Inside fuselage NA. Outside fuselage: Non moving LRUs A. Moving LRUs B.
66 | X |  |  | Verify Temperature requirement (DO-160 section 22) | John Rodgers | Boeing | 2018-11-01 | 2018-11-20 | 18Dec2018: per 12Dec2018 email from John: Inside fuselage A2. Outside fuselage: D2 Modified; Ground Thermal Cert 110C.
67 | X |  |  | Why are there duplicate Qual rows for Section 16, 20 and 22 (Different 160E,F,G) | KSAT SC | KSAT SC | 2018-11-01 | 2018-11-20 | Discuss further
68 |  |  | X | Boeing to request considering Active Low for WoW (ARINC 792 Att6, Section 6.3.2 _ WOW (Air/Gnd) | John Rodgers | Boeing | 2018-10-31 | 2018-11-20 | What would it take to change B787? 18Dec2018: per 12Dec2018 email from John: Have requested details and impact for 787 to change this logic. NO CHANGE
69 | X |  | X | IRU global, except for system descriptions | Jose Godoy | ARINC IA | 2018-10-31 | 2018-11-20 | 18Dec2018: Done for ARINC 792
70 | X | X | X | Provide info on next AEEC SAI Meeting (Date and Vanue) | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-02 | February 7-8, 2019 at Gables Engineering in Coral Gables, Florida.
71 |  |  | X | Provide APIM Form | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-02 | In AEEC KSAT Subcommittee SharePoint
72 |  |  | X | Create A792 Supplement 1 - Wish List matrix | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-02 | In AEEC KSAT Subcommittee SharePoint
73
74 |  |  | X | Start APIM. All to submit items for A792-1 Wish List | KSAT SC | KSAT SC | 2018-11-01 | 2018-11-20 | APIM Form and Wish list matrix are in SharePoint
75 |  |  |  | Post A791Part 1 D1S3 | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-27 | Expected right after Jan meeting; 3Jan2019: Trying to post prior to Cocoa Beach meeting
76 | X | X | X | Schedule next WebEx conference (Nov 27, 2018) | Jose Godoy | ARINC IA | 2018-10-31 |  | Scheduled for Nov 27, 2018
77 | X | X | X | Arrange next meeting (Jan 15-17, 2019) | Jose Godoy | ARINC IA | 2018-10-31 |  | Scheduled for Jan 15-17, 2019
78 |  |  |  | Post next meeting announcement | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-27 | 20Nov2018: Expected by Nov 26th (Ask Jose if details are needed in advance)
Nov 27, 2018 - Conference
80 |  |  | X | Review Alternate KPSU to OAE wiring proposal | KSAT SC | KSAT SC | 2018-11-27 |  | Already in A792?
81 |  |  |  | Review Installation/Calibration/Alignment emails | KSAT SC | KSAT SC | 2018-11-27
82 |  |  |  | Add calibration and Alignment definition on ARINC 791 P1 and 2 | Chris Schaupmann | Airbus | 2018-11-27
83 |  |  |  | Schedule next WebEx | Jose Godoy | ARINC IA | 2018-11-27 |  | Scheduled for December 18, 2019
Dec 18, 2018 - Conference
85 | X | X | X | Confirm Dan and Justin (Bombarsdier are on the AEEC KSAT Subcommittee distribution | Jose Godoy | ARINC IA | 2018-12-18 |  | Added
86 | X |  |  | Populate Attachment 2 (Equip. Qual.) - Table 2-2 with TMA values |  |  | 2018-12-18 |  | Ask if Bombardier to provide (previously committed to by Victor). See item 33
87 | X |  |  | Include Astronics inputs to TMA diagram |  |  | 2018-12-18 |  | Ask if Bombardier to provide (previously committed to by Victor). See item 45
88 | X |  |  | Add Figure 2-3b (Topographic Distribution) for TMA configuration |  |  | 2018-12-18 |  | Ask if Bombardier to provide (previously committed to by Victor). See item 47
89 | X |  |  | Create Figure 4-21B (KANDU interfaces for TMA configuration | Peter Lemme | TOTAPORT | 2018-12-18 |  | See Item 50
90 | X |  |  | Create Interwiring for KANDU interfaces (new Attachment) | Peter Lemme | TOTAPORT | 2018-12-18 |  | See Item 50
91 | X | X | X | Contact Embrear and Gulfstream (TMA configuration and Attachment 2 (Equipment Qualification - Environmental Table) | Jose Godoy | ARINC IA | 2018-12-18 |  | request they review Qual Section, attned conferences and comment on TMA. See items 22 and 53
92 |  | X |  | New drawing for option between KANDU and Modem (bulkhead penetration). Maybe other figures |  |  |  |  | Ask if Bombardier to provide (previously committed to by Victor). See Item 58
93
94 | X | X | X | Schedule Jan 2019 web Conference
95
Cocoa Beach Meeting
100 |  | X |  | Astronics to provide commentary for maximum linear power (or Calibration Section) | Jonathan | Astronics | 2019-01-15
101 |  | X |  | Rearrange Section 3.0 for Generic Antenna Description, followed by FMA and then TMA requirements | Jose | ARINC IA | 2019-01-15
102 |  | X |  | Rework Figures 3-1 (OAE with Ku/Ka band interfaces) and 3-2 - revise drawing for generic Antenna Installation instead of FMA) | Peter | TotaPort | 2019-01-15 |  | If the artwork is found
103 |  | X |  | Write Commentary KANDU 10 Output Voltage (section 5.1.2) | Paul |  | 2019-01-15
104 |  | X |  | Contact Boeing and Airframers so they can confirm support (add to APIM) | Jose | ARINC IA | 2019-01-16
105 |  | X |  | Contact Embraer, Bombardier and Gulfstream for assistance completing TMA Section/s | Jose |  | 2019-01-16
106 |  | X |  | Submit APIM (A792-1) | Jose |  | 2019-01-16
107 |  | X |  | Peter to re-do Attachment 3 with David's Antenna Pattern (Blockage) | Peter | TotaPort | 2019-01-16 |  | ON GOING
108 |  | X |  | David to provide model with bank angle, move location, etc. | David | AMS
109 |  | X |  | Chris to research source of change for Figures 1-13 and 1-14 (Attachment 1) | Chris and Peter |  | 2019-01-16
110 |  | X |  | Chris to research 21L75 Quadrax connector and add history commentary (use/availablity). Explain why 21-84 was replaced | Chris | Airbus | 2019-01-17
111
112 |  | X |  | Brad to propose new flange wording (Figure 1-3,...1-13 and 1-14) 8mm versus new 8.8; why 8.8 | Brad | Carlisle | 2019-01-17 |  | ON GOING
113 |  | X |  | Ask Honeywell and all A791 suppliers if they are using all KANDU spares; discrete is needed to address possible hazzardous situation (Tx Control Logic as in A792) | Peter and Jose |  | 2019-01-17 |  | See Action 111
114 |  | X |  | Delete A629 Interface (only A429)? | Peter | TotaPort | 2019-01-17
115 |  | X |  | Appendix E - peter to provide new figure and extreme temp | Peter | TotaPort | 2019-01-17
116 |  | X |  | Figure 10-1 (attachment 10) fix size of J2. Make B1 Power Box smaller | Jose | ARINC IA | 2019-01-17
Annapolis KSAT Meeting - 18 June 2019
130 |  |  | X | Schedule next Common Modem WebEx | Peter Lemme and Jose Godoy | Totaport and ARINC IA | 2019-06-18 |  | After July 8th (target 15July)
131 |  |  | X | Review the architecture tradeoffs (4 MCU 100 Watts for Modman) | C. Modem WG | C. Modem WG | 2019-06-18 |  | Tradeoffs
132 |  |  | X | Describe SDR (Software Defined Radio) KSAT requirements | Matt |  | 2019-06-18 |  | Matt to write initial commentary. 5Sept2019: ONGOING
133 |  |  | X | Study feasibility of using LTE modem for gate-to-gate service (when A/C on Gnd not moving) | Antenna and/or Modem Suppliers |  | 2019-06-18 |  | Victor: How is this goal achieved; removes colling antenna requirements at GND Spd = low speed (higher than taxi, ant inop during taxi; enough spd to cool); and extreme temp conditions; potential benefit: smaller and lighter antenna. 5Sept2019: Kenny Kirchoff (Kymeta) volunteered to submit wording since they operate hybridly...
134 |  |  | X | What are maximum radome temperatures (in order to avoid skin damage for different fuselage before any damage). Equipment shutdown or other value that must be considered. Rephrase: at what temp does the skin start to get damaged. | Chris, (John) Michael Reinbold, Dan, Victor | Airframers | 2019-06-18 |  | Chris to provide initial study and discuss/share w/ airframers: Boeing, Mitsubishi and Bombardier…Include Outside Air Temp, wind assumption (i.e., wind, no wind), …worst case - sitting at gate? no due to solid state componenets material). 5Sept2019: Airbus and Boeing had discusions - 25Sept2019: ONGOING - Boeing to provide white paper (see item 177)
135 |  |  |  | Reach out to Gufstream and Embraer for item 134 | Jose | ARINC IA/SAE ITC | 2019-06-18 |  | NO RESPONSE
136 |  |  | X | Do wirng provisions and feedthroughs support necessary cooling solutions not already provided by KPSU to OAE |  |  | 2019-06-18 |  | Ongoing. Current baseline includes no additional penetration, wiring, or power budget is allocated for cooling provisions. Consider adding commententary to Section 10.1 / or revise wording and make body text (requirement) instead of just a commentary. 5Sept2019: No new penetrations - 25Sep2019: work within existing penetrations and wiring pinouts
|  |  |  | Chris to Solicit participation from high power antenna manufacturers | Chris Schaupmann | Airbus | 2019-06-18
137 |  | X | X | What to do with Cutting Power (not on essential Bus) | Chris Schaupmann | Airbus | 2019-06-18 |  | What power is consumed, - power for degraded mode 17Jan2019. Add as a MIB functionality? SEE ITEM 13 ; 24SEPT2019: Airbus - no active plans.
138 |  | X |  | Identify if there is an Attenuators issue (Design issue?) | Eric Cross and Ant Suppliers | Viasat and … | 2019-06-18 |  | In ARINC 791 P2 determined attenuation power is adequate? 1Aug 2018: There are attenuators in the L-Band systems. 17Jan2019: On Going. 18June2019: Add guidance commentary. SEE ITEM 14. 24Sep2019: Ongoing, review A792 power. 25Sep2019: Antenna suppliers to review A791P2, Section 7.1 (System Cascade) . see Item 14 and 200
139 |  |  | X | Is there a fiber feedthrough connector? | Paul Alhf | Carlisle | 2019-06-18 |  | Paul to provide options available in market. 12July2019: Paul, Carlisle, provided a response. 5Sept2019: See Revised Totaport Common Modem white paper.
140 |  |  | X | Modem WG to provide fiber cabling recommendation | C. Modem WG | C. Modem WG | 2019-06-18 |  | Tradeoffs. 5Sept2019: See Revised Totaport Common Modem white paper / ONGOING. See GlenAir presentation confirmed that this technology can be used; direction being discussed. Also Irv (Chesapeake Adv Technologies to present at next meeting?); encouraging. What are the concerns. Coax to Fiber conversion (cost)
141 |  | X |  | Add Airbus security proposal to A791 Part 2 Strawman | Timo, Chris and Jose |  | 2019-06-19 |  | Airbus to provide revised proposal, ARINC IA to add to next draft. Jose to post to sharepoint. 29Oct2019: Airbus to present at the joint session with NIS Subcommittee during Jan 2020 meeting at Viasat (see item 201). 11Feb2020: Dr. Timo Warns submitted prposed wording for Appendix A of ARINC 791P2 strawman; to be reviewed during 12Feb2020 WebEx. 12Feb2020:
142 |  | X |  | Contact SpaceX, TeleSat, VIASAT and Inmarsat. Share Airbus network security proposal. Ref AI 141 | Victor, John, and Jose | Mitsubishi, Boeing and ARINC IA | 2019-06-19 |  | Constellation providers to provide comments. OneWeb(Mark)? 12July2019: Victor advised he had contacted Space X and TeleSat.
143 |  |  |  | Review Security Section in A792; does it reference A791 Part 2 | Jose Godoy | ARINC IA/SAE ITC | 2019-06-19 |  | See ARINC 842. (see items 141 and 201).
144 |  |  |  | Revised fittings proposal (reduce or remove fittings 3/4) - Tradeoffs study | Brad, Matt and Loren | Carlisle, Gogo | 2019-06-19 |  | Look at Aperture Form Factors and how to address. Based on Tradeoff study, determine how to handle (segregate Commercial from RJ or Leo Tech). See Item 180
145 |  | X |  | MIBs: Add mute # 8 = vendor defined (other) | Mark Sorensen | Delta Air Lines | 2019-06-19 |  | Ref Marks email. 29Oct2019: added to A791P2 D1S2 Strawman (on SharePoint)
146 |  | X |  | Review MIBs Section and provide feedback - Brief Subcommittee | Equipment Manufactures and system integrator | Equipment Manufactures and system integrator | 2019-06-19 |  | See Actions 6, 20, 145, 146, 147, 192, 202
147 |  | X |  | Airbus to provide MIBs feedback | Chris Schaupmann | Airbus | 2019-06-19 |  | See 6, 20, 145, 146, 147, 192 and 202. 23Jan2020: To be discussed during 12Feb2020. Chris to submit comments prior to WebEx.
148 |  | X | X | Schedule next KSAT Web Conference | Jose Godoy | ARINC IA/SAE ITC | 2019-06-20
KSAT WebConference - 16 July 2019
150 |  |  |  | Distribute Amazon Leo link |  |  | 2019-07-16
151 |  |  |  | Schedule Common Modem WebEx | Jose Godoy | ARINC IA/SAE ITC | 2019-07-16 |  | September 5th
Send dedicated invite to Peter for distribution
152 |  |  |  | If feasible, invite connector manufacturers to Sept 6th WebEx | Jose Godoy | ARINC IA/SAE ITC | 2019-07-16
153 |  |  |  | Inform the Flight Crew when the ant is shut off due to over temp | Chris | Airbus |  |  | Related to item 134. Consider a MIB object, See 192 and 200
154 |  |  |  | Schedule next Face to Face meeting | Jose Godoy | ARINC IA/SAE ITC | 2019-07-16 |  | SMA Posted; Meeing Sept 24-26, 2019 @ The Boeing Company in Seattle
155 |  |  |  | Jose to announce NIS activities (face to face and WebExes) | Jose Godoy | ARINC IA/SAE ITC | 2019-07-16 |  | Monitor ARINC 848 activity. Last NIS SC meeting June in Hamburg. Subcommittee reviewing inouts to last draft (Draft 7 to ARINC Project Paper 848. Jose added to NIS SC distribution. 02September2019: Next NIS meeting conflicts with KSAT SC meeting (September 24-26, 2019).
KSAT WebConference - 05 September 2019
160 |  |  |  | review updated Common Modem white paper and be ready to discuss at Seattle meeting | KSAT SC | KSAT SC
161 |  |  |  | Array Antenna Thermal Management - Boeing Inquiries |  |  |  |  | See items 134 and 177
170 |  |  |  | Post Supplement 3 to ARINC Characteristic 791 Part 1 | Jose Godoy | ARINC IA/SAE ITC |  |  | Published September 19, 2019
171 |  |  |  | Schedule next Face to Face meeting | Jose Godoy | ARINC IA/SAE ITC
172 |  |  |  | Schedule next Face to Face meeting | Jose Godoy | ARINC IA/SAE ITC
173 |  |  |  | Schedule Common Modem WebEx |  |  |  |  | WebEx on September 25th 8:00 AM PST
174 |  |  |  | Schedule Fiber optics WebEx |  |  |  |  | WebEx on September 26th 8:30 AM PST
Seattle KSAT Meeting - 24-26 Sept, 2019
175 |  |  |  | Present Array Antenna Thermal Management | Chris / Mike | Airbus / Boeing | 2019-09-24
176 |  |  |  | Array Antenna Thermal Management - Boeing White Paper |  |  | 2019-09-24 |  | Review Boeing Inquiry and Comment
177 |  |  |  | Draft Thermal Management Appendix from Airframers perpective (Thermal Mgt / Form Factor SG - now) | Chris and John | Airbus / Boeing | 2019-09-24 |  | See item 134. 29Oct2019: Boeing to provide white paper. See items 134 and 178. 22Jan2020: Add Wording in the main body and an Appendix with guidance. Waiting for Airbus/Boeing to share WhitePaper.
178 |  |  |  | Work with Airframers (review) above Item from systems Suppier perspective | Loren Ayotte | Gogo | 2019-09-24 |  | Related to 134 and 177
179 |  |  |  | Present Updates to Common Modem white paper | Peter Lemme | Totaport
179a |  |  |  | Update and distribute Common Modem paper w/ meeting results | Peter Lemme | Totaport | 2019-09-24
180 |  |  |  | Propose smaller form factor antenna attachment as an option (Form Factor SG - now) | Victor, Gregg, and Jonathan | Mitsubihi, Thinkom, Astronics | 2019-09-24 |  | See 144. Ongoing - Astronics and Victor working together to make proposal/ presentaion at the next face to face meeting. See item 206
181 |  |  |  | Viasat to Present | Eric Cross | Viasat
182 |  |  |  | Review / Discuss Viasat white paper | KSAT SC | KSAT SC | 2019-09-25
183 |  |  |  | Schedule next Common Modem web conference | Jose Godoy | ARINC IA/SAE ITC | 2019-09-25 | 2019-09-26 | Schedule for October 23, 2019; Provide Invite to Peter for distribution
184 |  |  |  | Eric Cross to propose 2 + 1 + 1 Common Modem IF Blk Diagram | Eric Cross | Viasat | 2019-09-25
185 |  |  |  | Create template to satisfy Service Provider requirements solicitation | Eric Cross | Viasat | 2019-09-25 |  | provided on Nov 8, 2019. See 186.
186 |  |  |  | Satellite Service Provider to submit acceptable minimum terminal requirements |  |  |  |  | In support of 185. Viasat to provide. 16April2020: Contact Eric (use what we have received and post)
187 |  |  |  | Viasat to research Coax attenuations given in A792 (Section 4.1.1 Coax IF). See action X. | Chris, Mike and Victor |  |  |  | Taking into account available Coax cables and length (100Ft). 29Oct2019: Boeing - longest runs also in 90+ ft. Ongoing. Ranges (i.e., 4 and 6 Ghz) are not spec'd. See A791P2 …if loss is see action than 11 dBs, add more cable or attenuate? Ideally avoid attenuation...Viasat to propose 3 options
188 |  |  |  | Robert Skuza (ComTech) to update Table in Common Modem | Robert Skuza | ComTech | 2019-09-25
189 |  |  |  | Peter to determine suitability of using celular for passenger | Peter Lemme | Totaport | 2019-09-25 |  | To be reported on during Jan meeting
190 |  |  |  | Review RFoF Presentation | KSAT SC | KSAT SC | 2019-09-25
191 |  |  |  | Adding Cell as a segregated sub network into A791P2 (ARINC 688 will be ref'd) | Peter Lemme | Totaport | 2019-09-25 |  | Carving out the address space to present the internal cell radio. 29Oct2019: To be reported on during Jan meeting
192 |  |  |  | Review MIB Section, improve to make it more implemented. External MIBs | Mike (Lead) | The Boeing Company | 2019-09-25 |  | Solicit proposal. Delta Air Lines wants maintenance (LRU Level) diagnostic. 29Oct2019: See item 202
193 |  |  |  | Correct Figure 1-14 in ARINC 792 | Jose Godoy | ARINC IA/SAE ITC | 2019-09-25
194 |  |  |  | Survey Antenna suppliers for signal characteristics (for Fiber) | Antenna Suppliers | Antenna Suppliers | 2019-09-25
198 |  |  |  | Schedule next web conference | Jose Godoy | ARINC IA/SAE ITC | 2019-09-25 |  | Oct 29th
199 |  |  |  | Schedule next Face to Face meeting | Jose Godoy | ARINC IA/SAE ITC | 2019-09-25 |  | January 21-23, 2019 at Viasat - co-located with NIS. 29Oct2019: Ongoing
KSAT WebConference - 29 October 2019
200 |  |  |  | Viasat to provide attenuation white paper ( see item X) | Eric Cross | Viasat | 2019-11-29 |  | See items 14 and 138
201 |  |  |  | Schedule Joint Security Session with NIS and Timo (Airbus) | Jose, Vanessa, Timo/Chris | ARINC IA and Airbus | 2019-11-29 |  | Morning Session so Airbus can dial in (see item 141)
202 |  |  |  | IMPROVE MIBs, review MIBs Sections, Make more user friendly to allow extensive usage. Suppliers to further popoulate sMIB sections; concentrate on making it an efficient maintenance tool for troubleshooting, LRU level diagnostic/repacement. | Jose Godoy | ARINC IA/SAE ITC | 2019-11-29 |  | Gathered all MIB items: 6, 20, 145, 146, 147, 192 and 202
205 |  |  |  | Schedule next web conference (12Dec2019) | Jose Godoy | ARINC IA/SAE ITC | 2019-11-29 |  | Mark Sorensen to confirm availability
KSAT WebConference - 12 December 2019
206 |  |  |  | Victor and Jonathan to prepare Fiber option proposal for 792 | Victor and Jonathan | Mitsubishi / Astronics | 2019-12-12 |  | 16April20: To be provided at June Virtual meeting (See item 180)
207 |  |  |  | reach out to ViaLight for Fiber presentation at next meeting | Jose Godoy | ARINC IA/SAE ITC | 2019-12-12 |  | No response
208 |  |  |  | Viasat to provide list of Sat Providers to send survey | Eric Cross | Viasat | 2019-12-12
KSAT Meeting at Viasat in Carlsbad - January 21-23, 20202
215 |  |  |  | Resend Satellite Providers Survey | Jose Godoy | ARINC IA/SAE ITC | 2020-01-22
216
217 |  |  |  | Feasibility of adding Amphenol and Radiall size 1 conn to ARINC 600 | Jose Godoy | ARINC IA/SAE ITC | 2020-01-22 |  | Using Size 2
218 |  |  |  | Distribute (KSAT Share Point) 6MCU space availability presentation | Jose Godoy | ARINC IA/SAE ITC | 2020-01-22 |  | Sent on 23Jan2020
219 |  |  |  | Write APIM for new generation Modman - digital interface APIM | KSAT SC | KSAT SC | 2020-01-22
220 |  |  |  | Send APIM Template | Jose | ARINC IA | 2020-01-22
221 |  |  |  | Insert QoS/CoS info from PP848 into ARINC 791P2 | Peter Lemme | Totaport | 2020-01-22 |  | 16April2020: Ongoing
222 |  |  |  | Markus to update Airbus A792-1 fittings 3 and 4 proposal |  |  | 2020-01-22
223 |  |  |  | Add AMU into ARINC 791P2 | Peter Lemme | Totaport | 2020-01-22 |  | Some work has to be done, check if complete. Classic config selected (AMU with Coax and Star Quad).
224 |  |  |  | Arrange Security Conf with Timo Warns, wording into A791P2 Section 5 and Appendix A | Chris Schaupmann | Airbus | 2020-01-22 |  | 11Feb2020: Timo provided security guidance (new wording) for Appendix A
225 |  |  |  | AMIP - revise F command as needed | Eric Cross | Viasat | 2020-01-22 |  | 16April2020: iDirect is revising AMIP. 11Nov2020: Ref AMIP document (remove from Part 2)
226 |  |  |  | Review remote Load (Appendix B of A791P2) | Eric Cross | Viasat | 2020-01-22
227 |  |  |  | Contact iDirect and inquire how AMIP will be controlled, advise of KSAT inputs? | Steve Moses | iDirect | 2020-01-23 |  | 16April2020: iDirect is revising AMIP.
228 |  |  |  | Next Virtual KSAT Face to Face Meeting? |  |  | 2020-01-23 |  | Looking at week of June 15th or 22nd, ongoing
229 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA | 2020-01-23 |  | Scehduled for 12 February 2020
KSAT WebConference - 12 February 2020
230 |  |  |  | Review Timo's Interfaces Security inputrs for A791 P2 | KSAT SC | KSAT SC | 2020-02-12 |  | See 141 and 231
231 |  |  |  | Dr. Timo Warns to submit revised proposed wording | Timo Warns | Airbus | 2020-02-12 |  | Replace AES and GES, add high level wording in section 5 and ref Appendix A
232 |  |  |  | Peter Lemme to add authentication wording? | Peter Lemme | Totaport | 2020-02-12
233 |  |  |  | Revise A792A APIM | KSAT SC | KSAT SC | 2020-02-12
234 |  |  |  | Submit revised APIM Draft to Paul | Jose Godoy | ARINC IA | 2020-02-12
235 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  |  | Schedule for 25March2020
KSAT WebConference - 16 April 2020
236 |  |  |  | Draft Attachment/Appendix with Viasat's & Satellite Survey Response values | Eric Cross | Viasat |  |  | See 186 and 250
237 |  |  |  | Submit APIM 20-001 Final (ARINC 792A multi modem-fiber KSAT System | Jose Godoy | ARINC IA | 2020-04-16
238 |  |  |  | Move to how to use open AMIP (Implementation guidelines) | Steve Moses | iDirect | 2020-04-16
239 |  |  |  | Schedule Next KSAT SC WebConference - 13May2020 | Jose Godoy | ARINC IA | 2020-04-16
KSAT WebConference - 13 May 2020
240 |  |  |  | Schedule next virtual meeting - June 22 thru June 25 (3-4 Hrs each day | Jose Godoy | ARINC IA | 2020-05-13 |  | SMA Availabe
241 |  |  |  | Update AMUpresentation with webex conference results | Peter Lemme | TOTAPORT | 2020-05-13
242 |  |  |  | AMU: which Modes will be supported | KSAT SC | KSAT SC | 2020-05-13 |  | 24June2020: See TOTAPORT Presentation (v8)
243 |  |  |  | Based on AMU Modes to be supported, are wiring changes required | KSAT SC | KSAT SC | 2020-05-13
244 |  |  |  | Ask Eric to populate the Sat Antenna Characteristics using what we have | Jose Godoy | ARINC IA | 2020-05-13
245 |  |  |  | Eric (viasat) to populate new Sat Provider interoperability attachment in A791P2 S2D1 | Eric Cross | Viasat | 2020-05-13 |  | See item 250
246 |  |  |  | Highlight Differences between Ka-bnd and Ku-Band characteristics | KSAT SC | KSAT SC | 2020-05-13
247 |  |  |  | Consider including an Avionics Data Acquisition function in ARINC KSAT Standards | KSAT SC | KSAT SC | 2020-05-13 |  | Related to ARINC 834A (Aircraft Data Broadcast) project
248 |  |  |  | Schedule Next KSAT SC WebConference - 10June2020 | Jose Godoy | ARINC IA | 2020-05-13
KSAT WebConference - 10 June 2020
250 |  |  |  | Make Satellite Provider Recommendations for InterOp decision (Appendix format) |  |  |  |  | Compare Viasat, eutelsat and SES Characteristics, 23June2020: Viasat provided Sat Provider inputs throughout body of doc
251 |  |  |  | Draft Virtual Meeting Agenda
252 |  |  |  | Review Items required for release of Supplement 2 to ARINC 791 Part 2 Draft 1
KSAT Virtual Meeting: June 23, 2020
255 |  |  |  | Review Inuts to Supplement 2 to ARINC 791 Part 2
256 |  |  |  | Should A771 (Iridium) and 741/761 (L-Band) Satcom be added to list of ref Docs | Jose
257 |  |  |  | Review Section 2.2 wording - Satcom System Interfaces/Channels
258 |  |  |  | Section 2.2 Figures 2-4, 2-6, 2-8: add ARINC 848 MISON | Peter Lemme | TOTAPORT
159 |  |  |  | Show Router Domain to Figure 2-9 (Etherner Domain Schematic
260 |  |  |  | Review new Elevation beamwidth characteristics (Section 2.8,1)
261 |  |  |  | Review VIASAT Sat provider Survey Inputs
262 |  |  |  | Are eutelsat and SES recommendations included | Jose and Gary
263 |  |  |  | Section 2.82 (Consider Renaming and add Ka characteristics
264 |  |  |  | Section 2.82 - Review Ka/Ku band dBW/MHz peak EIRP values
265 |  |  |  | Section 2.8.3 Polarization - use 10 or 100 millisec switching time | Viasat |  |  |  | Ask LEO Suppliers. Also add Ku Staement?. Viasat to consult with other providers
266 |  |  |  | SECTION 3.8 - Review Second/Maintenance Channel System wording |  |  |  |  | Change Channel to System
267 |  |  |  | Section 4.3: Need to decide on the GbE interface to the AMU for 791
268 |  |  |  | Section 4.5.1 and 4.5.3 - review / add IPv6 info | Jose |  |  |  | Consult with NIS
269 |  |  |  | Section 7.1: Review Viasat inputs and should Ku Band equivelant info be added? | KSAT SC
270 |  |  |  | Section 7.1: Review proposed Note 4 |  |  |  |  | reworded
271 |  |  |  | Section 7.3.1 - Ref Frequecies: Reconsile with AMU
272 |  |  |  | Table 7-5: Review new Table Values (Collins Proposal?)
273 |  |  |  | Table 7-7: Review Table Values (Under review?) |  |  |  |  | IF Signal Additional Characteristics – Tx
274 |  |  |  | Section 7.4.7 Ant SubSys Lo Freq - use 10 or 100 millisec switching time
275 |  |  |  | Table 7-9: Review Table Values (Under review?)
276
277 |  |  |  | Review Section 11 - QoS | Jose |  |  |  | Jose to implement initial compare for draft 2
278 |  |  |  | Fiber Optics Presentation
279 |  |  |  | Action Item based on Kontron AMU white paper - Ack | Jose |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified
280 |  |  |  | Do we need to provision to an additional AMU discrete, define In or Out is required? |  |  |  |  | KSAT SC decided
281 |  |  |  | assess, then to revise AMU presentation - wiring between AMU and Modman does not change. Provision for only 2 AMUs |  |  |  |  | Provision for only 2 AMUs. New discrete will be labled Man Specifiic. How many pins are affordable
282 |  |  |  | Kontron connector, specify as alternate? |  |  |  |  | Subcommittee/ Kintron to decide
283 |  |  |  | Should a connector with fiber be added to Kontron FormFactor, add fiber to existing middle plug? |  |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
284 |  |  |  | Discuss existing Kontron and Hughes ARINC 600 Connectors further |  |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
285 |  |  |  | Mitsubishi Comment: Review Power over Ethernet feasibility - High Voltage ? GEO issue?
286 |  |  |  | Comments on Mitsubishi proposal GPS at the Gate/MEO issue (no HDG) ?
287 |  |  |  | Brad Purpus - Carlisle to provide alternate sealant (feedthru cableing) presentation |  |  |  |  | fusalege penetration solution (to support Fiber Feedthru). Depending on availability. 19July2020: Provided compression fittings white paper on 18July2020.
288 |  |  |  | Michael - Boeing to provide alternate sealant (feedthru cableing) presentation |  |  |  |  | If feasible for July 22nd conf
289 |  |  |  | A791P2 Section 6 - Josh (Honeywell) to propose wording
290 |  |  |  | Schedule next Conference Call - July 22nd at 11:00 AM EST USA
291 |  |  |  | ADD MIB to next meeting/web conf agenda
292 |  |  |  | Thermal Management - Create Subgroup led by airframers. Subgroup to brief Subcommittee | Markus Altmann and Michael Reinbold | Airbus and Boeing |  |  | Contact Markus, Lead to be added to subgroup
293 |  |  |  | Schedule Next KSAT SC WebConference - 22July2020 | Jose Godoy | ARINC IA | 2020-07-02
KSAT WebConference - 22July2020
295 |  |  |  | Review and Comments on Carlisle Pass through presentation | KSAT SC | KSAT SC |  |  | Compression pass throughs white paper
296 |  |  |  | Carlisle to provide pertinent leakage information | Brad | Carlisle
297 |  |  |  | Create feedthrough requirements that supports multiple cable types (fiber, coax, cooper)
298 |  |  |  | Standardize passthrough method | KSAT SC | KSAT SC |  |  | Define hole/s location/diameter, drill pattern, doubler needed?
299 |  |  |  | Schedule Thermal/Form Factor Subgroup Web Conferenece | Markus Altmann | Airbus
300 |  |  |  | Contact Smitty (coordination with Fiber Connector Subcommittees/working group) | Jose Godoy | ARINC IA |  |  | Initial contact made; presentation shared
302 |  |  |  | Schedule Next KSAT SC WebConference - 2Sept2020 | Jose Godoy | ARINC IA
KSAT WebConference - 2Sept2020
303 |  |  |  | Review posted Draft 1 of Supplement 2 to ARINC Characteristic 791, Part 2 | KSAT SC | KSAT SC
304 |  |  |  | Decision on AMU Connectors Cavity A, B and C |  |  |  |  | Decide on Oct 7th meeting?
205 |  |  |  | Thermal/Form Factor Meeting |  |  |  |  | Next Subgroup Meeting held 9Sept 2020
306 |  |  |  | Decide -792 in 791P2 or (new 792 Part 2 needed) |  |  |  |  | Arrange meeting with AEEC Exec Director
309 |  |  |  | Schedule Next KSAT SC WebConference - 7Oct2020 | Jose Godoy | ARINC IA
KSAT WebConference - 7Oct2020
310 |  |  |  | Report on Sept 9th Subgroup Meeting Meeting
311 |  |  |  | Present and Review Kontron white paper update
312 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  |  | Next Web Meeting 11Nov2020
KSAT WebConference - 11Nov2020
320 |  |  |  | Update APIM 16-006A
321 |  |  |  | Chris Schaupmann (Airbus) to provide initial Fiber Connection Requirements white paper | Chris Schaupmann | Airbus
322 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA
323 |  |  |  | Coordinate with FOS and CSS | Jose and Smitty | ARINC IA |  |  | 3Dec2020: Ongoing See item
324 |  |  |  | Schedule Next KSAT Vitual Meetig | Jose Godoy | ARINC IA |  |  | Meetings Dec 2-3, 2020 and 5-6Jan2021
325 |  |  |  | Carlile to submit white paper for next thermal subgroup meeting
KSAT Virtual Meeting - December 2-3, 2020
330 |  |  |  | Victor to contact Markus/Subgroup and identify issue (jose send email to parties)
331 |  |  |  | Peter to provide updates to A791P2 (Josh, Anh, and Matt to assist)
332 |  |  |  | Loren to provide A792 strawman (AMU material)
333 |  |  |  | Jose to add other inputs (i.e., Viasat) to A791P2 Strawman after Peter makes it available
334 |  |  |  | Work with Fiber group, identify requirements / maybe APIM
335 |  |  |  | Chris to update Fiber presentation (see 321)
336 |  |  |  | What AMU Modes to be supported, are wiring changes required (see 242, 243)
337 |  |  |  | ARINC 629 is being removed
338 |  |  |  | Submit APIM 16-006A (see item 320)
339 |  |  |  | Boeing, Matt Landel (astronics) and Airbus will further develop MIB section
340 |  |  |  | Draft agenda for Jan 5-6, 2021
341 |  |  |  | Update KSAT SharePoint with meeting white papers and presentations (e.g., Mitsubitshi fittings)
342 |  |  |  | Add KSAT SharePoint folders for Action Items, Fiber, AMU, etc
343 |  |  |  | Schedule Next KSAT SC Teams Meetings (Jan 5 and 6, 2021)
344 |  |  |  | Develop Draft 2 of Supplement 2 to ARINC Characteristic 791 Part 2
345 |  |  |  | Update APIM 16-006A
346 |  |  |  | Standardize passthrough method (see item 298)
347 |  |  |  | Create feedthrough requirements; supports multiple cable types (fiber, coax, cooper) see item 297
348 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 5, 2021 (Day 1 of 2) | Jose Godoy | ARINC IA / SAE ITC
KSAT Virtual Meeting - January 5-6, 2021
350 |  |  |  | Thermal and Form Factor SuGroup to provide briefing to KSAT Subcommittee
351 |  |  |  | Review A791P2 strawman - develop Draft 2
352 |  |  |  | Review A792-1 Draft 1
353
354 |  |  |  | Submit revised A791P2-2 APIM to SAI
355 |  |  |  | Submit ARINC 791 P2 D2 S2
356 |  |  |  | Submit ARINC 792 D1 S1
357 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 22, 2021
FOS Kickoff Meeting - February 9, 2021
360 |  |  |  | FOS to develop quentionaire
361 |  |  |  | KSAT will use FOS questionaire to generate requirements list for FOS recommendations
362 |  |  |  | Schedule Next KSAT Vitual Meeting - March 3, 2021
KSAT Conference - March 3, 2021
364 |  |  |  | Expand FO requirements list for FOS | Subcommittee | Subcommittee |  |  | e.g., list signal type
365 |  |  |  | Schedule Next KSAT AMU Confernece - April 7, 2021 |  |  |  |  | Changed from March 31st due to conflict with Thermo Management / Form Factor
KSAT at IPS Sucommittee Meeting - March 18, 2021
367 |  |  |  | Review Honeywell Inputs to APIM 16-006A | KSAT Subcommittee | KSAT Subcommittee
368 |  |  |  | Complere APIM (revise or leave as is) | KSAT Subcommittee | KSAT Subcommittee
FOS Meeting - March 24, 2021
370 |  |  |  | Expand FOS/KSAT Matrix |  |  |  |  | See item # 375
371 |  |  |  | Label each of the 26 connections and describe (Ethernet/RF, Freq/Speed, # of disconnects, type) | KSAT Subcommittee | KSAT Subcommittee |  |  | worst case length from pr
372 |  |  |  | Provide Link Budget, include in requirements matrix for FOS
373 |  |  |  | Distribute KSAT / Fiber Requirements Matrix | Jose and Smitty | ARINC IA/SAE ITC
KSAT Conference - April 7, 2021
375 |  |  |  | Expand FO requirements list for FOS | FOS & KSAT | FOS & KSAT
376
377
378
379
380 |  |  |  | Schedule Next KSAT Online Conference
381 |  |  |  | Schedule Next KSAT Virtual Meeting (multi-Day)

## Sheet2
Number | ISSUE | Responsible | Company | Date Opened | Due Date | Comments
1 | Security / Domain Segregation | Iridium Source / AGCS Subcommittee |  |  |  | Cooperation with NIS and RTCA SC-216. e for A781 Inmarsat set up guidance from subgroups (e.g., Airframers and others)
2 | Data Priority / Pre-emption (QoS) Domains | AGCS Committee |  |  |  | Based on Iridium NEXT network defined capabilities
3 | Data Priority / Pre-emption (QoS) Time Sensitive Apps | AGCS Committee |  |  |  | Based on Iridium NEXT network defined capabilities
4 | GNSS Filtering (how much Cable loss is allowed 3dBs?) | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
5 | Out of Iridium Band Filtering | Iridium |  |  |  | How do systems coexist non sumltaneously (Inmarsat/Iridium/other) | Iridium to have independent conference with Avionica and report to Subcommittee
6 | Will ARINC 771 embrase existing short burst data services | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
7 | Will ARINC 771 embrase existing circuit switch services | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
8 | Architecture Selection - narrow down five configurations | Iridium |  |  |  | Airbus: Agree on one configuration for LGA and one for the MGA | Iridium to propose on how to clasify each configuration
9 | Antenna Footprint | Iridium/Cobham / AGCS Subcommittee
Airbus to provide revised proposal, ARINC IA to add to next draft. Jose to post to sharepoint. 29Oct2019: Airbus to present at the joint session with NIS Subcommittee during Jan 2020 meeting at Viasat (see item 201). 11Feb2020: Dr. Timo Warns submitted prposed wording for Appendix A of ARINC 791P2 strawman; to be reviewed during 12Feb2020 WebEx. 12Feb2020:
See 6, 20, 145, 146, 147, 192 and 202. 23Jan2020: To be discussed during 12Feb2020. Chris to submit comments prior to WebEx.
[5 empty] | Chris | Airbus
|  |  |  | Draft Thermal Management Appendix from Airframers perpective (Thermal Mgt / Form Factor SG - now) |  |  |  | See item 134. 29Oct2019: Boeing to provide white paper. See items 134 and 178. 22Jan2020: Add Wording in the main body and an Appendix with guidance. Waiting for Airbus/Boeing to share WhitePaper.
|  |  |  | Propose smaller form factor antenna attachment as an option (Form Factor SG - now) |  |  |  | See 144. Ongoing - Astronics and Victor working together to make proposal/ presentaion at the next face to face meeting. See item 206
In support of 185. Viasat to provide. 16April2020: Contact Eric (use what we have received and post)
|  |  |  | Viasat to research Coax attenuations given in A792 (Section 4.1.1 Coax IF). See action X. |  |  |  | Taking into account available Coax cables and length (100Ft). 29Oct2019: Boeing - longest runs also in 90+ ft. Ongoing. Ranges (i.e., 4 and 6 Ghz) are not spec'd. See A791P2 …if loss is see action than 11 dBs, add more cable or attenuate? Ideally avoid attenuation...Viasat to propose 3 options
Adding Cell as a segregated sub network into A791P2 (ARINC 688 will be ref'd)
Solicit proposal. Delta Air Lines wants maintenance (LRU Level) diagnostic. 29Oct2019: See item 202
16April20: To be provided at June Virtual meeting (See item 180)
No response
215 |  |  |  | Resend Satellite Providers Survey
216
217 | [7 empty] | Using Size 2
218 | [7 empty] | Sent on 23Jan2020
219 |  |  |  |  | KSAT SC | KSAT SC
220 | [5 empty] | ARINC IA
221 | [5 empty] | Totaport |  | 16April2020: Ongoing
222 |  |  |  | Markus to update Airbus A792-1 fittings 3 and 4 proposal
223 |  |  |  |  | Peter Lemme | Totaport |  | Some work has to be done, check if complete. Classic config selected (AMU with Coax and Star Quad).
224 |  |  |  | Arrange Security Conf with Timo Warns, wording into A791P2 Section 5 and Appendix A |  | Airbus |  | 11Feb2020: Timo provided security guidance (new wording) for Appendix A
225 | [5 empty] | Viasat |  | 16April2020: iDirect is revising AMIP. 11Nov2020: Ref AMIP document (remove from Part 2)
226 |  |  |  | Review remote Load (Appendix B of A791P2) |  | Viasat
227 |  |  |  | Contact iDirect and inquire how AMIP will be controlled, advise of KSAT inputs? | Steve Moses | iDirect | 2020-01-23 | 16April2020: iDirect is revising AMIP.
228 |  |  |  | Next Virtual KSAT Face to Face Meeting? |  |  | 2020-01-23 | Looking at week of June 15th or 22nd, ongoing
229 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA | 2020-01-23 | Scehduled for 12 February 2020
KSAT WebConference - 12 February 2020
230 |  |  |  | Review Timo's Interfaces Security inputrs for A791 P2 | KSAT SC | KSAT SC | 2020-02-12 | See 141 and 231
231 |  |  |  | Dr. Timo Warns to submit revised proposed wording | Timo Warns | Airbus | 2020-02-12 | Replace AES and GES, add high level wording in section 5 and ref Appendix A
232 |  |  |  | Peter Lemme to add authentication wording? | Peter Lemme | Totaport | 2020-02-12
233 |  |  |  | Revise A792A APIM | KSAT SC | KSAT SC | 2020-02-12
234 |  |  |  | Submit revised APIM Draft to Paul | Jose Godoy | ARINC IA | 2020-02-12
235 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  | Schedule for 25March2020
KSAT WebConference - 16 April 2020
236 |  |  |  | Draft Attachment/Appendix with Viasat's & Satellite Survey Response values | Eric Cross | Viasat |  | See 186 and 250
237 |  |  |  | Submit APIM 20-001 Final (ARINC 792A multi modem-fiber KSAT System | Jose Godoy | ARINC IA | 2020-04-16
238 |  |  |  | Move to how to use open AMIP (Implementation guidelines) | Steve Moses | iDirect | 2020-04-16
239 |  |  |  | Schedule Next KSAT SC WebConference - 13May2020 | Jose Godoy | ARINC IA | 2020-04-16
KSAT WebConference - 13 May 2020
240 |  |  |  | Schedule next virtual meeting - June 22 thru June 25 (3-4 Hrs each day | Jose Godoy | ARINC IA | 2020-05-13 | SMA Availabe
241 |  |  |  | Update AMUpresentation with webex conference results | Peter Lemme | TOTAPORT | 2020-05-13
242 |  |  |  | AMU: which Modes will be supported | KSAT SC | KSAT SC | 2020-05-13 | 24June2020: See TOTAPORT Presentation (v8)
243 |  |  |  | Based on AMU Modes to be supported, are wiring changes required | KSAT SC | KSAT SC | 2020-05-13
244 |  |  |  | Ask Eric to populate the Sat Antenna Characteristics using what we have | Jose Godoy | ARINC IA | 2020-05-13
245 |  |  |  | Eric (viasat) to populate new Sat Provider interoperability attachment in A791P2 S2D1 | Eric Cross | Viasat | 2020-05-13 | See item 250
246 |  |  |  | Highlight Differences between Ka-bnd and Ku-Band characteristics | KSAT SC | KSAT SC | 2020-05-13
247 |  |  |  | Consider including an Avionics Data Acquisition function in ARINC KSAT Standards | KSAT SC | KSAT SC | 2020-05-13 | Related to ARINC 834A (Aircraft Data Broadcast) project
248 |  |  |  | Schedule Next KSAT SC WebConference - 10June2020 | Jose Godoy | ARINC IA | 2020-05-13
KSAT WebConference - 10 June 2020
250 |  |  |  | Make Satellite Provider Recommendations for InterOp decision (Appendix format) |  |  |  | Compare Viasat, eutelsat and SES Characteristics, 23June2020: Viasat provided Sat Provider inputs throughout body of doc
251 |  |  |  | Draft Virtual Meeting Agenda
252 |  |  |  | Review Items required for release of Supplement 2 to ARINC 791 Part 2 Draft 1
KSAT Virtual Meeting: June 23, 2020
255 |  |  |  | Review Inuts to Supplement 2 to ARINC 791 Part 2
256 |  |  |  | Should A771 (Iridium) and 741/761 (L-Band) Satcom be added to list of ref Docs | Jose
257 |  |  |  | Review Section 2.2 wording - Satcom System Interfaces/Channels
258 |  |  |  | Section 2.2 Figures 2-4, 2-6, 2-8: add ARINC 848 MISON | Peter Lemme | TOTAPORT
159 |  |  |  | Show Router Domain to Figure 2-9 (Etherner Domain Schematic
260 |  |  |  | Review new Elevation beamwidth characteristics (Section 2.8,1)
261 |  |  |  | Review VIASAT Sat provider Survey Inputs
262 |  |  |  | Are eutelsat and SES recommendations included | Jose and Gary
263 |  |  |  | Section 2.82 (Consider Renaming and add Ka characteristics
264 |  |  |  | Section 2.82 - Review Ka/Ku band dBW/MHz peak EIRP values
265 |  |  |  | Section 2.8.3 Polarization - use 10 or 100 millisec switching time | Viasat |  |  | Ask LEO Suppliers. Also add Ku Staement?. Viasat to consult with other providers
266 |  |  |  | SECTION 3.8 - Review Second/Maintenance Channel System wording |  |  |  | Change Channel to System
267 |  |  |  | Section 4.3: Need to decide on the GbE interface to the AMU for 791
268 |  |  |  | Section 4.5.1 and 4.5.3 - review / add IPv6 info | Jose |  |  | Consult with NIS
269 |  |  |  | Section 7.1: Review Viasat inputs and should Ku Band equivelant info be added? | KSAT SC
270 |  |  |  | Section 7.1: Review proposed Note 4 |  |  |  | reworded
271 |  |  |  | Section 7.3.1 - Ref Frequecies: Reconsile with AMU
272 |  |  |  | Table 7-5: Review new Table Values (Collins Proposal?)
273 |  |  |  | Table 7-7: Review Table Values (Under review?) |  |  |  | IF Signal Additional Characteristics – Tx
274 |  |  |  | Section 7.4.7 Ant SubSys Lo Freq - use 10 or 100 millisec switching time
275 |  |  |  | Table 7-9: Review Table Values (Under review?)
276
277 |  |  |  | Review Section 11 - QoS | Jose |  |  | Jose to implement initial compare for draft 2
278 |  |  |  | Fiber Optics Presentation
279 |  |  |  | Action Item based on Kontron AMU white paper - Ack | Jose |  |  | Jose to advise Kontron that existing AMU v8 will be specified
280 |  |  |  | Do we need to provision to an additional AMU discrete, define In or Out is required? |  |  |  | KSAT SC decided
281 |  |  |  | assess, then to revise AMU presentation - wiring between AMU and Modman does not change. Provision for only 2 AMUs |  |  |  | Provision for only 2 AMUs. New discrete will be labled Man Specifiic. How many pins are affordable
282 |  |  |  | Kontron connector, specify as alternate? |  |  |  | Subcommittee/ Kintron to decide
283 |  |  |  | Should a connector with fiber be added to Kontron FormFactor, add fiber to existing middle plug? |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
284 |  |  |  | Discuss existing Kontron and Hughes ARINC 600 Connectors further |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
285 |  |  |  | Mitsubishi Comment: Review Power over Ethernet feasibility - High Voltage ? GEO issue?
286 |  |  |  | Comments on Mitsubishi proposal GPS at the Gate/MEO issue (no HDG) ?
287 |  |  |  | Brad Purpus - Carlisle to provide alternate sealant (feedthru cableing) presentation |  |  |  | fusalege penetration solution (to support Fiber Feedthru). Depending on availability. 19July2020: Provided compression fittings white paper on 18July2020.
288 |  |  |  | Michael - Boeing to provide alternate sealant (feedthru cableing) presentation |  |  |  | If feasible for July 22nd conf
289 |  |  |  | A791P2 Section 6 - Josh (Honeywell) to propose wording
290 |  |  |  | Schedule next Conference Call - July 22nd at 11:00 AM EST USA
291 |  |  |  | ADD MIB to next meeting/web conf agenda
292 |  |  |  | Thermal Management - Create Subgroup led by airframers. Subgroup to brief Subcommittee | Markus Altmann and Michael Reinbold | Airbus and Boeing |  | Contact Markus, Lead to be added to subgroup
293 |  |  |  | Schedule Next KSAT SC WebConference - 22July2020 | Jose Godoy | ARINC IA | 2020-07-02
KSAT WebConference - 22July2020
295 |  |  |  | Review and Comments on Carlisle Pass through presentation | KSAT SC | KSAT SC |  | Compression pass throughs white paper
296 |  |  |  | Carlisle to provide pertinent leakage information | Brad | Carlisle
297 |  |  |  | Create feedthrough requirements that supports multiple cable types (fiber, coax, cooper)
298 |  |  |  | Standardize passthrough method | KSAT SC | KSAT SC |  | Define hole/s location/diameter, drill pattern, doubler needed?
299 |  |  |  | Schedule Thermal/Form Factor Subgroup Web Conferenece | Markus Altmann | Airbus
300 |  |  |  | Contact Smitty (coordination with Fiber Connector Subcommittees/working group) | Jose Godoy | ARINC IA |  | Initial contact made; presentation shared
302 |  |  |  | Schedule Next KSAT SC WebConference - 2Sept2020 | Jose Godoy | ARINC IA
KSAT WebConference - 2Sept2020
303 |  |  |  | Review posted Draft 1 of Supplement 2 to ARINC Characteristic 791, Part 2 | KSAT SC | KSAT SC
304 |  |  |  | Decision on AMU Connectors Cavity A, B and C |  |  |  | Decide on Oct 7th meeting?
205 |  |  |  | Thermal/Form Factor Meeting |  |  |  | Next Subgroup Meeting held 9Sept 2020
306 |  |  |  | Decide -792 in 791P2 or (new 792 Part 2 needed) |  |  |  | Arrange meeting with AEEC Exec Director
309 |  |  |  | Schedule Next KSAT SC WebConference - 7Oct2020 | Jose Godoy | ARINC IA
KSAT WebConference - 7Oct2020
310 |  |  |  | Report on Sept 9th Subgroup Meeting Meeting
311 |  |  |  | Present and Review Kontron white paper update
312 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  | Next Web Meeting 11Nov2020
KSAT WebConference - 11Nov2020
320 |  |  |  | Update APIM 16-006A
321 |  |  |  | Chris Schaupmann (Airbus) to provide initial Fiber Connection Requirements white paper | Chris Schaupmann | Airbus
322 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA
323 |  |  |  | Coordinate with FOS and CSS | Jose and Smitty | ARINC IA |  | 3Dec2020: Ongoing See item
324 |  |  |  | Schedule Next KSAT Vitual Meetig | Jose Godoy | ARINC IA |  | Meetings Dec 2-3, 2020 and 5-6Jan2021
325 |  |  |  | Carlile to submit white paper for next thermal subgroup meeting
KSAT Virtual Meeting - December 2-3, 2020
330 |  |  |  | Victor to contact Markus/Subgroup and identify issue (jose send email to parties)
331 |  |  |  | Peter to provide updates to A791P2 (Josh, Anh, and Matt to assist)
332 |  |  |  | Loren to provide A792 strawman (AMU material)
333 |  |  |  | Jose to add other inputs (i.e., Viasat) to A791P2 Strawman after Peter makes it available
334 |  |  |  | Work with Fiber group, identify requirements / maybe APIM
335 |  |  |  | Chris to update Fiber presentation (see 321)
336 |  |  |  | What AMU Modes to be supported, are wiring changes required (see 242, 243)
337 |  |  |  | ARINC 629 is being removed
338 |  |  |  | Submit APIM 16-006A (see item 320)
339 |  |  |  | Boeing, Matt Landel (astronics) and Airbus will further develop MIB section
340 |  |  |  | Draft agenda for Jan 5-6, 2021
341 |  |  |  | Update KSAT SharePoint with meeting white papers and presentations (e.g., Mitsubitshi fittings)
342 |  |  |  | Add KSAT SharePoint folders for Action Items, Fiber, AMU, etc
343 |  |  |  | Schedule Next KSAT SC Teams Meetings (Jan 5 and 6, 2021)
344 |  |  |  | Develop Draft 2 of Supplement 2 to ARINC Characteristic 791 Part 2
345 |  |  |  | Update APIM 16-006A
346 |  |  |  | Standardize passthrough method (see item 298)
347 |  |  |  | Create feedthrough requirements; supports multiple cable types (fiber, coax, cooper) see item 297
348 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 5, 2021 (Day 1 of 2) | Jose Godoy | ARINC IA / SAE ITC
KSAT Virtual Meeting - January 5-6, 2021
350 |  |  |  | Thermal and Form Factor SuGroup to provide briefing to KSAT Subcommittee
351 |  |  |  | Review A791P2 strawman - develop Draft 2
352 |  |  |  | Review A792-1 Draft 1
353
354 |  |  |  | Submit revised A791P2-2 APIM to SAI
355 |  |  |  | Submit ARINC 791 P2 D2 S2
356 |  |  |  | Submit ARINC 792 D1 S1
357 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 22, 2021
FOS Kickoff Meeting - February 9, 2021
360 |  |  |  | FOS to develop quentionaire
361 |  |  |  | KSAT will use FOS questionaire to generate requirements list for FOS recommendations
362 |  |  |  | Schedule Next KSAT Vitual Meeting - March 3, 2021
KSAT Conference - March 3, 2021
364 |  |  |  | Expand FO requirements list for FOS | Subcommittee | Subcommittee |  | e.g., list signal type
365 |  |  |  | Schedule Next KSAT AMU Confernece - April 7, 2021 |  |  |  | Changed from March 31st due to conflict with Thermo Management / Form Factor
KSAT at IPS Sucommittee Meeting - March 18, 2021
367 |  |  |  | Review Honeywell Inputs to APIM 16-006A | KSAT Subcommittee | KSAT Subcommittee
368 |  |  |  | Complere APIM (revise or leave as is) | KSAT Subcommittee | KSAT Subcommittee
FOS Meeting - March 24, 2021
370 |  |  |  | Expand FOS/KSAT Matrix |  |  |  | See item # 375
371 |  |  |  | Label each of the 26 connections and describe (Ethernet/RF, Freq/Speed, # of disconnects, type) | KSAT Subcommittee | KSAT Subcommittee |  | worst case length from pr
372 |  |  |  | Provide Link Budget, include in requirements matrix for FOS
373 |  |  |  | Distribute KSAT / Fiber Requirements Matrix | Jose and Smitty | ARINC IA/SAE ITC
KSAT Conference - April 7, 2021
375 |  |  |  | Expand FO requirements list for FOS | FOS & KSAT | FOS & KSAT
376
377
378
379
380 |  |  |  | Schedule Next KSAT Online Conference
381 |  |  |  | Schedule Next KSAT Virtual Meeting (multi-Day)

## Compatibility Report
Compatibility Report for AGCS SC_Action Items _ 20Aug2017.xls
Run on 8/21/2017 21:25
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 3 | Excel 97-2003