## Sheet1
Action Item | ARINC 791 P1 | ARINC 791 P2 | ARINC 792/A | Description | Responsible | Company | Date Opened | Due Date | Comments
1 | X |  |  | Review D1S3 to ARINC 791 P1 prior to next Web conference | KSAT Subcommittee | ALL | 2018-05-08 | 2018-06-14 | Draft 1 is in the AEEC AGCS SC SharePoint. Will be discussed during the June 14th conference call. See Item 15
2 | X | X | X | On AGCS SharePoint Create meeting directory under Libraries | Jose Godoy | ARINC IA / SAE ITC | 2018-05-08 |  | Completed
3 | X |  |  | Schedule 14June Conference Call | Jose Godoy | ARINC IA / SAE ITC | 2018-05-08 |  | Completed
4 | X |  |  | Accept Changes for A791P1 D1S3 | KSAT Subcommittee | ALL | 2018-05-08
5 | X |  |  | Post A791 D1S3 | Jose Godoy | ARINC IA / SAE ITC | 2018-05-08 |  | See Item 75
6 | X |  |  | Name a MIBs Section Editor | KSAT Subcommittee | ALL | 2018-05-08 |  | 1Aug2018: Mark to contact GoGo, they may be the MIBs editor. See item 20. 18Dec2018 - Possible Airbus person (Chris to confirm). See 6, 20, 145, 146, 147, 192 and item 202
14June2018 - Web Conference
7 |  |  |  | Reach out to (Domingo) Embraer for tail Mount Ant info | Peter Lemme | Totaport | 2018-06-14 | 2018-07-18 | Domingo Barbosa
8 | X |  |  | Provide strawman source document to Victor | Jose Godoy | ARINC IA / SAE ITC | 2018-06-14 | 2018-06-15 | Completed
9 |  |  |  | Victor to revise A791 P1 TMA Section add to new Attachment | Victor Gheorghian | Bombardier | 2018-06-14 |  | 1Aug2018: Target next web Conference
10 | X |  | X | Expand DeIcing Section (RTCA DO-160) on Radome | Mark Sorensen | Delta | 2018-06-14 |  | Include penetration info/spaying; DO-160 not adequate (to 792 in future). Add as commentary. Inputs welcomed. target July 18th. 1Aug 2018: Do not have the same environmental requirements, Antenna should be tested on its own for susceptibility - On Going (add supplementary test). 18Dec2018: On Going to be discussed at next meeting.
11 | X |  | X | Advise RTCA that DO-160 need revision to address Ant DeIcing | Mark Sorensen | Delta | 2018-06-14 | 2018-07-18 | Contact Brad Green (Section 10 (Waterproofness) and/or Section 11 (Fluids susceptibility). 1Aug 2018: On Going (See item 10). On Going (add supplementary test). 18Dec2018: On Going to be discussed at next meeting.
12 |  |  |  | What to do with Fiber (replace Coax Cables?) | Chris Schaupmann | Airbus | 2018-06-14 | 2018-07-18
13 |  | X | X | What to do with Cutting Power (not on essential Bus) | Chris Schaupmann | Airbus | 2018-06-14 |  | What power is consumed, - power for degraded mode 17Jan2019: Add A/C Input Pwr Magt to A792-1 APIIM
14 | X | X |  | Identify if there is an Attenuators issue (Design issue?) | Chris and Mark | Airbus and Delta Air Lines | 2018-06-14 |  | In ARINC 791 P2 determined attenuation power is adequate? 1Aug 2018: There are attenuators in the L-Band systems. 29Oct2019 - Waiting on Viasat analysis See items 138 and 200
15 | X |  |  | Review D1S3 to ARINC 791 P1 prior to next Web conference | KSAT Subcommittee | ALL | 2018-06-14 | 2018-07-18 | Draft 1 is in the AEEC AGCS SC SharePoint. Will be discussed during the next conference call. See Item 1
16 |  |  |  | Ad Hoc working group to develop common form factor and edge connector for MODEM (component of MODMAN) | Peter Lemme and Gary | Totaport | 2018-06-14 | 2018-07-18 | Isotropic Systems
17 | X | X | X | Schedule next Conference Call | Jose Godoy | ARINC IA / SAE ITC | 2018-07-18 |  | Schedule for July 18
18 | X | X | X | Schedule next Conference Call | Jose Godoy | ARINC IA / SAE ITC | 2018-07-18 |  | 2018-08-01
1 August 2018 - Web Conference
19 |  |  |  | Consider adding radome disturbance cautionary note |  |  | 2018-08-01 |  | 18Dec2018: review inputs if submitted
20 |  | X |  | Update MIB Section? | Mark Sorensen | Delta | 2018-08-01 |  | 1Aug2018: Mark to contact GoGo, they may be the MIBs editor. 18Dec2018 - Possible Airbus person (Chris to confirm). 29Oct2019: See Action 6, 20, 145, 146, 147, 192, and 202
21 | X | X | X | Work on the next meeting | Jose Godoy | ARINC IA / SAE ITC | 2018-08-01 |  | Oct 30, 31 and Nov 1st in Annapolis, MD
22 | X | X | X | Reach out to Embraer (Domingo) |  |  | 2018-08-01 |  | See action 7; Embraer states they are interested (TMA)
23 | X |  |  | Review D1S3 to ARINC 791 P1 prior to next Web conference | KSAT Subcommittee | KSAT Subcommittee | 2018-08-01 |  | See item 15
11 September 2018 - Web Conference
24 | X |  |  | Place A791 Strawman in SharePoint | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11 |  | Updated with Airbus' (Chris) Comments
25 | X |  |  | Review A791 Strawman (Airbus Comments) | KSAT Subcommittee | KSAT Subcommittee | 2018-09-11 |  | Be prepared to discuss during 16Oct2018 Web Conference. See item 25
26 | X |  |  | Victor to update TMA white paper | Victor Gheorghian | Bombardier | 2018-09-11 |  | Add Environmental Table and mechanicals (size, # of screws, loads). Oct 10, 2018: Submitted by Victor
27 | X |  |  | Place Bombardier Tail Mount Ant white paper in SharePoint | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11 |  | Victor presented white paper
28 | X |  |  | Review Bombardier TMA white paper; comment | KSAT Subcommittee | KSAT Subcommittee | 2018-09-11 |  | See Item 33
29 |  |  | X | What to do with pinout inconsistencies, why was it implemented |  |  | 2018-09-11 |  | A429/IRS/GPS/GNSS - Feedback from Peter. See item 35
30 |  |  | X | Distribute RC Comments and place on SharePoint | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11
31 | X | X | X | Schedule next meeting | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11 |  | Oct 30, 31, Nov 1 in Annapolis, MD
32 | X | X | X | Schedule next web conference | Jose Godoy | ARINC IA / SAE ITC | 2018-09-11 |  | 2018-10-16
16 October 2018 - Web Conference
33 | X |  |  | Review/Discuss updated Bombardier TMA and Environmental Categories white paper | KSAT Subcommittee | KSAT Subcommittee | 2018-10-16 |  | 18Dec2018: Ongoing; contact bombardier for continuity after Victor's departure. See items 26 and 28. See item 86
34 | X |  |  | Review ARINC 791 Part 1 Strawman | KSAT Subcommittee | KSAT Subcommittee | 2018-10-16 |  | see items 23 and 25
35 |  |  | X | Clarify ARINC 792 inconsistencies | KSAT Subcommittee | KSAT Subcommittee | 2018-10-16 |  | see item 29
36 | X |  |  | Astronics to provide alternate TMA configuration diagram | Jonathan Epstein | Astonics | 2018-10-16 | 2018-10-29 | Send to Victor and Jose
37 | X |  |  | Propose tail mount antenna structural susceptibility (movement) note/comment | Jonathan Epstein | Astonics | 2018-10-16 | 2018-10-29 | High level comment/requirement/generic (awareness and/or guidance)
38
39 |  |  |  | create WishList for ARINC 792-1 APIM |  |  |  |  | See Item 74
40 | X | X | X | Schedule next web conference | Jose Godoy | ARINC IA / SAE ITC | 2018-10-16
30 Oct - Nov 1, 2018 - Annapolis Meeting
45 | X |  |  | Victor to revise Astronics provided TMA Block Diagram | Victor Gheorghian | Bombardier | 2018-10-30 | 2018-11-20 | Add Justin and Dan to mailing list Contact Bombardier. See item 87
46 |  |  |  | Provide Table 2-3 (SharePoint ) for modification (e.g., visio) | Jose Godoy | ARINC IA |  | 2018-11-20
47 | X |  |  | New TMA Configuration Figure that is equivalent to Figure 2-3 Topo distribution, with TMA topography with all options (all equipment that cab reside in the pressurized vessel) | Victor Gheorghian | Bombardier | 2018-10-30 | 2018-11-20 | Also revise Figure 2-3a name (rename) for FMA only. Contact Bombardier; See item 88
48 | X |  |  | Airbus to provide updated Cable Insertion Loss (Section 6.4) based on ARINC 792 | Chris Schaupmann | Airbus | 2018-10-30 | 2018-11-20 | 18dec2018 - OnGoing
49 | X |  |  | Review out dated Section 8 - | Greg Otto and KSAT SC | Thinkom Solutions | 2018-10-30 | 2018-11-20 | Greg and Chris have provided inputs for review. See Item 81
49 | X |  |  | Carlisle to provide cooling comment | Brad Purpus | Carlisle Interconnect | 2018-10-30
50 | X |  |  | Add 2nd drawing for TMA option for Figure 4-21 KANDU Interfaces | Peter Lemme | TOTAPORT | 2018-10-30 | 2018-11-20 | Create different attachment for interwiring. See item 89. 17Jan2019: No interwiring will be added for TMA.
51 | X |  |  | Victor ro revise TMA Qual Req (add columns for ea assy) | Victor Gheorghian | Bombardier | 2018-10-30 | 2018-11-20 | A792 Qual Notes 22 and 23 Applicable to A791 Qual ? (Co-route power & control cables). 18Dec2018: Contact Bombardier. See items 33 and 86
52 | X |  |  | Replace Qual test Table 2-2 with revised TMA Qual Table | Jose Godoy | ARINC IA | 2018-10-30 | 2018-11-20 | After Victor provides
53 |  |  |  | Request Gulfstream and Embraer input on their qual requirements if co-locating coax and power cables in TMA | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-20 | Like Note 23 in A792 18Dec2018: Contact Embraer and Gulfstream. See item 91
54 | X |  |  | Airbus to provide Attachment 1.1 (Figure 1-19) | Chris Schaupmann | Airbus | 2018-10-30 |  | Cutout zones (geometry)
55 |  |  |  | Airframers to investigate if they use/hacv access to European Norm EN3645 (size 8 connector) | Victor, John, Jorge | Bombardier, Boeing and Gulfstream | 2018-11-01 | 2018-11-20 | Change connector? European Norm EN3645 and Mil ST are not interchangeable
56 | X |  |  | Paul to send white paper with issue with arrangement 21-84 | Paul Ahlf | Carlisle Interconnect | 2018-10-30 |  | Replace arrangement 21-84 (Quadrax Conn Table 4-17
67 | X |  |  | Consider reducing number of Modem outputs | KSAT SC | KSAT SC | 2018-10-30 | 2018-11-20 | Per A792. Suppliers to comment if used or if they object. Airbus to check. Delta, Boeing and Bombardier: disagree, it could limit options.
58 | X |  |  | New drawing for option between KANDU and Modem (bulkhead penetration). Maybe other figures | Victor Gheorghian | Bombardier | 2018-10-30 | 2018-11-20 | Victor to request source file/s (figure number/s). 18Dec2018: Contact Bombardier. See Item 92
59 | X |  |  | Clean up drawing with Quadrax connectors.(Figure 4-31) | Chris Schaupmann | Airbus | 2018-11-01 | 2018-11-20 | See A664P2 (ref line). Figure 4-31
60 | X |  |  | Qual Requirements for Cat 7 and 8 curves | Chris Schaupmann | Airbus | 2018-10-30 | 2018-11-20 | Airbus (Markus) to comment ; compare
61 | X |  |  | 5/1000 range comment | Chris Schaupmann | Airbus | 2018-10-30 |  | Origin of 5/1000
62 | X |  |  | Global Eagle to advise if Note 22 is required in Qual Test Table (Section 4), if so provide proposed Note wording | Antonio Campobasso | Global Eagle | 2018-10-30 | 2018-11-20 | Global Eagle: Level might be too high. See Global eagle email (Jose). 18Dec2018: See November 6, 2018 email from A. Campobasso (Global Eagle)m, stating no issue
63 | X |  |  | Verify the crash safety sustained impulses (Section 7, Category change from E to B for all except OAE) | John Rodgers | Boeing | 2018-11-01 | 2018-11-20 | Airbus has confirmed (Ok to go to B). 18Dec2018: Boeing confirmed OK with B inside LRUs. See 12Dec2018 email from John Rodgers
64 | X |  |  | Verify the lighting requirement (>than DO-160?) | John Rodgers | Boeing | 2018-11-01 | 2018-11-20 | 18Dec2018: per 12Dec2018 email from John: Boeing ok as stated in attachment A. Specific Boeing requirements per Boeing documents.
65 |  |  |  | Verify Icing requirement (DO-160 section 24) | John Rodgers | Boeing | 2018-11-01 | 2018-11-20 | 18Dec2018: per 12Dec2018 email from John: Inside fuselage NA. Outside fuselage: Non moving LRUs A. Moving LRUs B.
66 | X |  |  | Verify Temperature requirement (DO-160 section 22) | John Rodgers | Boeing | 2018-11-01 | 2018-11-20 | 18Dec2018: per 12Dec2018 email from John: Inside fuselage A2. Outside fuselage: D2 Modified; Ground Thermal Cert 110C.
67 | X |  |  | Why are there duplicate Qual rows for Section 16, 20 and 22 (Different 160E,F,G) | KSAT SC | KSAT SC | 2018-11-01 | 2018-11-20 | Discuss further
68 |  |  | X | Boeing to request considering Active Low for WoW (ARINC 792 Att6, Section 6.3.2 _ WOW (Air/Gnd) | John Rodgers | Boeing | 2018-10-31 | 2018-11-20 | What would it take to change B787? 18Dec2018: per 12Dec2018 email from John: Have requested details and impact for 787 to change this logic. NO CHANGE
69 | X |  | X | IRU global, except for system descriptions | Jose Godoy | ARINC IA | 2018-10-31 | 2018-11-20 | 18Dec2018: Done for ARINC 792
70 | X | X | X | Provide info on next AEEC SAI Meeting (Date and Vanue) | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-02 | February 7-8, 2019 at Gables Engineering in Coral Gables, Florida.
71 |  |  | X | Provide APIM Form | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-02 | In AEEC KSAT Subcommittee SharePoint
72 |  |  | X | Create A792 Supplement 1 - Wish List matrix | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-02 | In AEEC KSAT Subcommittee SharePoint
73
74 |  |  | X | Start APIM. All to submit items for A792-1 Wish List | KSAT SC | KSAT SC | 2018-11-01 | 2018-11-20 | APIM Form and Wish list matrix are in SharePoint
75 |  |  |  | Post A791Part 1 D1S3 | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-27 | Expected right after Jan meeting; 3Jan2019: Trying to post prior to Cocoa Beach meeting
76 | X | X | X | Schedule next WebEx conference (Nov 27, 2018) | Jose Godoy | ARINC IA | 2018-10-31 |  | Scheduled for Nov 27, 2018
77 | X | X | X | Arrange next meeting (Jan 15-17, 2019) | Jose Godoy | ARINC IA | 2018-10-31 |  | Scheduled for Jan 15-17, 2019
78 |  |  |  | Post next meeting announcement | Jose Godoy | ARINC IA | 2018-11-01 | 2018-11-27 | 20Nov2018: Expected by Nov 26th (Ask Jose if details are needed in advance)
Nov 27, 2018 - Conference
80 |  |  | X | Review Alternate KPSU to OAE wiring proposal | KSAT SC | KSAT SC | 2018-11-27 |  | Already in A792?
81 |  |  |  | Review Installation/Calibration/Alignment emails | KSAT SC | KSAT SC | 2018-11-27
82 |  |  |  | Add calibration and Alignment definition on ARINC 791 P1 and 2 | Chris Schaupmann | Airbus | 2018-11-27
83 |  |  |  | Schedule next WebEx | Jose Godoy | ARINC IA | 2018-11-27 |  | Scheduled for December 18, 2019
Dec 18, 2018 - Conference
85 | X | X | X | Confirm Dan and Justin (Bombardier are on the AEEC KSAT Subcommittee distribution | Jose Godoy | ARINC IA | 2018-12-18 |  | Added
86 | X |  |  | Populate Attachment 2 (Equip. Qual.) - Table 2-2 with TMA values |  |  | 2018-12-18 |  | Ask if Bombardier to provide (previously committed to by Victor). See item 33
87 | X |  |  | Include Astronics inputs to TMA diagram |  |  | 2018-12-18 |  | Ask if Bombardier to provide (previously committed to by Victor). See item 45
88 | X |  |  | Add Figure 2-3b (Topographic Distribution) for TMA configuration |  |  | 2018-12-18 |  | Ask if Bombardier to provide (previously committed to by Victor). See item 47
89 | X |  |  | Create Figure 4-21B (KANDU interfaces for TMA configuration | Peter Lemme | TOTAPORT | 2018-12-18 |  | See Item 50
90 | X |  |  | Create Interwiring for KANDU interfaces (new Attachment) | Peter Lemme | TOTAPORT | 2018-12-18 |  | See Item 50
91 | X | X | X | Contact Embraer and Gulfstream (TMA configuration and Attachment 2 (Equipment Qualification - Environmental Table) | Jose Godoy | ARINC IA | 2018-12-18 |  | request they review Qual Section, attend conferences and comment on TMA. See items 22 and 53
92 |  | X |  | New drawing for option between KANDU and Modem (bulkhead penetration). Maybe other figures |  |  |  |  | Ask if Bombardier to provide (previously committed to by Victor). See Item 58
93
94 | X | X | X | Schedule Jan 2019 web Conference
95
Cocoa Beach Meeting
100 |  | X |  | Astronics to provide commentary for maximum linear power (or Calibration Section) | Jonathan | Astronics | 2019-01-15
101 |  | X |  | Rearrange Section 3.0 for Generic Antenna Description, followed by FMA and then TMA requirements | Jose | ARINC IA | 2019-01-15
102 |  | X |  | Rework Figures 3-1 (OAE with Ku/Ka band interfaces) and 3-2 - revise drawing for generic Antenna Installation instead of FMA) | Peter | Totaport | 2019-01-15 |  | If the artwork is found
103 |  | X |  | Write Commentary KANDU 10 Output Voltage (section 5.1.2) | Paul |  | 2019-01-15
104 |  | X |  | Contact Boeing and Airframers so they can confirm support (add to APIM) | Jose | ARINC IA | 2019-01-16
105 |  | X |  | Contact Embraer, Bombardier and Gulfstream for assistance completing TMA Section/s | Jose |  | 2019-01-16
106 |  | X |  | Submit APIM (A792-1) | Jose |  | 2019-01-16
107 |  | X |  | Peter to re-do Attachment 3 with David's Antenna Pattern (Blockage) | Peter | Totaport | 2019-01-16 |  | ON GOING
108 |  | X |  | David to provide model with bank angle, move location, etc. | David | AMS
109 |  | X |  | Chris to research source of change for Figures 1-13 and 1-14 (Attachment 1) | Chris and Peter |  | 2019-01-16
110 |  | X |  | Chris to research 21L75 Quadrax connector and add history commentary (use/availability). Explain why 21-84 was replaced | Chris | Airbus | 2019-01-17
111
112 |  | X |  | Brad to propose new flange wording (Figure 1-3,...1-13 and 1-14) 8mm versus new 8.8; why 8.8 | Brad | Carlisle | 2019-01-17 |  | ON GOING
113 |  | X |  | Ask Honeywell and all A791 suppliers if they are using all KANDU spares; discrete is needed to address possible hazardous situation (Tx Control Logic as in A792) | Peter and Jose |  | 2019-01-17 |  | See Action 111
114 |  | X |  | Delete A629 Interface (only A429)? | Peter | Totaport | 2019-01-17
115 |  | X |  | Appendix E - peter to provide new figure and extreme temp | Peter | Totaport | 2019-01-17
116 |  | X |  | Figure 10-1 (attachment 10) fix size of J2. Make B1 Power Box smaller | Jose | ARINC IA | 2019-01-17
Annapolis KSAT Meeting - 18 June 2019
130 |  |  | X | Schedule next Common Modem WebEx | Peter Lemme and Jose Godoy | Totaport and ARINC IA | 2019-06-18 |  | After July 8th (target 15July)
131 |  |  | X | Review the architecture tradeoffs (4 MCU 100 Watts for Modman) | C. Modem WG | C. Modem WG | 2019-06-18 |  | Tradeoffs
132 |  |  | X | Describe SDR (Software Defined Radio) KSAT requirements | Matt |  | 2019-06-18 |  | Matt to write initial commentary. 5Sept2019: ONGOING
133 |  |  | X | Study feasibility of using LTE modem for gate-to-gate service (when A/C on Gnd not moving) | Antenna and/or Modem Suppliers |  | 2019-06-18 |  | Victor: How is this goal achieved; removes colling antenna requirements at GND Spd = low speed (higher than taxi, ant inop during taxi; enough spd to cool); and extreme temp conditions; potential benefit: smaller and lighter antenna. 5Sept2019: Kenny Kirchoff (Kymeta) volunteered to submit wording since they operate hybridly...
134 |  |  | X | What are maximum radome temperatures (in order to avoid skin damage for different fuselage before any damage). Equipment shutdown or other value that must be considered. Rephrase: at what temp does the skin start to get damaged. | Chris, (John) Michael Reinbold, Dan, Victor | Airframers | 2019-06-18 |  | Chris to provide initial study and discuss/share w/ airframers: Boeing, Mitsubishi and Bombardier…Include Outside Air Temp, wind assumption (i.e., wind, no wind), …worst case - sitting at gate? no due to solid state components material). 5Sept2019: Airbus and Boeing had discussions - 25Sept2019: ONGOING - Boeing to provide white paper (see item 177)
135 |  |  |  | Reach out to Gulfstream and Embraer for item 134 | Jose | ARINC IA/SAE ITC | 2019-06-18 |  | NO RESPONSE
136 |  |  | X | Do wiring provisions and feedthroughs support necessary cooling solutions not already provided by KPSU to OAE |  |  | 2019-06-18 |  | Ongoing. Current baseline includes no additional penetration, wiring, or power budget is allocated for cooling provisions. Consider adding commententary to Section 10.1 / or revise wording and make body text (requirement) instead of just a commentary. 5Sept2019: No new penetrations - 25Sep2019: work within existing penetrations and wiring pinouts
|  |  |  | Chris to Solicit participation from high power antenna manufacturers | Chris Schaupmann | Airbus | 2019-06-18
137 |  | X | X | What to do with Cutting Power (not on essential Bus) | Chris Schaupmann | Airbus | 2019-06-18 |  | What power is consumed, - power for degraded mode 17Jan2019. Add as a MIB functionality? SEE ITEM 13 ; 24SEPT2019: Airbus - no active plans.
138 |  | X |  | Identify if there is an Attenuators issue (Design issue?) | Eric Cross and Ant Suppliers | Viasat and … | 2019-06-18 |  | In ARINC 791 P2 determined attenuation power is adequate? 1Aug 2018: There are attenuators in the L-Band systems. 17Jan2019: On Going. 18June2019: Add guidance commentary. SEE ITEM 14. 24Sep2019: Ongoing, review A792 power. 25Sep2019: Antenna suppliers to review A791P2, Section 7.1 (System Cascade) . see Item 14 and 200
139 |  |  | X | Is there a fiber feedthrough connector? | Paul Alhf | Carlisle | 2019-06-18 |  | Paul to provide options available in market. 12July2019: Paul, Carlisle, provided a response. 5Sept2019: See Revised Totaport Common Modem white paper.
140 |  |  | X | Modem WG to provide fiber cabling recommendation | C. Modem WG | C. Modem WG | 2019-06-18 |  | Tradeoffs. 5Sept2019: See Revised Totaport Common Modem white paper / ONGOING. See GlenAir presentation confirmed that this technology can be used; direction being discussed. Also Irv (Chesapeake Adv Technologies to present at next meeting?); encouraging. What are the concerns. Coax to Fiber conversion (cost)
141 |  | X |  | Add Airbus security proposal to A791 Part 2 Strawman | Timo, Chris and Jose |  | 2019-06-19 |  | Airbus to provide revised proposal, ARINC IA to add to next draft. Jose to post to sharepoint. 29Oct2019: Airbus to present at the joint session with NIS Subcommittee during Jan 2020 meeting at Viasat (see item 201). 11Feb2020: Dr. Timo Warns submitted prposed wording for Appendix A of ARINC 791P2 strawman; to be reviewed during 12Feb2020 WebEx. 12Feb2020:
142 |  | X |  | Contact SpaceX, TeleSat, VIASAT and Inmarsat. Share Airbus network security proposal. Ref AI 141 | Victor, John, and Jose | Mitsubishi, Boeing and ARINC IA | 2019-06-19 |  | Constellation providers to provide comments. OneWeb(Mark)? 12July2019: Victor advised he had contacted Space X and TeleSat.
143 |  |  |  | Review Security Section in A792; does it reference A791 Part 2 | Jose Godoy | ARINC IA/SAE ITC | 2019-06-19 |  | See ARINC 842. (see items 141 and 201).
144 |  |  |  | Revised fittings proposal (reduce or remove fittings 3/4) - Tradeoffs study | Brad, Matt and Loren | Carlisle, Gogo | 2019-06-19 |  | Look at Aperture Form Factors and how to address. Based on Tradeoff study, determine how to handle (segregate Commercial from RJ or Leo Tech). See Item 180
145 |  | X |  | MIBs: Add mute # 8 = vendor defined (other) | Mark Sorensen | Delta Air Lines | 2019-06-19 |  | Ref Marks email. 29Oct2019: added to A791P2 D1S2 Strawman (on SharePoint)
146 |  | X |  | Review MIBs Section and provide feedback - Brief Subcommittee | Equipment Manufactures and system integrator | Equipment Manufactures and system integrator | 2019-06-19 |  | See Actions 6, 20, 145, 146, 147, 192, 202
147 |  | X |  | Airbus to provide MIBs feedback | Chris Schaupmann | Airbus | 2019-06-19 |  | See 6, 20, 145, 146, 147, 192 and 202. 23Jan2020: To be discussed during 12Feb2020. Chris to submit comments prior to WebEx.
148 |  | X | X | Schedule next KSAT Web Conference | Jose Godoy | ARINC IA/SAE ITC | 2019-06-20
KSAT WebConference - 16 July 2019
150 |  |  |  | Distribute Amazon Leo link |  |  | 2019-07-16
151 |  |  |  | Schedule Common Modem WebEx | Jose Godoy | ARINC IA/SAE ITC | 2019-07-16 |  | September 5th
Send dedicated invite to Peter for distribution
152 |  |  |  | If feasible, invite connector manufacturers to Sept 6th WebEx | Jose Godoy | ARINC IA/SAE ITC | 2019-07-16
153 |  |  |  | Inform the Flight Crew when the ant is shut off due to over temp | Chris | Airbus |  |  | Related to item 134. Consider a MIB object, See 192 and 200
154 |  |  |  | Schedule next Face to Face meeting | Jose Godoy | ARINC IA/SAE ITC | 2019-07-16 |  | SMA Posted; Meeing Sept 24-26, 2019 @ The Boeing Company in Seattle
155 |  |  |  | Jose to announce NIS activities (face to face and WebExes) | Jose Godoy | ARINC IA/SAE ITC | 2019-07-16 |  | Monitor ARINC 848 activity. Last NIS SC meeting June in Hamburg. Subcommittee reviewing inouts to last draft (Draft 7 to ARINC Project Paper 848. Jose added to NIS SC distribution. 02September2019: Next NIS meeting conflicts with KSAT SC meeting (September 24-26, 2019).
KSAT WebConference - 05 September 2019
160 |  |  |  | review updated Common Modem white paper and be ready to discuss at Seattle meeting | KSAT SC | KSAT SC
161 |  |  |  | Array Antenna Thermal Management - Boeing Inquiries |  |  |  |  | See items 134 and 177
170 |  |  |  | Post Supplement 3 to ARINC Characteristic 791 Part 1 | Jose Godoy | ARINC IA/SAE ITC |  |  | Published September 19, 2019
171 |  |  |  | Schedule next Face to Face meeting | Jose Godoy | ARINC IA/SAE ITC
172 |  |  |  | Schedule next Face to Face meeting | Jose Godoy | ARINC IA/SAE ITC
173 |  |  |  | Schedule Common Modem WebEx |  |  |  |  | WebEx on September 25th 8:00 AM PST
174 |  |  |  | Schedule Fiber optics WebEx |  |  |  |  | WebEx on September 26th 8:30 AM PST
Seattle KSAT Meeting - 24-26 Sept, 2019
175 |  |  |  | Present Array Antenna Thermal Management | Chris / Mike | Airbus / Boeing | 2019-09-24
176 |  |  |  | Array Antenna Thermal Management - Boeing White Paper |  |  | 2019-09-24 |  | Review Boeing Inquiry and Comment
177 |  |  |  | Draft Thermal Management Appendix from Airframers perpective (Thermal Mgt / Form Factor SG - now) | Chris and John | Airbus / Boeing | 2019-09-24 |  | See item 134. 29Oct2019: Boeing to provide white paper. See items 134 and 178. 22Jan2020: Add Wording in the main body and an Appendix with guidance. Waiting for Airbus/Boeing to share WhitePaper.
178 |  |  |  | Work with Airframers (review) above Item from systems Suppier perspective | Loren Ayotte | Gogo | 2019-09-24 |  | Related to 134 and 177
179 |  |  |  | Present Updates to Common Modem white paper | Peter Lemme | Totaport
179a |  |  |  | Update and distribute Common Modem paper w/ meeting results | Peter Lemme | Totaport | 2019-09-24
180 |  |  |  | Propose smaller form factor antenna attachment as an option (Form Factor SG - now) | Victor, Gregg, and Jonathan | Mitsubihi, Thinkom, Astronics | 2019-09-24 |  | See 144. Ongoing - Astronics and Victor working together to make proposal/ presentaion at the next face to face meeting. See item 206
181 |  |  |  | Viasat to Present | Eric Cross | Viasat
182 |  |  |  | Review / Discuss Viasat white paper | KSAT SC | KSAT SC | 2019-09-25
183 |  |  |  | Schedule next Common Modem web conference | Jose Godoy | ARINC IA/SAE ITC | 2019-09-25 | 2019-09-26 | Schedule for October 23, 2019; Provide Invite to Peter for distribution
184 |  |  |  | Eric Cross to propose 2 + 1 + 1 Common Modem IF Blk Diagram | Eric Cross | Viasat | 2019-09-25
185 |  |  |  | Create template to satisfy Service Provider requirements solicitation | Eric Cross | Viasat | 2019-09-25 |  | provided on Nov 8, 2019. See 186.
186 |  |  |  | Satellite Service Provider to submit acceptable minimum terminal requirements |  |  |  |  | In support of 185. Viasat to provide. 16April2020: Contact Eric (use what we have received and post)
187 |  |  |  | Viasat to research Coax attenuations given in A792 (Section 4.1.1 Coax IF). See action X. | Chris, Mike and Victor |  |  |  | Taking into account available Coax cables and length (100Ft). 29Oct2019: Boeing - longest runs also in 90+ ft. Ongoing. Ranges (i.e., 4 and 6 Ghz) are not spec'd. See A791P2 …if loss is see action than 11 dBs, add more cable or attenuate? Ideally avoid attenuation...Viasat to propose 3 options
188 |  |  |  | Robert Skuza (ComTech) to update Table in Common Modem | Robert Skuza | ComTech | 2019-09-25
189 |  |  |  | Peter to determine suitability of using celular for passenger | Peter Lemme | Totaport | 2019-09-25 |  | To be reported on during Jan meeting
190 |  |  |  | Review RFoF Presentation | KSAT SC | KSAT SC | 2019-09-25
191 |  |  |  | Adding Cell as a segregated sub network into A791P2 (ARINC 688 will be ref'd) | Peter Lemme | Totaport | 2019-09-25 |  | Carving out the address space to present the internal cell radio. 29Oct2019: To be reported on during Jan meeting
192 |  |  |  | Review MIB Section, improve to make it more implemented. External MIBs | Mike (Lead) | The Boeing Company | 2019-09-25 |  | Solicit proposal. Delta Air Lines wants maintenance (LRU Level) diagnostic. 29Oct2019: See item 202
193 |  |  |  | Correct Figure 1-14 in ARINC 792 | Jose Godoy | ARINC IA/SAE ITC | 2019-09-25
194 |  |  |  | Survey Antenna suppliers for signal characteristics (for Fiber) | Antenna Suppliers | Antenna Suppliers | 2019-09-25
198 |  |  |  | Schedule next web conference | Jose Godoy | ARINC IA/SAE ITC | 2019-09-25 |  | Oct 29th
199 |  |  |  | Schedule next Face to Face meeting | Jose Godoy | ARINC IA/SAE ITC | 2019-09-25 |  | January 21-23, 2019 at Viasat - co-located with NIS. 29Oct2019: Ongoing
KSAT WebConference - 29 October 2019
200 |  |  |  | Viasat to provide attenuation white paper ( see item X) | Eric Cross | Viasat | 2019-11-29 |  | See items 14 and 138
201 |  |  |  | Schedule Joint Security Session with NIS and Timo (Airbus) | Jose, Vanessa, Timo/Chris | ARINC IA and Airbus | 2019-11-29 |  | Morning Session so Airbus can dial in (see item 141)
202 |  |  |  | IMPROVE MIBs, review MIBs Sections, Make more user friendly to allow extensive usage. Suppliers to further popoulate sMIB sections; concentrate on making it an efficient maintenance tool for troubleshooting, LRU level diagnostic/repacement. | Jose Godoy | ARINC IA/SAE ITC | 2019-11-29 |  | Gathered all MIB items: 6, 20, 145, 146, 147, 192 and 202
205 |  |  |  | Schedule next web conference (12Dec2019) | Jose Godoy | ARINC IA/SAE ITC | 2019-11-29 |  | Mark Sorensen to confirm availability
KSAT WebConference - 12 December 2019
206 |  |  |  | Victor and Jonathan to prepare Fiber option proposal for 792 | Victor and Jonathan | Mitsubishi / Astronics | 2019-12-12 |  | 16April20: To be provided at June Virtual meeting (See item 180)
207 |  |  |  | reach out to ViaLight for Fiber presentation at next meeting | Jose Godoy | ARINC IA/SAE ITC | 2019-12-12 |  | No response
208 |  |  |  | Viasat to provide list of Sat Providers to send survey | Eric Cross | Viasat | 2019-12-12
KSAT Meeting at Viasat in Carlsbad - January 21-23, 20202
215 |  |  |  | Resend Satellite Providers Survey | Jose Godoy | ARINC IA/SAE ITC | 2020-01-22
216
217 |  |  |  | Feasibility of adding Amphenol and Radiall size 1 conn to ARINC 600 | Jose Godoy | ARINC IA/SAE ITC | 2020-01-22 |  | Using Size 2
218 |  |  |  | Distribute (KSAT Share Point) 6MCU space availability presentation | Jose Godoy | ARINC IA/SAE ITC | 2020-01-22 |  | Sent on 23Jan2020
219 |  |  |  | Write APIM for new generation Modman - digital interface APIM | KSAT SC | KSAT SC | 2020-01-22
220 |  |  |  | Send APIM Template | Jose | ARINC IA | 2020-01-22
221 |  |  |  | Insert QoS/CoS info from PP848 into ARINC 791P2 | Peter Lemme | Totaport | 2020-01-22 |  | 16April2020: Ongoing
222 |  |  |  | Markus to update Airbus A792-1 fittings 3 and 4 proposal |  |  | 2020-01-22
223 |  |  |  | Add AMU into ARINC 791P2 | Peter Lemme | Totaport | 2020-01-22 |  | Some work has to be done, check if complete. Classic config selected (AMU with Coax and Star Quad).
224 |  |  |  | Arrange Security Conf with Timo Warns, wording into A791P2 Section 5 and Appendix A | Chris Schaupmann | Airbus | 2020-01-22 |  | 11Feb2020: Timo provided security guidance (new wording) for Appendix A
225 |  |  |  | AMIP - revise F command as needed | Eric Cross | Viasat | 2020-01-22 |  | 16April2020: iDirect is revising AMIP. 11Nov2020: Ref AMIP document (remove from Part 2)
226 |  |  |  | Review remote Load (Appendix B of A791P2) | Eric Cross | Viasat | 2020-01-22
227 |  |  |  | Contact iDirect and inquire how AMIP will be controlled, advise of KSAT inputs? | Steve Moses | iDirect | 2020-01-23 |  | 16April2020: iDirect is revising AMIP.
228 |  |  |  | Next Virtual KSAT Face to Face Meeting? |  |  | 2020-01-23 |  | Looking at week of June 15th or 22nd, ongoing
229 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA | 2020-01-23 |  | Scehduled for 12 February 2020
KSAT WebConference - 12 February 2020
230 |  |  |  | Review Timo's Interfaces Security inputrs for A791 P2 | KSAT SC | KSAT SC | 2020-02-12 |  | See 141 and 231
231 |  |  |  | Dr. Timo Warns to submit revised proposed wording | Timo Warns | Airbus | 2020-02-12 |  | Replace AES and GES, add high level wording in section 5 and ref Appendix A
232 |  |  |  | Peter Lemme to add authentication wording? | Peter Lemme | Totaport | 2020-02-12
233 |  |  |  | Revise A792A APIM | KSAT SC | KSAT SC | 2020-02-12
234 |  |  |  | Submit revised APIM Draft to Paul | Jose Godoy | ARINC IA | 2020-02-12
235 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  |  | Schedule for 25March2020
KSAT WebConference - 16 April 2020
236 |  |  |  | Draft Attachment/Appendix with Viasat's & Satellite Survey Response values | Eric Cross | Viasat |  |  | See 186 and 250
237 |  |  |  | Submit APIM 20-001 Final (ARINC 792A multi modem-fiber KSAT System | Jose Godoy | ARINC IA | 2020-04-16
238 |  |  |  | Move to how to use open AMIP (Implementation guidelines) | Steve Moses | iDirect | 2020-04-16
239 |  |  |  | Schedule Next KSAT SC WebConference - 13May2020 | Jose Godoy | ARINC IA | 2020-04-16
KSAT WebConference - 13 May 2020
240 |  |  |  | Schedule next virtual meeting - June 22 thru June 25 (3-4 Hrs each day | Jose Godoy | ARINC IA | 2020-05-13 |  | SMA Availabe
241 |  |  |  | Update AMUpresentation with webex conference results | Peter Lemme | TOTAPORT | 2020-05-13
242 |  |  |  | AMU: which Modes will be supported | KSAT SC | KSAT SC | 2020-05-13 |  | 24June2020: See TOTAPORT Presentation (v8)
243 |  |  |  | Based on AMU Modes to be supported, are wiring changes required | KSAT SC | KSAT SC | 2020-05-13
244 |  |  |  | Ask Eric to populate the Sat Antenna Characteristics using what we have | Jose Godoy | ARINC IA | 2020-05-13
245 |  |  |  | Eric (viasat) to populate new Sat Provider interoperability attachment in A791P2 S2D1 | Eric Cross | Viasat | 2020-05-13 |  | See item 250
246 |  |  |  | Highlight Differences between Ka-bnd and Ku-Band characteristics | KSAT SC | KSAT SC | 2020-05-13
247 |  |  |  | Consider including an Avionics Data Acquisition function in ARINC KSAT Standards | KSAT SC | KSAT SC | 2020-05-13 |  | Related to ARINC 834A (Aircraft Data Broadcast) project
248 |  |  |  | Schedule Next KSAT SC WebConference - 10June2020 | Jose Godoy | ARINC IA | 2020-05-13
KSAT WebConference - 10 June 2020
250 |  |  |  | Make Satellite Provider Recommendations for InterOp decision (Appendix format) |  |  |  |  | Compare Viasat, eutelsat and SES Characteristics, 23June2020: Viasat provided Sat Provider inputs throughout body of doc
251 |  |  |  | Draft Virtual Meeting Agenda
252 |  |  |  | Review Items required for release of Supplement 2 to ARINC 791 Part 2 Draft 1
KSAT Virtual Meeting: June 23, 2020
255 |  |  |  | Review Inuts to Supplement 2 to ARINC 791 Part 2
256 |  |  |  | Should A771 (Iridium) and 741/761 (L-Band) Satcom be added to list of ref Docs | Jose
257 |  |  |  | Review Section 2.2 wording - Satcom System Interfaces/Channels
258 |  |  |  | Section 2.2 Figures 2-4, 2-6, 2-8: add ARINC 848 MISON | Peter Lemme | TOTAPORT
159 |  |  |  | Show Router Domain to Figure 2-9 (Etherner Domain Schematic
260 |  |  |  | Review new Elevation beamwidth characteristics (Section 2.8,1)
261 |  |  |  | Review VIASAT Sat provider Survey Inputs
262 |  |  |  | Are eutelsat and SES recommendations included | Jose and Gary
263 |  |  |  | Section 2.82 (Consider Renaming and add Ka characteristics
264 |  |  |  | Section 2.82 - Review Ka/Ku band dBW/MHz peak EIRP values
265 |  |  |  | Section 2.8.3 Polarization - use 10 or 100 millisec switching time | Viasat |  |  |  | Ask LEO Suppliers. Also add Ku Staement?. Viasat to consult with other providers
266 |  |  |  | SECTION 3.8 - Review Second/Maintenance Channel System wording |  |  |  |  | Change Channel to System
267 |  |  |  | Section 4.3: Need to decide on the GbE interface to the AMU for 791
268 |  |  |  | Section 4.5.1 and 4.5.3 - review / add IPv6 info | Jose |  |  |  | Consult with NIS
269 |  |  |  | Section 7.1: Review Viasat inputs and should Ku Band equivelant info be added? | KSAT SC
270 |  |  |  | Section 7.1: Review proposed Note 4 |  |  |  |  | reworded
271 |  |  |  | Section 7.3.1 - Ref Frequecies: Reconsile with AMU
272 |  |  |  | Table 7-5: Review new Table Values (Collins Proposal?)
273 |  |  |  | Table 7-7: Review Table Values (Under review?) |  |  |  |  | IF Signal Additional Characteristics – Tx
274 |  |  |  | Section 7.4.7 Ant SubSys Lo Freq - use 10 or 100 millisec switching time
275 |  |  |  | Table 7-9: Review Table Values (Under review?)
276
277 |  |  |  | Review Section 11 - QoS | Jose |  |  |  | Jose to implement initial compare for draft 2
278 |  |  |  | Fiber Optics Presentation
279 |  |  |  | Action Item based on Kontron AMU white paper - Ack | Jose |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified
280 |  |  |  | Do we need to provision to an additional AMU discrete, define In or Out is required? |  |  |  |  | KSAT SC decided
281 |  |  |  | assess, then to revise AMU presentation - wiring between AMU and Modman does not change. Provision for only 2 AMUs |  |  |  |  | Provision for only 2 AMUs. New discrete will be labled Man Specifiic. How many pins are affordable
282 |  |  |  | Kontron connector, specify as alternate? |  |  |  |  | Subcommittee/ Kintron to decide
283 |  |  |  | Should a connector with fiber be added to Kontron FormFactor, add fiber to existing middle plug? |  |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
284 |  |  |  | Discuss existing Kontron and Hughes ARINC 600 Connectors further |  |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
285 |  |  |  | Mitsubishi Comment: Review Power over Ethernet feasibility - High Voltage ? GEO issue?
286 |  |  |  | Comments on Mitsubishi proposal GPS at the Gate/MEO issue (no HDG) ?
287 |  |  |  | Brad Purpus - Carlisle to provide alternate sealant (feedthru cableing) presentation |  |  |  |  | fusalege penetration solution (to support Fiber Feedthru). Depending on availability. 19July2020: Provided compression fittings white paper on 18July2020.
288 |  |  |  | Michael - Boeing to provide alternate sealant (feedthru cableing) presentation |  |  |  |  | If feasible for July 22nd conf
289 |  |  |  | A791P2 Section 6 - Josh (Honeywell) to propose wording
290 |  |  |  | Schedule next Conference Call - July 22nd at 11:00 AM EST USA
291 |  |  |  | ADD MIB to next meeting/web conf agenda
292 |  |  |  | Thermal Management - Create Subgroup led by airframers. Subgroup to brief Subcommittee | Markus Altmann and Michael Reinbold | Airbus and Boeing |  |  | Contact Markus, Lead to be added to subgroup
293 |  |  |  | Schedule Next KSAT SC WebConference - 22July2020 | Jose Godoy | ARINC IA | 2020-07-02
KSAT WebConference - 22July2020
295 |  |  |  | Review and Comments on Carlisle Pass through presentation | KSAT SC | KSAT SC |  |  | Compression pass throughs white paper
296 |  |  |  | Carlisle to provide pertinent leakage information | Brad | Carlisle
297 |  |  | A | Create feedthrough requirements that supports multiple cable types (fiber, coax, cooper)
298 |  |  | 792/A | Standardize passthrough method | KSAT SC | KSAT SC |  |  | Define hole/s location/diameter, drill pattern, doubler needed?
299 |  |  |  | Schedule Thermal/Form Factor Subgroup Web Conferenece | Markus Altmann | Airbus
300 |  |  |  | Contact Smitty (coordination with Fiber Connector Subcommittees/working group) | Jose Godoy | ARINC IA |  |  | Initial contact made; presentation shared
302 |  |  |  | Schedule Next KSAT SC WebConference - 2Sept2020 | Jose Godoy | ARINC IA
KSAT WebConference - 2Sept2020
303 |  |  |  | Review posted Draft 1 of Supplement 2 to ARINC Characteristic 791, Part 2 | KSAT SC | KSAT SC
304 |  |  |  | Decision on AMU Connectors Cavity A, B and C |  |  |  |  | Decide on Oct 7th meeting?
205 |  |  |  | Thermal/Form Factor Meeting |  |  |  |  | Next Subgroup Meeting held 9Sept 2020
306 |  |  |  | Decide -792 in 791P2 or (new 792 Part 2 needed) |  |  |  |  | Arrange meeting with AEEC Exec Director
309 |  |  |  | Schedule Next KSAT SC WebConference - 7Oct2020 | Jose Godoy | ARINC IA
KSAT WebConference - 7Oct2020
310 |  |  |  | Report on Sept 9th Subgroup Meeting Meeting
311 |  |  |  | Present and Review Kontron white paper update
312 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  |  | Next Web Meeting 11Nov2020
KSAT WebConference - 11Nov2020
320 |  |  |  | Update APIM 16-006A
321 |  |  |  | Chris Schaupmann (Airbus) to provide initial Fiber Connection Requirements white paper | Chris Schaupmann | Airbus
322 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA
323 |  |  |  | Coordinate with FOS and CSS | Jose and Smitty | ARINC IA |  |  | 3Dec2020: Ongoing See item
324 |  |  |  | Schedule Next KSAT Vitual Meetig | Jose Godoy | ARINC IA |  |  | Meetings Dec 2-3, 2020 and 5-6Jan2021
325 |  |  |  | Carlile to submit white paper for next thermal subgroup meeting
KSAT Virtual Meeting - December 2-3, 2020
330 |  |  |  | Victor to contact Markus/Subgroup and identify issue (jose send email to parties)
331 |  |  |  | q3
332 |  |  |  | Loren to provide A792 strawman (AMU material)
333 |  |  |  | Jose to add other inputs (i.e., Viasat) to A791P2 Strawman after Peter makes it available
334 |  |  |  | Work with Fiber group, identify requirements / maybe APIM
335 |  |  |  | Chris to update Fiber presentation (see 321)
336 |  |  |  | What AMU Modes to be supported, are wiring changes required (see 242, 243)
337 |  |  |  | ARINC 629 is being removed
338 |  |  |  | Submit APIM 16-006A (see item 320)
339 |  |  |  | Boeing, Matt Landel (astronics) and Airbus will further develop MIB section
340 |  |  |  | Draft agenda for Jan 5-6, 2021
341 |  |  |  | Update KSAT SharePoint with meeting white papers and presentations (e.g., Mitsubitshi fittings)
342 |  |  |  | Add KSAT SharePoint folders for Action Items, Fiber, AMU, etc
343 |  |  |  | Schedule Next KSAT SC Teams Meetings (Jan 5 and 6, 2021)
344 |  |  |  | Develop Draft 2 of Supplement 2 to ARINC Characteristic 791 Part 2
345 |  |  |  | Update APIM 16-006A
346 |  |  |  | Standardize passthrough method (see item 298)
347 |  |  |  | Create feedthrough requirements; supports multiple cable types (fiber, coax, cooper) see item 297
348 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 5, 2021 (Day 1 of 2) | Jose Godoy | ARINC IA / SAE ITC
KSAT Virtual Meeting - January 5-6, 2021
350 |  |  |  | Thermal and Form Factor SuGroup to provide briefing to KSAT Subcommittee
351 |  |  |  | Review A791P2 strawman - develop Draft 2
352 |  |  |  | Review A792-1 Draft 1
353
354 |  |  |  | Submit revised A791P2-2 APIM to SAI
355 |  |  |  | Submit ARINC 791 P2 D2 S2
356 |  |  |  | Submit ARINC 792 D1 S1
357 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 22, 2021
FOS Kickoff Meeting - February 9, 2021
360 |  |  |  | FOS to develop quentionaire
361 |  |  |  | KSAT will use FOS questionaire to generate requirements list for FOS recommendations
362 |  |  |  | Schedule Next KSAT Vitual Meeting - March 3, 2021
KSAT Conference - March 3, 2021
364 |  |  |  | Expand FO requirements list for FOS | Subcommittee | Subcommittee |  |  | e.g., list signal type
365 |  |  |  | Schedule Next KSAT AMU Confernece - April 7, 2021 |  |  |  |  | Changed from March 31st due to conflict with Thermo Management / Form Factor
KSAT at IPS Sucommittee Meeting - March 18, 2021
367 |  |  |  | Review Honeywell Inputs to APIM 16-006A | KSAT Subcommittee | KSAT Subcommittee
368 |  |  |  | Complere APIM (revise or leave as is) | KSAT Subcommittee | KSAT Subcommittee
FOS Meeting - March 24, 2021
370 |  |  |  | Expand FOS/KSAT Matrix |  |  |  |  | See item # 375
371 |  |  |  | Label each of the 26 connections and describe (Ethernet/RF, Freq/Speed, # of disconnects, type) | KSAT Subcommittee | KSAT Subcommittee |  |  | worst case length from pr
372 |  |  |  | Provide Link Budget, include in requirements matrix for FOS
373 |  |  |  | Distribute KSAT / Fiber Requirements Matrix | Jose and Smitty | ARINC IA/SAE ITC
KSAT Conference - April 7, 2021
375 |  |  |  | Expand FO requirements list for FOS | FOS & KSAT | FOS & KSAT
379 |  |  |  | Schedule Next KSAT Online Conference (10May2021)
380 |  |  |  | Schedule Next KSAT Virtual Meeting (multi-Day)
KSAT Conference - May 10, 2021
381 |  |  |  | No FOS Requirements Updates (no new inputs, didn't update during meeting)
382 |  |  |  | Review 792 Network Architecture
383 |  |  |  | Loren to present A792 Strawman
384 |  |  |  | Loren to provide A792 Draft foir distribution and formating
385 |  |  |  | Add Attachment/Appendix sections (i.e, keyline definition) to Loren's A792 Draft and distribute
386 |  |  |  | Michael (Boeing) to check if keyline is already defined in ARINC XXX
387 |  |  |  | Add Power Budget (suggested by Loren), Peter to implement
388 |  |  |  | Totaport to provide updatred mural pdf
389 |  |  |  | Distribute revised "mural" A792 pdf
390 |  |  |  | Change AMU to Auxilary Modem Unit (globally - ARINC 792 and 792A)
391 |  |  |  | Plan briefing by Markus (Thermo and Form Factor recommendations)
392 |  |  |  | Plan joint session with NIS
393 |  |  |  | Need help with IPv6 editing siggestions
394 |  |  |  | Schedule Next KSAT Online Conference (May 21 11:00AM - 1:00PM EST
395 |  |  |  | Schedule Next KSAT Virtual Meeting (multi-Day)
KSAT Conference - June 21, 2021
400 |  |  |  | Add GeorgeNicola (OneWeb) and Brad Smith (Viasa) to AEEC KSAT Teams
401 |  |  |  | Provide Updated FO Requirements Matrix to Ron (GlenAir) and Subcommittee
402 |  |  |  | Jose and ARINC Staff to address ref issue (See Loren's email)
403 |  |  |  | Loren Ayotte,intelsat, to update A792-1 Figures + AMU 1per conferece decisions
404 |  |  |  | Add Meeting Docs to Teams
405 |  |  |  | Schedule Next KSAT Online Conference (July 19, 11:00AM - 1:00PM EST)
406
KSAT Conference - July 19, 2021
410 |  |  |  | Announce New Co-Chair
411 |  |  |  | Loren to contact Bob with info for cavity 2 (support fiber and be able to convert to (Quadrax) 792 pre Supplement 1)
412 |  |  |  | Schedule leadership Meeting (Thurday 29July2021)
413 |  |  |  | Distribute July 21st FOS meeting invitation
414 |  |  |  | Ron Logan to update FO Requirements Matrix (LF ) based on Trevor's email
415 |  |  |  | Schedule next Meeting (Sept 21-23)
416 |  |  |  | Jonathan to Verify req speeds for IQ transmission or suggest abandoning I/Q because rates for supporting greater than 10G/sec in this environment are challenging
417 |  |  |  | Totaport to comment on Jonathan's calculations (see above item)
418 |  |  |  | Annotate the arc block diagram with signal description (including IQ, Ethernet or other)
419
420 |  |  |  | Schedule next KSAT meeting (MIBs and AMU ) - 12Aug2021 (11:00 AM EST USA)
421 |  |  |  | Extensive MIBs update required - add to agenda (12August)
425 |  |  |  | Contact IPS and NIS so they can brief group on Status (tenatively for Sept 21st after intro)
KSAT Conference - Aug 12, 2021
430 |  |  |  | invite NIS and IPS (IPv6) present at Sept 21-23 meeting
431 |  |  |  | invite to preset: FOS and Thermal Management and Form Factor and EFB A834A
432 |  |  |  | What to about MIBs Section/s; align A792 add new LRUs)
433 |  |  |  | need volunteer for MIBs - What information (protocols) are required for MIBser LRU - Josh to look at work and advise, Chris will again request internal support, Mike wil look at Boeing requirements - inputs
434 |  |  |  | MIBs list of Concerns (see 433) + Create Working Group (Peter, Josh, Michael, Chris, ?)
435 |  |  |  | Distribute invite for MIBs SubGroup - Peter to coordinate with Josh and send info to Jose for invitation distribution
436 |  |  |  | Threat analysis - categorize each threat analysis / level of threats and what if flow chart
437 |  |  |  | Request modem suppliers attend a dedicated session during sept meeting ( Hughes and iDirect, Viasat, OneWeb,
438 |  |  |  | Can KPSU be changed? 5 Kg at 2200 Watts
439 |  |  |  | Announce and distribute next FOS (17August) | Jose Godoy | ARINC IA / SAE ITC
440 |  |  |  | Post Sept 21-23 SMA (Meeting Announcement) | Jose Godoy | ARINC IA / SAE ITC
KSAT LEADERSHIP September 2 and 9, 2021
441 |  |  |  | invite NIS and IPS (IPv6) , Markus-Airbus (Thermal and Form Factor); Fiber to present staus on Sept 21st | Jose Godoy | ARINC IA / SAE ITC
442 |  |  |  | Contact Modem and Sat Providers (iDirect, SES, HUGHES, Viasat, OneWeb, StarLink, gLat, NewTech) seamless
443 |  |  |  | Create AGENDA (6 Session) Day 1 FF/Thermal, NIS, IPS); Day 2: Fiber and A792; Day 3: MIBs, Schedule, Action Items) | Jose Godoy | ARINC IA / SAE ITC
444 |  |  |  | Contact Loren - A792 | Jose Godoy | ARINC IA / SAE ITC
445 |  |  |  | Contact Peter and Josh - when is the next subgroup meeting - who's particpating | Jose Godoy | ARINC IA / SAE ITC
446 |  |  |  | AMIP - what to do with MIBs, align 792 and A791P2 (only high level ? ) | KSAT Subcommittee | KSAT Subcommittee
447 |  |  |  | Schedule Leadership Meeting (Sept 9th at 9:30AM EST) | Jose Godoy | ARINC IA / SAE ITC
448 |  |  |  | Load A792-1 Strawman to KSAT Teams | Jose Godoy | ARINC IA / SAE ITC
KSAT Virtual Meeting - September 21-23, 2021
450 |  |  |  | Boeing and Airbus Action to study the installs for KPSU and KRFUs. Weight Issue went from 4.5 to 5, what next 7, 8 ? | Chris and Mike | Airbus and The Boeing Company
451 |  |  |  | Boeing and Airbus to arrange Thermal Management Meeting (Markus and Brenda) include Brad Purpuse, Matt Landell) | Markus Altmann and Mike Reinbold | Airbus and The Boeing Company
452 |  |  |  | Make Form Factor and Thermal Presentations avalable (including July 1st email summary) | Markus Altmann and Jose Godoy | Airbus and ARINC IA/SAE ITC
453 |  |  |  | Brad Purpose to provide Form Factor inputs) | Brad Purpus | Carlisle
454 |  |  |  | ARINC I A Staff to work on A792-1 strawman and share with Loren to assure links and figures are correct before posting | Jose Godoy | ARINC IA / SAE ITC
455 |  |  |  | ARINC IA to post ARINC 792-1 strawman can Attachment 1A and 1B be used | Jose Godoy | ARINC IA / SAE ITC
456 |  |  |  | Reach out to iDirect and wavestream (Keith King) for keyline timing verification | Greg Otto | VIASAT
457 |  |  |  | Request Subcommittee (Peter Lemme) present to SAI Subcommittee (ask to join a future SAI meeting - after Mid-Term | Jose Godoy | ARINC IA / SAE ITC
458 |  |  |  | Contact modem suppliers and provide FOS matrix so they may include their requirments (data rates) | Leadership
459 |  |  |  | Subcommittee to comment on P. Lemme's mural document on Teams | KSAT Subcommittee | KSAT Subcommittee
460 |  |  |  | Peter and Josh to arrange MIBs subgroup conference/s for thise that need to attend (matt to help Peter and Josh) - Working | Peter Lemme and Josh Laing | TOTAPORT and Honeywell
461 |  |  |  | Who can be added as A792A Industry Editor (per Section/Paragrpah/topic) Chris and Mike to lead effort | TBD
462 |  |  |  | Ron Logan (GlenAir) to provide updated Matrix (KSAT Optics requirements) | Ron Logan | GlenAir
463 |  |  |  | Recieve briefing on status of Staellite Providers Survey from Eric Cross, Viasat | Eric Cross | VIASAT
464 |  |  |  | Eric Cross to revise Survey and send to ARINC IA (Jose) for distribution | Eric Cross | VIASAT
465 |  |  |  | Send Satellite Providers Survey to Telesat, StarLink, MicroSoft, OneWeb, etc - info received form SES, Eutelsat and Viasat | Eric Cross | VIASAT |  |  | Eric Cross to provide and Jose to distribute
466 |  |  |  | Schedule the next Leadership Meeting 9:00 AM on Monday, Sept 27th) | Jose Godoy | ARINC IA / SAE ITC
467 |  |  |  | Schedule the next KSAT Subcommittee Confernce = October 19th 11:00 AM EST) | Jose Godoy | ARINC IA / SAE ITC
468 |  |  |  | Schedule the next KSAT Subcommittee Meeting (Dec 13-15, 2021) | Jose Godoy | ARINC IA / SAE ITC
KSAT LEADERSHIP September 28 and October 12, 2021
470 |  |  |  | Add spice to production breaks calcuations (wiring)
471 |  |  |  | Add drawing illustrating production breaks, disconnects (expand patch panel)
472 |  |  |  | Create Modem Survuey (information request) | Mike Reinbold and Chris Schaupmann | The Boeing Company and Airbus
473 |  |  |  | Section 3 - Pass Through ask Structural - including Brad Purpus | Brad Purpus | Carlisle
474 |  |  |  | Section 4 - Modem / Modem Manager | Modem Suppliers | Modem Suppliers
475 |  |  |  | Assign Modem Experts for industry editors for section 4 (Gilat, Hughes, iDirect, SES, etc. | Modem Suppliers | Modem Suppliers
476 |  |  |  | Drafted leter , send to modem distribution today on 12 October or early 10/13 | Jose Godoy | ARINC IA / SAE ITC
477 |  |  |  | Conatact Peter and Josh for MIBs meeting | Mike Reinbold | The Boeing Company
478 |  |  |  | Assign to section 5 (AMU)
479 |  |  |  | Ask Loren to review 5.1.1.5. AMU to Modem Interfaces
480 |  |  |  | 6 Section - KPSU: Challenge KPSU maybe Jonathan Epstein) Airbus and Boeing toalso support | Loren Ayotte
481 |  |  |  | 7 APIM - no forseen changes
482 |  |  |  | 8 - grounding and Bonding (any deltas due to fiber instead of fiber) Airframers to lead (mike and Chris) | Mike Reinbold and Chris Schaupmann | The Boeing Company and Airbus
483 |  |  |  | 9 - Installation and Alignment (
484 |  |  |  | 10 Maintenance and test (use existing 792 Text ask for Airline input
485 |  |  |  | Update Agenda
KSAT Online Conference - October 19, 2021
490 |  |  |  | Review Modem Suppliers survey - Hughes advised that 10Gb/sec satisfies all their current products, will continue internal inquiry
491 |  |  |  | Need more inputs from Modem Suppliersd
492 |  |  |  | Add Marcio Ferraz Gobato, Embraer, to AEEC KSAT
493 |  |  |  | What Fiber Type (multi-mode), ARINC 846?, 12 One Direction (Tx and Rx) or 4 x 4 (6 Tx and 6 Rx not available)
494 |  |  |  | Final Decision on disconnects (4 is minimum and 10 is default max)
495 |  |  |  | Decide on number of Beams to be supported, at Least 2 or 3, up to 6 (Main, HO, 2nd, 2nd HO, ATC and Broadcast)
496
497 |  |  |  | Need to purge excessive excessive information from MIBs Section - Need a volunteer to lead MIBs edits (use cases) and organize SG meetings (Update MIBs table) |  |  |  |  | MIBS Section must meet operator (Mechanic & Flt Crew requirements, Is it an outage, A/C issue, LRU @ fault, degraded operation, identify LRU trends
498 |  |  |  | Review proposed new Appendix provided by Peter Lemme (totaport)
499
500 |  |  |  | Schedule the next KSAT Subcommittee Conference: November 17 (11:00 AM EST) | Jose Godoy | ARINC IA / SAE ITC
501 |  |  |  | Next KSAT Subcommittee Meeting is Dec 13-15, 2021 - Create SMA | Jose Godoy | ARINC IA / SAE ITC
502
KSAT Leadership - October 28, November 4, and November 11, 2021
505 |  |  |  | Send Survey and invitation to Glat' - Suggext 9:00 AM EST on Nov 2 or 3rd (Tuesday or Wednesday) | Jose Godoy | ARINC IA / SAE ITC
506 |  |  |  | Create November 17 Meeting Draft Agenda | Jose Godoy | ARINC IA / SAE ITC
507 |  |  |  | Create December Meeting Draft Agenda (six sessions , 2 per day, 3 days)
508 |  |  |  | Send reminder with Agenda, highlight that mature drafts for A791P2 and A792-1 are due in late March to meet schedule (2022 AEEC GS) | Jose Godoy | ARINC IA / SAE ITC
509 |  |  |  | Remind FOS Leadership and Markus Altmann of November 17th meeting | Jose and Chris | ARINC IA / SAE ITC and Airbus
510 |  |  |  | Discuss Intersystem Protocol commonality (Industry) led by Airframers - coordinate with IPS?
511 |  |  |  | Complete Nov 17 Agenda (add A791P2 (by Chapters) and A792-1 (Is it mature for 2022 GS adoption) | Jose Godoy | ARINC IA / SAE ITC
512 |  |  |  | Distribute Nov 17 agenda | Jose Godoy | ARINC IA / SAE ITC
513 |  |  |  | Modem Suppliers Survey (4 out of 5 agree current propoal 10G/sec is adequate for present and short term (approx. next 5 years )
514 |  |  |  | Draft December Meeting Agenda | Jose Godoy | ARINC IA / SAE ITC
515 |  |  |  | Update A792A architecture (remove Extar Radio to reduce wiring to 24 connections (AMU 1/2, Modem, OAE Manager, + 2 spares) | Chris Schaupmann | Airbus
KSAT Meeting - Dec 13-15, 2021
520 |  |  |  | Share Boeing Thermal Presentation add to Teams KSAT Dec2021 Meeting Folder | Jose Godoy | ARINC IA / SAE ITC
521 |  |  |  | Share Airbus Thermal Slides add to Teams KSAT Dec2021 Meeting Folder | Jose Godoy | ARINC IA / SAE ITC
522 |  |  |  | Share Carlisle Thermal Presentation (Adapter - radome) and add to Teams KSAT Dec2021 Meeting Folder (after updated with weight) | Jose Godoy | ARINC IA / SAE ITC
523 |  |  |  | Add High Level Guidance to Standard on thermal assessment modeling + temp limit agreed by OEMs ( 180 degrees F) | Markus
524 |  |  |  | Include designassurance level for shutoff mechanism before fatiguing skin (is it the same temp for all fuselage) led Markus and Brenda | Markus
525 |  |  |  | OEMs to Draft value (numbers for blue and violet vectors (Heat Transfer along and through A/C skin) | Chris - Airbus, Mike - Boeing, Marcio - Embraer | Airbus, Boeing, Embraer
526 |  |  |  | Boeing and Embraer to review Airbus proposal (when Airbus makes suggestions) Heat Transfer Coefficient/factor + temperatures - Blk fuselage in Dubai | Chris - Airbus, Mike - Boeing, | Airbus, Boeing
527 |  |  |  | Include Use cases (operators that use A/C to kool aircraft or equipment)
528 |  |  |  | ARINC 792 Form Factor: What to do with reduction from 6 to 4 settings; Boeing believes that this belongs in a different standard (differnet loads than in A792)
529 |  |  |  | Embraer to share presentations with internal structural department for comments | Jose Godoy | ARINC IA / SAE ITC
530 |  |  |  | Distribute older Airbus white paper with fittings options (reduction by eliminating 4 and 6, or bring them inward) | Jose Godoy | ARINC IA / SAE ITC
531 |  |  |  | Get Brad's alternate fittings paper - | Jose Godoy | ARINC IA / SAE ITC
532 |  |  |  | OEMs to have an offline Fittings Reduction (Airbus and Boeing as Embraer will shut down til January 25) | Chris - Airbus, Mike - Boeing, Marcio - Embraer | Airbus, Boeing, Embraer
533 |  |  |  | A792-1 - Jonathan to add commentary on effects of the KPSU max Cable Length | Jonathan Epstein
534 |  |  |  | Embraer to verify if 10 Kg for the KPSU is acceptable for their configurations | Marcio Ferraz Gobato | Embraer
535 |  |  |  | Loren to revise ARINC 792A-1 Strawman with weight and power commentary | Loren Ayotte | Intelsat
536 |  |  |  | Share Loren's A792-1 Updates White Paper and add to Teams KSAT Dec2021 Meeting Folder | Jose Godoy | ARINC IA / SAE ITC
537 |  |  |  | Include Thermal Guidance in Draft 2 o Draft 3 (based on timimg os OEMs assessment)
538 |  |  |  | Embraer to submit Qual Test info (RTCA DO-160 Table) | Marcio Ferraz Gobato | Embraer
539 |  |  |  | Subcommittee to review and comment on ARINC 792-1 Strawman as reviewed and updated by Loren Ayotte)
540
541 |  |  |  | DAY 2
542
543 |  |  |  | Optics Requirements Matrix: Reference FO link in the digital representation, what are the characteristics?
544 |  |  |  | Based on 543, Study the fiber optics are there more requirements?
545 |  |  |  | Contact Jack Mandela (SeamLess) regarding alignment on interfaces and messages | Chris Schaupmann | Airbus
546 |  |  |  | Leadership to contact Peter to assure any changes that he has made are incorporated into the A791P2-2 Strawman |  |  |  |  | Section 1-3 have been moved to the AEEC KSAT Teams Sharepoint
547 |  |  |  | Josh to populate Teams Folder with the 3 Sections he has A582:E586 | Josh | Honeywell
548 |  |  |  | Eric Cross (Viasat) to send LEO contacts so that they may complete SAT Providers Survey | Eric Cross | Visat
549 |  |  |  | TeleSAT, OneWeb, SES, Amazon, StarLink, Inmarsat should be contacted
550 |  |  |  | Jose to send email with Survey to SAT Providers | Jose Godoy | ARINC IA/SAE ITC
DAY 3
551 |  |  |  | PP792A: Section 3 - Revise existing Legacy IF Diagram and add fiber | Brad Purvis | Carlisle
552 |  |  |  | PP792A: Section 3 - Revise existing Legacy IF Diagram and create the digital version (Two Fifures 31a and 31b) base band | Ron Logan
553 |  |  |  | Peter Lemme (totaport) to provide source doc for the figure in Section 3.1 (Jonathan, Peter, Ron, Gary) managed by Brad | Peter Leme | TOTAPORT
554 |  |  |  | Kevin Tat (Hughes) leads Section 4 - Modman | Kevin Tat | Hughes
555 |  |  |  | Consult with iDirect/Gilat and confirm Section 4 is acceptable? (per Gary, Kevin) | Kevin and Jose
556 |  |  |  | Provide iDirect/Gilat contact (and LEOs) - OneWeb to mediate
557 |  |  |  | preserve existing bus' and naming - just add new for multibeam | KSAT SC | KSAT SC
558 |  |  |  | Add placeholder Section 4.5 with connectors for Jonathan (at least two connectors to support MTs and Single Fibers?)
559 |  |  |  | Connector recommendations for Jonathan so he can complete the KPSU
560 |  |  |  | Chris to add KPSU/breakout box option | Chris Schaupmann | Airbus
561 |  |  |  | Review and comment on Marcio Embraer fiber proposal for Section 7 Bonding and Grounding | KSAT SC | KSAT SC
562 |  |  |  | Marcio to update presentation per meeting results | Marcio Ferraz Gobato | Embraer
563 |  |  |  | Marcio to add Figures and wording as required | Marcio Ferraz Gobato | Embraer
564 |  |  |  | Ask Tom Jaeger if he can ook at maintenance sectioin for Fiber | Jose Godoy | ARINC IA/SAE ITC
565 |  |  |  | Peter Lemme (totaport) to provide Amplifier Phase Noise slide | Peter Leme | TOTAPORT
566 |  |  |  | Send Survey to Cris and Mike - Today | Jose Godoy | ARINC IA/SAE ITC
567 |  |  |  | 1 pps Clock - GPS Source for timing - Higher rate needed, second clk/pulse needed - fiber requirements
568
569 |  |  |  | Schedule January 19 FO Session | Jose Godoy | ARINC IA/SAE ITC
570 |  |  |  | Schedule January 18-19, 2022 A791P2-2 Session | Jose Godoy | ARINC IA/SAE ITC
Jan 6, 2022 Leadership Conference
571 |  |  |  | Contact SpaceX for Sat Survey
572 |  |  |  | Distribute FOS Meeting Invite 13Jan2022p; email Smitty
573 |  |  |  | Contact Peter Lemme and request he attednd Thursday's Meeting; send email
574 |  |  |  | Gather in Teams all A791P2 Chapters (compile Standard body) |  |  |  |  | Sections 1-3 have been added
575 |  |  |  | Sat Surveys to Inmarsat and Hughes (get contact Brett Paterson.Bill Rowell/Inmarsat)
576
577 |  |  |  | Jan 18, 2022 - ARINC 791 Part 2 - 2 Conference
578
579 |  |  |  | KSAT Subcommittee to comment and decide on Totaport proposal re structure A791 Part 2, add Part 3 (Network and Info Security) ?
580 |  |  |  | Determine when A791 P2 Sections can migrate to the AEEC KSAT SC Microsoft Teams' folder (see item 574)
581 |  |  |  | Determine and transfer Sections XX from Part 2 into Part 3. Part 3 also includes Network and Security threat to Information (NIS is tasked with providing the Ciber Security Method, new APIM)
582 |  |  |  | Announce General Session Infomration, register on ARINC IA site / events May 10 - 12, 2022 Memphis, Tennessee
583 |  |  |  | Advise of next week's IPS Air/Ground Meeting (Jan 26, 2022, Morning Session)
Jan 20, 2022 Leadership Conference
585 |  |  |  | Send Notice to Peter, Matt, Josh, Jonathan, Loren, Eric Cross (meeting on 15th or 22nd (Tuesday)
586 |  |  |  | Distribute when available the next FOS Meeting Invite ; email Smitty
587 |  |  |  | schedule (SMA) March meetings
588 |  |  |  | Create Agenda for March Meeting Agenda
589 |  |  |  | From Action Item 247: Consider including an Avionics Data Acquisition function in ARINC KSAT Standards
590 |  |  |  | From Action Item 260: Consider including an Avionics Data Acquisition function in ARINC KSAT Standards
591 |  |  |  | Add Tail mount Characteristics to Sectio 2.82 and 2.8.3
592 |  |  |  | Address Reference Freq
Jan 27, 2022 Leadership Conference
595 |  |  |  | Create Agendas for February 15th (ARINC 791 Part 2) and March 8-10 (3 Day KSAT Subcommittee Meeting) | Marcio | Embraer
596 |  |  |  | Remind to Sat Providers to attend the Feb 15 meeting (add time to agenda) and to the March 8-10 KSAT meeting agenda)
597 |  |  |  | March 8-10 KSAT Subcommittee Meeting Announcement
Jan 27, 2022 - A792A Architecure and KSAT Fiber Requirements
600 |  |  |  | Review Architecture comment on trade off
601 |  |  |  | Keep the Patch Panels or just point to poiny harness
602 |  |  |  | MT configuration or discrete fiber connections (Chris and Rex)
603 |  |  |  | Rework Architecture to add discrete drawing
604 |  |  |  | Consider adding Digital Reference Signal Column (between Columns B and C, line 23) to KSAT FO
Feb 3 and 10, 2022 Leadership Conference
605 |  |  |  | Send Feb 15 A791-2 Standard Review only (document body) - Advise Peter (totaport) will lead
606
607 |  |  |  | Peter Lemme to provide Summary of Sections in exisitng P2 body that are moved to Part 3
608 |  |  |  | Confirm Jim Rosenberg (Wavestream) can lead/present KSAT Meeting
Feb 15, 2022 - Supplement 2 to ARINC Characteristic 791 Part 2 - Online Conference
610 |  |  |  | Review A791 Part 2 - 2 Strawman (Section 3)
611 |  |  |  | Distribute - February 16 FOS Conference Call Invite
Feb 24 and March 3, 2022 Leadership Conference
615 |  |  |  | Send meeting reminder with agenda
616 |  |  |  | Survey for meeting on the week of June 20th; who can and will attend (If face to face in Seattle) will you be authorized to travel
617 |  |  |  | Send Notice that A791Part 2-2 Sections 1 through 3, and the ARINC 792-1 Strawman are in the AEEC KSAT Teams' folders
618 |  |  |  | Distribute latest version of A792A FO Architecture (get latest version from Chris Schaupmann) |  |  |  |  | It is in AEEC KSAT Teams
KSAT Meeting - March 8-10, 2021
Markus to propose text (Thermal & Form Factor) for standard/s; Brenda (Boeing) & Marcio (Embraer) to review prior to Subcommiyttee review)
Since ARINC 791 P2 wll not be a GS item, continue with development of A792-1 after lunch on Wednesday March 9th (Session 3)
Review and decide how to update Enviromental Table (Waterproofness (change to Y as in ARINC 791)?
Get presentations from Markus and Jim and load to Teams
Create June Attendnace Survey for proposed meeting at Boeing in Seattle - create a June Meeting Folder

## Sheet2
Number | ISSUE | Responsible | Company | Date Opened | Due Date | Comments
1 | Security / Domain Segregation | Iridium Source / AGCS Subcommittee |  |  |  | Cooperation with NIS and RTCA SC-216. e for A781 Inmarsat set up guidance from subgroups (e.g., Airframers and others)
2 | Data Priority / Pre-emption (QoS) Domains | AGCS Committee |  |  |  | Based on Iridium NEXT network defined capabilities
3 | Data Priority / Pre-emption (QoS) Time Sensitive Apps | AGCS Committee |  |  |  | Based on Iridium NEXT network defined capabilities
4 | GNSS Filtering (how much Cable loss is allowed 3dBs?) | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
5 | Out of Iridium Band Filtering | Iridium |  |  |  | How do systems coexist non sumltaneously (Inmarsat/Iridium/other) | Iridium to have independent conference with Avionica and report to Subcommittee
6 | Will ARINC 771 embrase existing short burst data services | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
7 | Will ARINC 771 embrase existing circuit switch services | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
8 | Architecture Selection - narrow down five configurations | Iridium |  |  |  | Airbus: Agree on one configuration for LGA and one for the MGA | Iridium to propose on how to clasify each configuration
9 | Antenna Footprint | Iridium/Cobham / AGCS Subcommittee
Airbus to provide revised proposal, ARINC IA to add to next draft. Jose to post to sharepoint. 29Oct2019: Airbus to present at the joint session with NIS Subcommittee during Jan 2020 meeting at Viasat (see item 201). 11Feb2020: Dr. Timo Warns submitted prposed wording for Appendix A of ARINC 791P2 strawman; to be reviewed during 12Feb2020 WebEx. 12Feb2020:
See 6, 20, 145, 146, 147, 192 and 202. 23Jan2020: To be discussed during 12Feb2020. Chris to submit comments prior to WebEx.
[5 empty] | Chris | Airbus
|  |  |  | Draft Thermal Management Appendix from Airframers perpective (Thermal Mgt / Form Factor SG - now) |  |  |  | See item 134. 29Oct2019: Boeing to provide white paper. See items 134 and 178. 22Jan2020: Add Wording in the main body and an Appendix with guidance. Waiting for Airbus/Boeing to share WhitePaper.
|  |  |  | Propose smaller form factor antenna attachment as an option (Form Factor SG - now) |  |  |  | See 144. Ongoing - Astronics and Victor working together to make proposal/ presentaion at the next face to face meeting. See item 206
In support of 185. Viasat to provide. 16April2020: Contact Eric (use what we have received and post)
|  |  |  | Viasat to research Coax attenuations given in A792 (Section 4.1.1 Coax IF). See action X. |  |  |  | Taking into account available Coax cables and length (100Ft). 29Oct2019: Boeing - longest runs also in 90+ ft. Ongoing. Ranges (i.e., 4 and 6 Ghz) are not spec'd. See A791P2 …if loss is see action than 11 dBs, add more cable or attenuate? Ideally avoid attenuation...Viasat to propose 3 options
Adding Cell as a segregated sub network into A791P2 (ARINC 688 will be ref'd)
Solicit proposal. Delta Air Lines wants maintenance (LRU Level) diagnostic. 29Oct2019: See item 202
16April20: To be provided at June Virtual meeting (See item 180)
No response
215 |  |  |  | Resend Satellite Providers Survey
216
217 | [7 empty] | Using Size 2
218 | [7 empty] | Sent on 23Jan2020
219 |  |  |  |  | KSAT SC | KSAT SC
220 | [5 empty] | ARINC IA
221 | [5 empty] | Totaport |  | 16April2020: Ongoing
222 |  |  |  | Markus to update Airbus A792-1 fittings 3 and 4 proposal
223 |  |  |  |  | Peter Lemme | Totaport |  | Some work has to be done, check if complete. Classic config selected (AMU with Coax and Star Quad).
224 |  |  |  | Arrange Security Conf with Timo Warns, wording into A791P2 Section 5 and Appendix A |  | Airbus |  | 11Feb2020: Timo provided security guidance (new wording) for Appendix A
225 | [5 empty] | Viasat |  | 16April2020: iDirect is revising AMIP. 11Nov2020: Ref AMIP document (remove from Part 2)
226 |  |  |  | Review remote Load (Appendix B of A791P2) |  | Viasat
227 |  |  |  | Contact iDirect and inquire how AMIP will be controlled, advise of KSAT inputs? | Steve Moses | iDirect | 2020-01-23 | 16April2020: iDirect is revising AMIP.
228 |  |  |  | Next Virtual KSAT Face to Face Meeting? |  |  | 2020-01-23 | Looking at week of June 15th or 22nd, ongoing
229 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA | 2020-01-23 | Scehduled for 12 February 2020
KSAT WebConference - 12 February 2020
230 |  |  |  | Review Timo's Interfaces Security inputrs for A791 P2 | KSAT SC | KSAT SC | 2020-02-12 | See 141 and 231
231 |  |  |  | Dr. Timo Warns to submit revised proposed wording | Timo Warns | Airbus | 2020-02-12 | Replace AES and GES, add high level wording in section 5 and ref Appendix A
232 |  |  |  | Peter Lemme to add authentication wording? | Peter Lemme | Totaport | 2020-02-12
233 |  |  |  | Revise A792A APIM | KSAT SC | KSAT SC | 2020-02-12
234 |  |  |  | Submit revised APIM Draft to Paul | Jose Godoy | ARINC IA | 2020-02-12
235 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  | Schedule for 25March2020
KSAT WebConference - 16 April 2020
236 |  |  |  | Draft Attachment/Appendix with Viasat's & Satellite Survey Response values | Eric Cross | Viasat |  | See 186 and 250
237 |  |  |  | Submit APIM 20-001 Final (ARINC 792A multi modem-fiber KSAT System | Jose Godoy | ARINC IA | 2020-04-16
238 |  |  |  | Move to how to use open AMIP (Implementation guidelines) | Steve Moses | iDirect | 2020-04-16
239 |  |  |  | Schedule Next KSAT SC WebConference - 13May2020 | Jose Godoy | ARINC IA | 2020-04-16
KSAT WebConference - 13 May 2020
240 |  |  |  | Schedule next virtual meeting - June 22 thru June 25 (3-4 Hrs each day | Jose Godoy | ARINC IA | 2020-05-13 | SMA Availabe
241 |  |  |  | Update AMUpresentation with webex conference results | Peter Lemme | TOTAPORT | 2020-05-13
242 |  |  |  | AMU: which Modes will be supported | KSAT SC | KSAT SC | 2020-05-13 | 24June2020: See TOTAPORT Presentation (v8)
243 |  |  |  | Based on AMU Modes to be supported, are wiring changes required | KSAT SC | KSAT SC | 2020-05-13
244 |  |  |  | Ask Eric to populate the Sat Antenna Characteristics using what we have | Jose Godoy | ARINC IA | 2020-05-13
245 |  |  |  | Eric (viasat) to populate new Sat Provider interoperability attachment in A791P2 S2D1 | Eric Cross | Viasat | 2020-05-13 | See item 250
246 |  |  |  | Highlight Differences between Ka-bnd and Ku-Band characteristics | KSAT SC | KSAT SC | 2020-05-13
247 |  |  |  | Consider including an Avionics Data Acquisition function in ARINC KSAT Standards | KSAT SC | KSAT SC | 2020-05-13 | Related to ARINC 834A (Aircraft Data Broadcast) project
248 |  |  |  | Schedule Next KSAT SC WebConference - 10June2020 | Jose Godoy | ARINC IA | 2020-05-13
KSAT WebConference - 10 June 2020
250 |  |  |  | Make Satellite Provider Recommendations for InterOp decision (Appendix format) |  |  |  | Compare Viasat, eutelsat and SES Characteristics, 23June2020: Viasat provided Sat Provider inputs throughout body of doc
251 |  |  |  | Draft Virtual Meeting Agenda
252 |  |  |  | Review Items required for release of Supplement 2 to ARINC 791 Part 2 Draft 1
KSAT Virtual Meeting: June 23, 2020
255 |  |  |  | Review Inuts to Supplement 2 to ARINC 791 Part 2
256 |  |  |  | Should A771 (Iridium) and 741/761 (L-Band) Satcom be added to list of ref Docs | Jose
257 |  |  |  | Review Section 2.2 wording - Satcom System Interfaces/Channels
258 |  |  |  | Section 2.2 Figures 2-4, 2-6, 2-8: add ARINC 848 MISON | Peter Lemme | TOTAPORT
159 |  |  |  | Show Router Domain to Figure 2-9 (Etherner Domain Schematic
260 |  |  |  | Review new Elevation beamwidth characteristics (Section 2.8,1)
261 |  |  |  | Review VIASAT Sat provider Survey Inputs
262 |  |  |  | Are eutelsat and SES recommendations included | Jose and Gary
263 |  |  |  | Section 2.82 (Consider Renaming and add Ka characteristics
264 |  |  |  | Section 2.82 - Review Ka/Ku band dBW/MHz peak EIRP values
265 |  |  |  | Section 2.8.3 Polarization - use 10 or 100 millisec switching time | Viasat |  |  | Ask LEO Suppliers. Also add Ku Staement?. Viasat to consult with other providers
266 |  |  |  | SECTION 3.8 - Review Second/Maintenance Channel System wording |  |  |  | Change Channel to System
267 |  |  |  | Section 4.3: Need to decide on the GbE interface to the AMU for 791
268 |  |  |  | Section 4.5.1 and 4.5.3 - review / add IPv6 info | Jose |  |  | Consult with NIS
269 |  |  |  | Section 7.1: Review Viasat inputs and should Ku Band equivelant info be added? | KSAT SC
270 |  |  |  | Section 7.1: Review proposed Note 4 |  |  |  | reworded
271 |  |  |  | Section 7.3.1 - Ref Frequecies: Reconsile with AMU
272 |  |  |  | Table 7-5: Review new Table Values (Collins Proposal?)
273 |  |  |  | Table 7-7: Review Table Values (Under review?) |  |  |  | IF Signal Additional Characteristics – Tx
274 |  |  |  | Section 7.4.7 Ant SubSys Lo Freq - use 10 or 100 millisec switching time
275 |  |  |  | Table 7-9: Review Table Values (Under review?)
276
277 |  |  |  | Review Section 11 - QoS | Jose |  |  | Jose to implement initial compare for draft 2
278 |  |  |  | Fiber Optics Presentation
279 |  |  |  | Action Item based on Kontron AMU white paper - Ack | Jose |  |  | Jose to advise Kontron that existing AMU v8 will be specified
280 |  |  |  | Do we need to provision to an additional AMU discrete, define In or Out is required? |  |  |  | KSAT SC decided
281 |  |  |  | assess, then to revise AMU presentation - wiring between AMU and Modman does not change. Provision for only 2 AMUs |  |  |  | Provision for only 2 AMUs. New discrete will be labled Man Specifiic. How many pins are affordable
282 |  |  |  | Kontron connector, specify as alternate? |  |  |  | Subcommittee/ Kintron to decide
283 |  |  |  | Should a connector with fiber be added to Kontron FormFactor, add fiber to existing middle plug? |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
284 |  |  |  | Discuss existing Kontron and Hughes ARINC 600 Connectors further |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
285 |  |  |  | Mitsubishi Comment: Review Power over Ethernet feasibility - High Voltage ? GEO issue?
286 |  |  |  | Comments on Mitsubishi proposal GPS at the Gate/MEO issue (no HDG) ?
287 |  |  |  | Brad Purpus - Carlisle to provide alternate sealant (feedthru cableing) presentation |  |  |  | fusalege penetration solution (to support Fiber Feedthru). Depending on availability. 19July2020: Provided compression fittings white paper on 18July2020.
288 |  |  |  | Michael - Boeing to provide alternate sealant (feedthru cableing) presentation |  |  |  | If feasible for July 22nd conf
289 |  |  |  | A791P2 Section 6 - Josh (Honeywell) to propose wording
290 |  |  |  | Schedule next Conference Call - July 22nd at 11:00 AM EST USA
291 |  |  |  | ADD MIB to next meeting/web conf agenda
292 |  |  |  | Thermal Management - Create Subgroup led by airframers. Subgroup to brief Subcommittee | Markus Altmann and Michael Reinbold | Airbus and Boeing |  | Contact Markus, Lead to be added to subgroup
293 |  |  |  | Schedule Next KSAT SC WebConference - 22July2020 | Jose Godoy | ARINC IA | 2020-07-02
KSAT WebConference - 22July2020
295 |  |  |  | Review and Comments on Carlisle Pass through presentation | KSAT SC | KSAT SC |  | Compression pass throughs white paper
296 |  |  |  | Carlisle to provide pertinent leakage information | Brad | Carlisle
297 |  |  |  | Create feedthrough requirements that supports multiple cable types (fiber, coax, cooper)
298 |  |  |  | Standardize passthrough method | KSAT SC | KSAT SC |  | Define hole/s location/diameter, drill pattern, doubler needed?
299 |  |  |  | Schedule Thermal/Form Factor Subgroup Web Conferenece | Markus Altmann | Airbus
300 |  |  |  | Contact Smitty (coordination with Fiber Connector Subcommittees/working group) | Jose Godoy | ARINC IA |  | Initial contact made; presentation shared
302 |  |  |  | Schedule Next KSAT SC WebConference - 2Sept2020 | Jose Godoy | ARINC IA
KSAT WebConference - 2Sept2020
303 |  |  |  | Review posted Draft 1 of Supplement 2 to ARINC Characteristic 791, Part 2 | KSAT SC | KSAT SC
304 |  |  |  | Decision on AMU Connectors Cavity A, B and C |  |  |  | Decide on Oct 7th meeting?
205 |  |  |  | Thermal/Form Factor Meeting |  |  |  | Next Subgroup Meeting held 9Sept 2020
306 |  |  |  | Decide -792 in 791P2 or (new 792 Part 2 needed) |  |  |  | Arrange meeting with AEEC Exec Director
309 |  |  |  | Schedule Next KSAT SC WebConference - 7Oct2020 | Jose Godoy | ARINC IA
KSAT WebConference - 7Oct2020
310 |  |  |  | Report on Sept 9th Subgroup Meeting Meeting
311 |  |  |  | Present and Review Kontron white paper update
312 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  | Next Web Meeting 11Nov2020
KSAT WebConference - 11Nov2020
320 |  |  |  | Update APIM 16-006A
321 |  |  |  | Chris Schaupmann (Airbus) to provide initial Fiber Connection Requirements white paper | Chris Schaupmann | Airbus
322 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA
323 |  |  |  | Coordinate with FOS and CSS | Jose and Smitty | ARINC IA |  | 3Dec2020: Ongoing See item
324 |  |  |  | Schedule Next KSAT Vitual Meetig | Jose Godoy | ARINC IA |  | Meetings Dec 2-3, 2020 and 5-6Jan2021
325 |  |  |  | Carlile to submit white paper for next thermal subgroup meeting
KSAT Virtual Meeting - December 2-3, 2020
330 |  |  |  | Victor to contact Markus/Subgroup and identify issue (jose send email to parties)
331 |  |  |  | Peter to provide updates to A791P2 (Josh, Anh, and Matt to assist)
332 |  |  |  | Loren to provide A792 strawman (AMU material)
333 |  |  |  | Jose to add other inputs (i.e., Viasat) to A791P2 Strawman after Peter makes it available
334 |  |  |  | Work with Fiber group, identify requirements / maybe APIM
335 |  |  |  | Chris to update Fiber presentation (see 321)
336 |  |  |  | What AMU Modes to be supported, are wiring changes required (see 242, 243)
337 |  |  |  | ARINC 629 is being removed
338 |  |  |  | Submit APIM 16-006A (see item 320)
339 |  |  |  | Boeing, Matt Landel (astronics) and Airbus will further develop MIB section
340 |  |  |  | Draft agenda for Jan 5-6, 2021
341 |  |  |  | Update KSAT SharePoint with meeting white papers and presentations (e.g., Mitsubitshi fittings)
342 |  |  |  | Add KSAT SharePoint folders for Action Items, Fiber, AMU, etc
343 |  |  |  | Schedule Next KSAT SC Teams Meetings (Jan 5 and 6, 2021)
344 |  |  |  | Develop Draft 2 of Supplement 2 to ARINC Characteristic 791 Part 2
345 |  |  |  | Update APIM 16-006A
346 |  |  |  | Standardize passthrough method (see item 298)
347 |  |  |  | Create feedthrough requirements; supports multiple cable types (fiber, coax, cooper) see item 297
348 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 5, 2021 (Day 1 of 2) | Jose Godoy | ARINC IA / SAE ITC
KSAT Virtual Meeting - January 5-6, 2021
350 |  |  |  | Thermal and Form Factor SuGroup to provide briefing to KSAT Subcommittee
351 |  |  |  | Review A791P2 strawman - develop Draft 2
352 |  |  |  | Review A792-1 Draft 1
353
354 |  |  |  | Submit revised A791P2-2 APIM to SAI
355 |  |  |  | Submit ARINC 791 P2 D2 S2
356 |  |  |  | Submit ARINC 792 D1 S1
357 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 22, 2021
FOS Kickoff Meeting - February 9, 2021
360 |  |  |  | FOS to develop quentionaire
361 |  |  |  | KSAT will use FOS questionaire to generate requirements list for FOS recommendations
362 |  |  |  | Schedule Next KSAT Vitual Meeting - March 3, 2021
KSAT Conference - March 3, 2021
364 |  |  |  | Expand FO requirements list for FOS | Subcommittee | Subcommittee |  | e.g., list signal type
365 |  |  |  | Schedule Next KSAT AMU Confernece - April 7, 2021 |  |  |  | Changed from March 31st due to conflict with Thermo Management / Form Factor
KSAT at IPS Sucommittee Meeting - March 18, 2021
367 |  |  |  | Review Honeywell Inputs to APIM 16-006A | KSAT Subcommittee | KSAT Subcommittee
368 |  |  |  | Complere APIM (revise or leave as is) | KSAT Subcommittee | KSAT Subcommittee
FOS Meeting - March 24, 2021
370 |  |  |  | Expand FOS/KSAT Matrix |  |  |  | See item # 375
371 |  |  |  | Label each of the 26 connections and describe (Ethernet/RF, Freq/Speed, # of disconnects, type) | KSAT Subcommittee | KSAT Subcommittee |  | worst case length from pr
372 |  |  |  | Provide Link Budget, include in requirements matrix for FOS
373 |  |  |  | Distribute KSAT / Fiber Requirements Matrix | Jose and Smitty | ARINC IA/SAE ITC
KSAT Conference - April 7, 2021
375 |  |  |  | Expand FO requirements list for FOS | FOS & KSAT | FOS & KSAT
379 |  |  |  | Schedule Next KSAT Online Conference (10May2021)
380 |  |  |  | Schedule Next KSAT Virtual Meeting (multi-Day)
KSAT Conference - May 10, 2021
381 |  |  |  | No FOS Requirements Updates (no new inputs, didn't update during meeting)
382 |  |  |  | Review 792 Network Architecture
383 |  |  |  | Loren to present A792 Strawman
384 |  |  |  | Loren to provide A792 Draft foir distribution and formating
385 |  |  |  | Add Attachment/Appendix sections (i.e, keyline definition) to Loren's A792 Draft and distribute
386 |  |  |  | Michael (Boeing) to check if keyline is already defined in ARINC XXX
387 |  |  |  | Add Power Budget (suggested by Loren), Peter to implement
388 |  |  |  | Totaport to provide updatred mural pdf
389 |  |  |  | Distribute revised "mural" A792 pdf
390 |  |  |  | Change AMU to Auxilary Modem Unit (globally - ARINC 792 and 792A)
391 |  |  |  | Plan briefing by Markus (Thermo and Form Factor recommendations)
392 |  |  |  | Plan joint session with NIS
393 |  |  |  | Need help with IPv6 editing siggestions
394 |  |  |  | Schedule Next KSAT Online Conference (May 21 11:00AM - 1:00PM EST
395 |  |  |  | Schedule Next KSAT Virtual Meeting (multi-Day)
KSAT Conference - June 21, 2021
400 |  |  |  | Add GeorgeNicola (OneWeb) and Brad Smith (Viasa) to AEEC KSAT Teams
401 |  |  |  | Provide Updated FO Requirements Matrix to Ron (GlenAir) and Subcommittee
402 |  |  |  | Jose and ARINC Staff to address ref issue (See Loren's email)
403 |  |  |  | Loren Ayotte,intelsat, to update A792-1 Figures + AMU 1per conferece decisions
404 |  |  |  | Add Meeting Docs to Teams
405 |  |  |  | Schedule Next KSAT Online Conference (July 19, 11:00AM - 1:00PM EST)
406
KSAT Conference - July 19, 2021
410 |  |  |  | Announce New Co-Chair
411 |  |  |  | Loren to contact Bob with info for cavity 2 (support fiber and be able to convert to (Quadrax) 792 pre Supplement 1)
412 |  |  |  | Schedule leadership Meeting (Thurday 29July2021)
413 |  |  |  | Distribute July 21st FOS meeting invitation
414 |  |  |  | Ron Logan to update FO Requirements Matrix (LF ) based on Trevor's email
415 |  |  |  | Schedule next Meeting (Sept 21-23)
416 |  |  |  | Jonathan to Verify req speeds for IQ transmission or suggest abandoning I/Q because rates for supporting greater than 10G/sec in this environment are challenging
417 |  |  |  | Totaport to comment on Jonathan's calculations (see above item)
418 |  |  |  | Annotate the arc block diagram with signal description (including IQ, Ethernet or other)
419
420 |  |  |  | Schedule next KSAT meeting (MIBs and AMU ) - 12Aug2021 (11:00 AM EST USA)
421 |  |  |  | Extensive MIBs update required - add to agenda (12August)
425 |  |  |  | Contact IPS and NIS so they can brief group on Status (tenatively for Sept 21st after intro)
KSAT Conference - Aug 12, 2021
430 |  |  |  | invite NIS and IPS (IPv6) present at Sept 21-23 meeting
431 |  |  |  | invite to preset: FOS and Thermal Management and Form Factor and EFB A834A
432 |  |  |  | What to about MIBs Section/s; align A792 add new LRUs)
433 |  |  |  | need volunteer for MIBs - What information (protocols) are required for MIBser LRU - Josh to look at work and advise, Chris will again request internal support, Mike wil look at Boeing requirements - inputs
434 |  |  |  | MIBs list of Concerns (see 433) + Create Working Group (Peter, Josh, Michael, Chris, ?)
435 |  |  |  | Distribute invite for MIBs SubGroup - Peter to coordinate with Josh and send info to Jose for invitation distribution
436 |  |  |  | Threat analysis - categorize each threat analysis / level of threats and what if flow chart
437 |  |  |  | Request modem suppliers attend a dedicated session during sept meeting ( Hughes and iDirect, Viasat, OneWeb,
438 |  |  |  | Can KPSU be changed? 5 Kg at 2200 Watts
439 |  |  |  | Announce and distribute next FOS (17August) | Jose Godoy | ARINC IA / SAE ITC
440 |  |  |  | Post Sept 21-23 SMA (Meeting Announcement) | Jose Godoy | ARINC IA / SAE ITC
KSAT LEADERSHIP September 2 and 9, 2021
441 |  |  |  | invite NIS and IPS (IPv6) , Markus-Airbus (Thermal and Form Factor); Fiber to present staus on Sept 21st | Jose Godoy | ARINC IA / SAE ITC
442 |  |  |  | Contact Modem and Sat Providers (iDirect, SES, HUGHES, Viasat, OneWeb, StarLink, gLat, NewTech) seamless
443 |  |  |  | Create AGENDA (6 Session) Day 1 FF/Thermal, NIS, IPS); Day 2: Fiber and A792; Day 3: MIBs, Schedule, Action Items) | Jose Godoy | ARINC IA / SAE ITC
444 |  |  |  | Contact Loren - A792 | Jose Godoy | ARINC IA / SAE ITC
445 |  |  |  | Contact Peter and Josh - when is the next subgroup meeting - who's particpating | Jose Godoy | ARINC IA / SAE ITC
446 |  |  |  | AMIP - what to do with MIBs, align 792 and A791P2 (only high level ? ) | KSAT Subcommittee | KSAT Subcommittee
447 |  |  |  | Schedule Leadership Meeting (Sept 9th at 9:30AM EST) | Jose Godoy | ARINC IA / SAE ITC
|  |  |  | Load A792-1 Strawman to KSAT Teams | Jose Godoy | ARINC IA / SAE ITC
KSAT Virtual Meeting - September 21-23, 2021
450 |  |  |  | Boeing and Airbus Action to study the installs for KPSU and KRFUs. Weight Issue went from 4.5 to 5, what next 7, 8 ? | Chris and Mike | Airbus and The Boeing Company
451 |  |  |  | Boeing and Airbus to arrange Thermal Management Meeting (Markus and Brenda) include Brad Purpuse, Matt Landell) | Markus Altmann and Mike Reinbold | Airbus and The Boeing Company
452 |  |  |  | Make Form Factor and Thermal Presentations avalable (including July 1st email summary) | Markus Altmann and Jose Godoy | Airbus and ARINC IA/SAE ITC
453 |  |  |  | Brad Purpose to provide Form Factor inputs) | Brad Purpus | Carlisle
454 |  |  |  | ARINC I A Staff to work on A792-1 strawman and share with Loren to assure links and figures are correct before posting | Jose Godoy | ARINC IA / SAE ITC
455 |  |  |  | ARINC IA to post ARINC 792-1 strawman can Attachment 1A and 1B be used | Jose Godoy | ARINC IA / SAE ITC
456 |  |  |  | Reach out to iDirect and wavestream (Keith King) for keyline timing verification | Greg Otto | VIASAT
457 |  |  |  | Request Subcommittee (Peter Lemme) present to SAI Subcommittee (ask to join a future SAI meeting - after Mid-Term | Jose Godoy | ARINC IA / SAE ITC
458 |  |  |  | Contact modem suppliers and provide FOS matrix so they may include their requirments (data rates) | Leadership
459 |  |  |  | Subcommittee to comment on P. Lemme's mural document on Teams | KSAT Subcommittee | KSAT Subcommittee
460 |  |  |  | Peter and Josh to arrange MIBs subgroup conference/s for thise that need to attend (matt to help Peter and Josh) - Working | Peter Lemme and Josh Laing | TOTAPORT and Honeywell
461 |  |  |  | Who can be added as A792A Industry Editor (per Section/Paragrpah/topic) Chris and Mike to lead effort | TBD
462 |  |  |  | Ron Logan (GlenAir) to provide updated Matrix (KSAT Optics requirements) | Ron Logan | GlenAir
463 |  |  |  | Recieve briefing on status of Staellite Providers Survey from Eric Cross, Viasat | Eric Cross | VIASAT
464 |  |  |  | Eric Cross to revise Survey and send to ARINC IA (Jose) for distribution | Eric Cross | VIASAT
465 |  |  |  | Send Satellite Providers Survey to Telesat, StarLink, MicroSoft, OneWeb, etc - info received form SES, Eutelsat and Viasat | Eric Cross | VIASAT |  | Eric Cross to provide and Jose to distribute
466 |  |  |  | Schedule the next Leadership Meeting 9:00 AM on Monday, Sept 27th) | Jose Godoy | ARINC IA / SAE ITC
467 |  |  |  | Schedule the next KSAT Subcommittee Confernce = October 19th 11:00 AM EST) | Jose Godoy | ARINC IA / SAE ITC
468 |  |  |  | Schedule the next KSAT Subcommittee Meeting (Dec 13-15, 2021) | Jose Godoy | ARINC IA / SAE ITC
KSAT LEADERSHIP September 28 and October 12, 2021
470 |  |  |  | Add spice to production breaks calcuations (wiring)
471 |  |  |  | Add drawing illustrating production breaks, disconnects (expand patch panel)
472 |  |  |  | Create Modem Survuey (information request) | Mike Reinbold and Chris Schaupmann | The Boeing Company and Airbus
473 |  |  |  | Section 3 - Pass Through ask Structural - including Brad Purpus | Brad Purpus | Carlisle
474 |  |  |  | Section 4 - Modem / Modem Manager | Modem Suppliers | Modem Suppliers
475 |  |  |  | Assign Modem Experts for industry editors for section 4 (Gilat, Hughes, iDirect, SES, etc. | Modem Suppliers | Modem Suppliers
476 |  |  |  | Drafted leter , send to modem distribution today on 12 October or early 10/13 | Jose Godoy | ARINC IA / SAE ITC
477 |  |  |  | Conatact Peter and Josh for MIBs meeting | Mike Reinbold | The Boeing Company
478 |  |  |  | Assign to section 5 (AMU)
479 |  |  |  | Ask Loren to review 5.1.1.5. AMU to Modem Interfaces
480 |  |  |  | 6 Section - KPSU: Challenge KPSU maybe Jonathan Epstein) Airbus and Boeing toalso support | Loren Ayotte
481 |  |  |  | 7 APIM - no forseen changes
482 |  |  |  | 8 - grounding and Bonding (any deltas due to fiber instead of fiber) Airframers to lead (mike and Chris) | Mike Reinbold and Chris Schaupmann | The Boeing Company and Airbus
483 |  |  |  | 9 - Installation and Alignment (
484 |  |  |  | 10 Maintenance and test (use existing 792 Text ask for Airline input
485 |  |  |  | Update Agenda
KSAT Online Conference - October 19, 2021
490 |  |  |  | Review Modem Suppliers survey - Hughes advised that 10Gb/sec satisfies all their current products, will continue internal inquiry
491 |  |  |  | Need more inputs from Modem Suppliersd
492 |  |  |  | Add Marcio Ferraz Gobato, Embraer, to AEEC KSAT
493 |  |  |  | What Fiber Type (multi-mode), ARINC 846?, 12 One Direction (Tx and Rx) or 4 x 4 (6 Tx and 6 Rx not available)
494 |  |  |  | Final Decision on disconnects (4 is minimum and 10 is default max)
495 |  |  |  | Decide on number of Beams to be supported, at Least 2 or 3, up to 6 (Main, HO, 2nd, 2nd HO, ATC and Broadcast)
496
497 |  |  |  | Need to purge excessive excessive information from MIBs Section - Need a volunteer to lead MIBs edits (use cases) and organize SG meetings (Update MIBs table) |  |  |  | MIBS Section must meet operator (Mechanic & Flt Crew requirements, Is it an outage, A/C issue, LRU @ fault, degraded operation, identify LRU trends
498 |  |  |  | Review proposed new Appendix provided by Peter Lemme (totaport)
499
500 |  |  |  | Schedule the next KSAT Subcommittee Conference: November 17 (11:00 AM EST) | Jose Godoy | ARINC IA / SAE ITC
501 |  |  |  | Next KSAT Subcommittee Meeting is Dec 13-15, 2021 - Create SMA | Jose Godoy | ARINC IA / SAE ITC
502
KSAT Leadership - October 28, November 4, and November 11, 2021
505 |  |  |  | Send Survey and invitation to Glat' - Suggext 9:00 AM EST on Nov 2 or 3rd (Tuesday or Wednesday) | Jose Godoy | ARINC IA / SAE ITC
506 |  |  |  | Create November 17 Meeting Draft Agenda | Jose Godoy | ARINC IA / SAE ITC
507 |  |  |  | Create December Meeting Draft Agenda (six sessions , 2 per day, 3 days)
508 |  |  |  | Send reminder with Agenda, highlight that mature drafts for A791P2 and A792-1 are due in late March to meet schedule (2022 AEEC GS) | Jose Godoy | ARINC IA / SAE ITC
509 |  |  |  | Remind FOS Leadership and Markus Altmann of November 17th meeting | Jose and Chris | ARINC IA / SAE ITC and Airbus
510 |  |  |  | Discuss Intersystem Protocol commonality (Industry) led by Airframers - coordinate with IPS?
511 |  |  |  | Complete Nov 17 Agenda (add A791P2 (by Chapters) and A792-1 (Is it mature for 2022 GS adoption) | Jose Godoy | ARINC IA / SAE ITC
512 |  |  |  | Distribute Nov 17 agenda | Jose Godoy | ARINC IA / SAE ITC
513 |  |  |  | Modem Suppliers Survey (4 out of 5 agree current propoal 10G/sec is adequate for present and short term (approx. next 5 years )
514 |  |  |  | Draft December Meeting Agenda | Jose Godoy | ARINC IA / SAE ITC
515 |  |  |  | Update A792A architecture (remove Extar Radio to reduce wiring to 24 connections (AMU 1/2, Modem, OAE Manager, + 2 spares) | Chris Schaupmann | Airbus
KSAT Meeting - Dec 13-15, 2021
520 |  |  |  | Share Boeing Thermal Presentation add to Teams KSAT Dec2021 Meeting Folder | Jose Godoy | ARINC IA / SAE ITC
521 |  |  |  | Share Airbus Thermal Slides add to Teams KSAT Dec2021 Meeting Folder | Jose Godoy | ARINC IA / SAE ITC
522 |  |  |  | Share Carlisle Thermal Presentation (Adapter - radome) and add to Teams KSAT Dec2021 Meeting Folder (after updated with weight) | Jose Godoy | ARINC IA / SAE ITC
523 |  |  |  | Add High Level Guidance to Standard on thermal assessment modeling + temp limit agreeed by OEMs ( 180 degrees F) | Markus
524 |  |  |  | Include designassurance level for shutoff mechanism before fatiguing skin (is it the same temp for all fuselage) led Markus and Brenda
525 |  |  |  | OEMs to Draft value (numbers for blue and violet vectors (Heat Transfer along and through A/C skin)
526 |  |  |  | Boeing and Embraer to review Airbus proposal (when Airbus makes suggestions) Heat Transfer Coefficient/factor + temperatures - Blk fuselage in Dubai
527 |  |  |  | Include Use cases (operators that use A/C to kool aircraft or equipment)
528 |  |  |  | ARINC 792 Form Factor: What to do with reduction from 6 to 4 settings; Boeing believes that this belongs in a different standard (differnet loads than in A792)
529 |  |  |  | Embraer to share presentations with internal structural department for comments | Jose Godoy | ARINC IA / SAE ITC
530 |  |  |  | Distribute older Airbus white paper with fittings options (reduction by eliminating 4 and 6, or bring them inward)
531 |  |  |  | Get Brad's alternate fittings paper
532 |  |  |  | OEMs to have an offline Fittings Reduction (Airbus and Boeing as Embraer will shut down til January 25)
533 |  |  |  | Jonathan to add commentary on effects of Cable Length
534 |  |  |  | Embraer to verify if 10 Kg for the KPSU is acceptable for their configurations
535 |  |  |  | Loren to revise ARINC 792A-1 Strawman with weight and power commentary
536 |  |  |  | Share Loren's A792-1 Updates White Paper and add to Teams KSAT Dec2021 Meeting Folder
537 |  |  |  | Include Thermal Guidance in Draft 2 o Draft 3 (based on timimg os OEMs assessment)
538 |  |  |  | Embraer to submit Qual Test info (RTCA DO-160 Table) | Marcio Ferraz Gobato | Embraer
539 |  |  |  | Subcommittee to review and comment on ARINC 792-1 Strawman as reviwed and updated by Loren Ayotte)
540
541 |  |  |  | DAY 2
542
543 |  |  |  | Reference FO link in the digital representation, what are the characteristics?
544 |  |  |  | Based on 543, Study the fiber optics are tere more requirements?
545 |  |  |  | Contact Jack Mandela (SeamLess) regarding alignment on interfaces and messages | Chris
546 |  |  |  | Leadership to contact Peter to assure any changes that he has made are incorporated into the A791P2-2 Strawman
547 |  |  |  | Josh to populate Teams Folder with the 3 Sections he has A582:E586
Eric Cross (Viasat) to send LEO contacts so that they may complete SAT Providers Survey
TeleSAT, OneWeb, SES, Amazon, SatLink, Inmarsat should be contacted
Jose to send email with Survey to SAT Providers
DAY 3
|  |  |  | PP792A: Section 3 - Revise existing Legacy IF Diagram and add fiber | Brad
|  |  |  | PP792A: Section 3 - Revise existing Legacy IF Diagram and create the digital version (Two Fifures 31a and 31b) base band | Ron
Peter Lemme (totaport) to provide source doc for the figure in Section 3.1 (Jonathan, Peter, Ron, Gary) managed by Brad
Kevin Tat (Hughes) leads Section 4 - Modman
Consult with iDirect/Gilat and confirm Section 4 is acceptable? (per Gary, Kevin)
Provide iDirect/Gilat contact (and LEOs) - OneWeb to mediate
preserve existing

## Compatibility Report
Compatibility Report for AGCS SC_Action Items _ 20Aug2017.xls
Run on 8/21/2017 21:25
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 3 | Excel 97-2003