## Sheet1
Action Item | ARINC 791 P2/P3 | ARINC 793 | Description | Responsible | Company | Date Opened | Due Date | Comments
Feb 14-16, 2023 Meeting in Chicago
1 |  |  | Review and update NIS Security APIM
2 |  |  | Request status of Form Factor Update; when will Boeing Appendix be available - Ryan to ask Brenda, she will then coordinate with Markus
3 |  |  | Markus - Airbus to propose Form Factor attachment
4 |  |  | Loren to review A791 Part 3 Section 2 - Josh Sent Comment
5 | X |  | New Beam Pattern wording needed ( skew angle , A/C - Raymond Thinkom to add flat panel antenna
6 |  |  | PSD or ESD, Loren to clean up and submit PSD section
7 |  |  | Add Bryan Loeb to distribution and Teams SharePoint folders
8 |  |  | ARINC 792 - 2: Thermal Management - Matt Landel to thermal management proposal (new appendix) Matt will coordinate with Markus
9 |  |  | ARINC 792 - 2: Form Factor - Boeing to add Appendix (Teams/WebEx conferences will be scheduled as needed) see 912
10 |  |  | ARINC 792 - 2: References to ARINC 791 Part 2 - Peter
11 |  |  | Eric Cross to review 791P2 Chapter 5 - include Wavestrean Ref Frequency (Spectral Mask)
12 |  |  | Next Conference call - March 7th - 12:00OM - 3:00PM Eastern USA Time
13 |  |  | Chris to provide updated V18 of FO diagrams Architecture
14 |  |  | Advise SAM SAI that there is no A792A its ARINC PP 793
15 |  |  | Invite KONTRON to discuss CCA modem standarization
16 |  |  | Create ARINC 793 Strawman |  |  |  |  | Draft 1 of ARINC 792A had been posted in 2021, very high evel
17 |  |  | Conference Call March 27th 11:00 AM to 1:00PM Eastern USA Time - recheduled for March 7th (see item 923)
18 |  |  | Mature Draft for A792 needed no later than March 31st
19 |  |  | Next Face to Face Meeting - June 13-15, 2023 in Annapolis/Bowie
20 |  |  | Ask Eric if Satellite Provider Data is Complete - OK as is
|  |  |  | 258.3333 | 292.6667
|  |  | March 7, 2023 Teams Meeting | 233.3333
21 |  |  | Matt (Astronics) presented a Thermal Guidance WP; he will revise with today's meeting results | Matt Landel | Astronics Aerosat |  |  | Matt submitted the wp on 14March2023
22 |  |  | Chris (Airbus) will submit Appendix 12 draft | Chris Schaupmann | Airbus
23 |  |  | Schedule March 27th (ARINC 792-2; Thermal MGT and Form Factor) | Jose Godoy | ARINC IA/SAE ITC
24 |  |  | Comfirm that the June 13-15, 2023 KSAT Meeting can be held in Annapolis/Bowie | Jose Godoy | ARINC IA/SAE ITC |  |  | Approved, will be tight if more than 15 attend
25 |  |  | Send June KSAT Subcommittee Meeting (SMA) Announcement
March 27, 2023 Teams Meeting
26 |  |  | Thermal Management Review and Comments on Astronics (Matt's) proposal
27 |  |  | Include Chris' attachement 2 comment prior to DO-160 Table - with ref to attachent 12
28 |  |  | Kenny Kiechoff to provide text on existing 90 Degree Temp
29 |  |  | Global replacement of standard with Baseline fittings configuration
30 |  |  | Form Factor - Fittings
31 |  |  | Markus - comments on 12.1 information on lugs / and if going from base line 6 to 4
32 |  |  | ARINC IA to global fix Attachment, Section,Chapter consuistency, Fittings Adapterplate/Air Frame side Lugs, X "x" Loads
33 |  |  | What Image s/b used for Small Factor drawing (Section 12.6)
34 |  |  | Address Lugs orientation (shift or don't shift 90 degree); decided not to shift based on Markus explanation
35 |  |  | Review Boeing Statement
36 |  |  | Review Body
37 |  |  | Review Section 12 - Small Factor Interface between Airplane and Antenna
38 |  |  | Review Thermal Management Considerations for Installation Approval Appendix
39 |  |  | Submit ARINC 792-2 Docs for Adoption Consideration at 2023 AEEC General Session (8-11May2023 Denver, Colorado)
April 13, 2023 - KSAT Leadership Meeting
40 |  |  | Start June 13-16, 2023 meeting agenda - Annapolis | Jose Godoy | ARINC IA/SAE ITC
41 |  |  | Prepare and share with KSAT Leadership Subcommittee Report for 2023 AEEC General Session | Jose Godoy | ARINC IA/SAE ITC
42 |  |  | Monitor Industry ARINC 792-2 comments | KSAT Leadership | KSAT Leadership |  |  | No comments yet
43 |  |  | Schedule May 1st (8 EDT) Leadership + Peter and Josh | Jose Godoy | ARINC IA/SAE ITC
44 |  |  | Prepare for June 13-15 meeting - Must produce mature draft of A791p2 AND p3 and strategize futre work | Jose Godoy | ARINC IA/SAE ITC
45 |  |  | Distribute June 13-15 Bowie Agenda, Highlight only an ARINC 791 meeting, no Fiber Optic discussions | Jose Godoy | ARINC IA/SAE ITC
June 13-15, 2023 Meeting at ARINC in Bowie
46 |  |  | Reviewed ARINC 791P2 - all sections exept Antenna - Ask ThinKom if they will provide edits to section
47 |  |  | Begin a new action Items matrix, start with the Chicago Meeting Feb 14-16, 2023 | Jose Godoy | ARINC IA / SAE ITC
48 |  |  | Schedule Teams Meeting for July 20th, 11:00 AM to 12 Noon (A793 Fiber Optic session), 12 PM to 3:00 PM (ARINC 791 P2/P3) | Jose Godoy | ARINC IA / SAE ITC
49 |  |  | Ask Jim Rosenberg if Wavestream if can host meeting in California after 1st wk in October 2023; meeting room for 20-25 attendees | Jose Godoy | ARINC IA / SAE ITC |  |  | Sent Jim emial request, he is inquiring internakly and will advise
50 |  |  | Report to SAE IT of Ryan Torgerson's Teams issue | Jose Godoy | ARINC IA / SAE ITC
51 |  |  | Peter Lemme to answer NIS APIM 23-004 questions (Vanessa Mastros email) - request that appropriate KSAT personnel attend NIS meetings | Jose Godoy | ARINC IA / SAE ITC
52 |  |  | Renamed ARINC Project Paper 791 Part 3: Information Transfer and Internetworking - rename globally | Peter Lemme | Totaport
53 |  |  | Produce mature versions of Supplement 2 to ARINC 791 Part 2 | KSAT Subcommittee | KSAT Subcommittee
54 |  |  | Produce mature versions of ARINC Project Paper 791 Part 3 | KSAT Subcommittee | KSAT Subcommittee
55 |  |  | Can ThinKom provide an update to the Appendix F: Coverage Limitations of Low Profile Apertures… | Greg, Raymond | Thinkom
56 |  |  | Peter Lemme to advise when Sections for A791 P2/P3 can be downloaded from Teams SharePoint to create unified draft | Peter Lemme | Totaport
57 |  |  | Send Chris A791 p2/p3 Sections (cannot access Teams SharePoint | Jose Godoy | ARINC IA / SAE ITC
58 |  |  | Advise FOS of July 20th Teams Meeting (first hour 11:00AM to 12 Noon) will be dedicated to KSAT Fiber architecture | Jose Godoy | ARINC IA / SAE ITC
July 20, 2023 Fiber and ARINC 791 P2/P3
60 |  |  | Jim Rosenberg/DIFI to Update on releases 1.2 and 1.3/ Reference Plane and DIFI - not against, want to add link establishment | Jim Rosenberg | Wavestream
61 |  |  | Fiber Schematic Presentation | Chris Schaupmann | Airbus
62 |  |  | Complete initial review of advanced ARINC 791-2 Part 2 Strawman
63 |  |  | Complete PSD Section of ARINC 791-2 Part 2
64 |  |  | ARINC IA Staff to compile Sections of ARINC 791-1 Part 2 (12:00 PM to 2:00 PM EST) | Jose Godoy | ARINC IA / SAE ITC
65 |  |  | Peter to send appropraite Section/s to Mark Sorensen for review | Peter Lemme | Totaport
66 |  |  | Schedule ARINC 791 Part 3 Information Transfer and Internetworking
67 |  |  | Schedule final review of ARINC 791 Part 2 and P3 (11:00 AM to 1:00 PM EST) | Jose Godoy | ARINC IA / SAE ITC
68 |  |  | Need a host for the next meeting - candidate: Carlisle in Milwakee - Brad Purpus to advise - Dates October 11-13, 2023 | Brad Purpus | Carlisle
69 |  |  | Peter Lemme to answer NIS APIM 23-004 questions (Vanessa Mastros email) - request that appropriate KSAT personnel attend NIS meetings | Peter Lemme and Jose Godoy | Totaport and ARINC IA / SAE ITC

## Sheet2
Number | ISSUE | Responsible | Company | Date Opened | Due Date | Comments
1 | Security / Domain Segregation | Iridium Source / AGCS Subcommittee |  |  |  | Cooperation with NIS and RTCA SC-216. e for A781 Inmarsat set up guidance from subgroups (e.g., Airframers and others)
2 | Data Priority / Pre-emption (QoS) Domains | AGCS Committee |  |  |  | Based on Iridium NEXT network defined capabilities
3 | Data Priority / Pre-emption (QoS) Time Sensitive Apps | AGCS Committee |  |  |  | Based on Iridium NEXT network defined capabilities
4 | GNSS Filtering (how much Cable loss is allowed 3dBs?) | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
5 | Out of Iridium Band Filtering | Iridium |  |  |  | How do systems coexist non sumltaneously (Inmarsat/Iridium/other) | Iridium to have independent conference with Avionica and report to Subcommittee
6 | Will ARINC 771 embrase existing short burst data services | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
7 | Will ARINC 771 embrase existing circuit switch services | Iridium |  |  |  | Iridium to have independent conference with Avionica and report to Subcommittee
8 | Architecture Selection - narrow down five configurations | Iridium |  |  |  | Airbus: Agree on one configuration for LGA and one for the MGA | Iridium to propose on how to clasify each configuration
9 | Antenna Footprint | Iridium/Cobham / AGCS Subcommittee
Airbus to provide revised proposal, ARINC IA to add to next draft. Jose to post to sharepoint. 29Oct2019: Airbus to present at the joint session with NIS Subcommittee during Jan 2020 meeting at Viasat (see item 201). 11Feb2020: Dr. Timo Warns submitted prposed wording for Appendix A of ARINC 791P2 strawman; to be reviewed during 12Feb2020 WebEx. 12Feb2020:
See 6, 20, 145, 146, 147, 192 and 202. 23Jan2020: To be discussed during 12Feb2020. Chris to submit comments prior to WebEx.
[5 empty] | Chris | Airbus
|  |  |  | Draft Thermal Management Appendix from Airframers perpective (Thermal Mgt / Form Factor SG - now) |  |  |  | See item 134. 29Oct2019: Boeing to provide white paper. See items 134 and 178. 22Jan2020: Add Wording in the main body and an Appendix with guidance. Waiting for Airbus/Boeing to share WhitePaper.
|  |  |  | Propose smaller form factor antenna attachment as an option (Form Factor SG - now) |  |  |  | See 144. Ongoing - Astronics and Victor working together to make proposal/ presentaion at the next face to face meeting. See item 206
In support of 185. Viasat to provide. 16April2020: Contact Eric (use what we have received and post)
|  |  |  | Viasat to research Coax attenuations given in A792 (Section 4.1.1 Coax IF). See action X. |  |  |  | Taking into account available Coax cables and length (100Ft). 29Oct2019: Boeing - longest runs also in 90+ ft. Ongoing. Ranges (i.e., 4 and 6 Ghz) are not spec'd. See A791P2 …if loss is see action than 11 dBs, add more cable or attenuate? Ideally avoid attenuation...Viasat to propose 3 options
Adding Cell as a segregated sub network into A791P2 (ARINC 688 will be ref'd)
Solicit proposal. Delta Air Lines wants maintenance (LRU Level) diagnostic. 29Oct2019: See item 202
16April20: To be provided at June Virtual meeting (See item 180)
No response
215 |  |  |  | Resend Satellite Providers Survey
216
217 | [7 empty] | Using Size 2
218 | [7 empty] | Sent on 23Jan2020
219 |  |  |  |  | KSAT SC | KSAT SC
220 | [5 empty] | ARINC IA
221 | [5 empty] | Totaport |  | 16April2020: Ongoing
222 |  |  |  | Markus to update Airbus A792-1 fittings 3 and 4 proposal
223 |  |  |  |  | Peter Lemme | Totaport |  | Some work has to be done, check if complete. Classic config selected (AMU with Coax and Star Quad).
224 |  |  |  | Arrange Security Conf with Timo Warns, wording into A791P2 Section 5 and Appendix A |  | Airbus |  | 11Feb2020: Timo provided security guidance (new wording) for Appendix A
225 | [5 empty] | Viasat |  | 16April2020: iDirect is revising AMIP. 11Nov2020: Ref AMIP document (remove from Part 2)
226 |  |  |  | Review remote Load (Appendix B of A791P2) |  | Viasat
227 |  |  |  | Contact iDirect and inquire how AMIP will be controlled, advise of KSAT inputs? | Steve Moses | iDirect | 2020-01-23 | 16April2020: iDirect is revising AMIP.
228 |  |  |  | Next Virtual KSAT Face to Face Meeting? |  |  | 2020-01-23 | Looking at week of June 15th or 22nd, ongoing
229 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA | 2020-01-23 | Scehduled for 12 February 2020
KSAT WebConference - 12 February 2020
230 |  |  |  | Review Timo's Interfaces Security inputrs for A791 P2 | KSAT SC | KSAT SC | 2020-02-12 | See 141 and 231
231 |  |  |  | Dr. Timo Warns to submit revised proposed wording | Timo Warns | Airbus | 2020-02-12 | Replace AES and GES, add high level wording in section 5 and ref Appendix A
232 |  |  |  | Peter Lemme to add authentication wording? | Peter Lemme | Totaport | 2020-02-12
233 |  |  |  | Revise A792A APIM | KSAT SC | KSAT SC | 2020-02-12
234 |  |  |  | Submit revised APIM Draft to Paul | Jose Godoy | ARINC IA | 2020-02-12
235 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  | Schedule for 25March2020
KSAT WebConference - 16 April 2020
236 |  |  |  | Draft Attachment/Appendix with Viasat's & Satellite Survey Response values | Eric Cross | Viasat |  | See 186 and 250
237 |  |  |  | Submit APIM 20-001 Final (ARINC 792A multi modem-fiber KSAT System | Jose Godoy | ARINC IA | 2020-04-16
238 |  |  |  | Move to how to use open AMIP (Implementation guidelines) | Steve Moses | iDirect | 2020-04-16
239 |  |  |  | Schedule Next KSAT SC WebConference - 13May2020 | Jose Godoy | ARINC IA | 2020-04-16
KSAT WebConference - 13 May 2020
240 |  |  |  | Schedule next virtual meeting - June 22 thru June 25 (3-4 Hrs each day | Jose Godoy | ARINC IA | 2020-05-13 | SMA Availabe
241 |  |  |  | Update AMUpresentation with webex conference results | Peter Lemme | TOTAPORT | 2020-05-13
242 |  |  |  | AMU: which Modes will be supported | KSAT SC | KSAT SC | 2020-05-13 | 24June2020: See TOTAPORT Presentation (v8)
243 |  |  |  | Based on AMU Modes to be supported, are wiring changes required | KSAT SC | KSAT SC | 2020-05-13
244 |  |  |  | Ask Eric to populate the Sat Antenna Characteristics using what we have | Jose Godoy | ARINC IA | 2020-05-13
245 |  |  |  | Eric (viasat) to populate new Sat Provider interoperability attachment in A791P2 S2D1 | Eric Cross | Viasat | 2020-05-13 | See item 250
246 |  |  |  | Highlight Differences between Ka-bnd and Ku-Band characteristics | KSAT SC | KSAT SC | 2020-05-13
247 |  |  |  | Consider including an Avionics Data Acquisition function in ARINC KSAT Standards | KSAT SC | KSAT SC | 2020-05-13 | Related to ARINC 834A (Aircraft Data Broadcast) project
248 |  |  |  | Schedule Next KSAT SC WebConference - 10June2020 | Jose Godoy | ARINC IA | 2020-05-13
KSAT WebConference - 10 June 2020
250 |  |  |  | Make Satellite Provider Recommendations for InterOp decision (Appendix format) |  |  |  | Compare Viasat, eutelsat and SES Characteristics, 23June2020: Viasat provided Sat Provider inputs throughout body of doc
251 |  |  |  | Draft Virtual Meeting Agenda
252 |  |  |  | Review Items required for release of Supplement 2 to ARINC 791 Part 2 Draft 1
KSAT Virtual Meeting: June 23, 2020
255 |  |  |  | Review Inuts to Supplement 2 to ARINC 791 Part 2
256 |  |  |  | Should A771 (Iridium) and 741/761 (L-Band) Satcom be added to list of ref Docs | Jose
257 |  |  |  | Review Section 2.2 wording - Satcom System Interfaces/Channels
258 |  |  |  | Section 2.2 Figures 2-4, 2-6, 2-8: add ARINC 848 MISON | Peter Lemme | TOTAPORT
159 |  |  |  | Show Router Domain to Figure 2-9 (Etherner Domain Schematic
260 |  |  |  | Review new Elevation beamwidth characteristics (Section 2.8,1)
261 |  |  |  | Review VIASAT Sat provider Survey Inputs
262 |  |  |  | Are eutelsat and SES recommendations included | Jose and Gary
263 |  |  |  | Section 2.82 (Consider Renaming and add Ka characteristics
264 |  |  |  | Section 2.82 - Review Ka/Ku band dBW/MHz peak EIRP values
265 |  |  |  | Section 2.8.3 Polarization - use 10 or 100 millisec switching time | Viasat |  |  | Ask LEO Suppliers. Also add Ku Staement?. Viasat to consult with other providers
266 |  |  |  | SECTION 3.8 - Review Second/Maintenance Channel System wording |  |  |  | Change Channel to System
267 |  |  |  | Section 4.3: Need to decide on the GbE interface to the AMU for 791
268 |  |  |  | Section 4.5.1 and 4.5.3 - review / add IPv6 info | Jose |  |  | Consult with NIS
269 |  |  |  | Section 7.1: Review Viasat inputs and should Ku Band equivelant info be added? | KSAT SC
270 |  |  |  | Section 7.1: Review proposed Note 4 |  |  |  | reworded
271 |  |  |  | Section 7.3.1 - Ref Frequecies: Reconsile with AMU
272 |  |  |  | Table 7-5: Review new Table Values (Collins Proposal?)
273 |  |  |  | Table 7-7: Review Table Values (Under review?) |  |  |  | IF Signal Additional Characteristics – Tx
274 |  |  |  | Section 7.4.7 Ant SubSys Lo Freq - use 10 or 100 millisec switching time
275 |  |  |  | Table 7-9: Review Table Values (Under review?)
276
277 |  |  |  | Review Section 11 - QoS | Jose |  |  | Jose to implement initial compare for draft 2
278 |  |  |  | Fiber Optics Presentation
279 |  |  |  | Action Item based on Kontron AMU white paper - Ack | Jose |  |  | Jose to advise Kontron that existing AMU v8 will be specified
280 |  |  |  | Do we need to provision to an additional AMU discrete, define In or Out is required? |  |  |  | KSAT SC decided
281 |  |  |  | assess, then to revise AMU presentation - wiring between AMU and Modman does not change. Provision for only 2 AMUs |  |  |  | Provision for only 2 AMUs. New discrete will be labled Man Specifiic. How many pins are affordable
282 |  |  |  | Kontron connector, specify as alternate? |  |  |  | Subcommittee/ Kintron to decide
283 |  |  |  | Should a connector with fiber be added to Kontron FormFactor, add fiber to existing middle plug? |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
284 |  |  |  | Discuss existing Kontron and Hughes ARINC 600 Connectors further |  |  |  | Jose to advise Kontron that existing AMU v8 will be specified. Could be added as an aleternate in Appendix
285 |  |  |  | Mitsubishi Comment: Review Power over Ethernet feasibility - High Voltage ? GEO issue?
286 |  |  |  | Comments on Mitsubishi proposal GPS at the Gate/MEO issue (no HDG) ?
287 |  |  |  | Brad Purpus - Carlisle to provide alternate sealant (feedthru cableing) presentation |  |  |  | fusalege penetration solution (to support Fiber Feedthru). Depending on availability. 19July2020: Provided compression fittings white paper on 18July2020.
288 |  |  |  | Michael - Boeing to provide alternate sealant (feedthru cableing) presentation |  |  |  | If feasible for July 22nd conf
289 |  |  |  | A791P2 Section 6 - Josh (Honeywell) to propose wording
290 |  |  |  | Schedule next Conference Call - July 22nd at 11:00 AM EST USA
291 |  |  |  | ADD MIB to next meeting/web conf agenda
292 |  |  |  | Thermal Management - Create Subgroup led by airframers. Subgroup to brief Subcommittee | Markus Altmann and Michael Reinbold | Airbus and Boeing |  | Contact Markus, Lead to be added to subgroup
293 |  |  |  | Schedule Next KSAT SC WebConference - 22July2020 | Jose Godoy | ARINC IA | 2020-07-02
KSAT WebConference - 22July2020
295 |  |  |  | Review and Comments on Carlisle Pass through presentation | KSAT SC | KSAT SC |  | Compression pass throughs white paper
296 |  |  |  | Carlisle to provide pertinent leakage information | Brad | Carlisle
297 |  |  |  | Create feedthrough requirements that supports multiple cable types (fiber, coax, cooper)
298 |  |  |  | Standardize passthrough method | KSAT SC | KSAT SC |  | Define hole/s location/diameter, drill pattern, doubler needed?
299 |  |  |  | Schedule Thermal/Form Factor Subgroup Web Conferenece | Markus Altmann | Airbus
300 |  |  |  | Contact Smitty (coordination with Fiber Connector Subcommittees/working group) | Jose Godoy | ARINC IA |  | Initial contact made; presentation shared
302 |  |  |  | Schedule Next KSAT SC WebConference - 2Sept2020 | Jose Godoy | ARINC IA
KSAT WebConference - 2Sept2020
303 |  |  |  | Review posted Draft 1 of Supplement 2 to ARINC Characteristic 791, Part 2 | KSAT SC | KSAT SC
304 |  |  |  | Decision on AMU Connectors Cavity A, B and C |  |  |  | Decide on Oct 7th meeting?
205 |  |  |  | Thermal/Form Factor Meeting |  |  |  | Next Subgroup Meeting held 9Sept 2020
306 |  |  |  | Decide -792 in 791P2 or (new 792 Part 2 needed) |  |  |  | Arrange meeting with AEEC Exec Director
309 |  |  |  | Schedule Next KSAT SC WebConference - 7Oct2020 | Jose Godoy | ARINC IA
KSAT WebConference - 7Oct2020
310 |  |  |  | Report on Sept 9th Subgroup Meeting Meeting
311 |  |  |  | Present and Review Kontron white paper update
312 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA |  | Next Web Meeting 11Nov2020
KSAT WebConference - 11Nov2020
320 |  |  |  | Update APIM 16-006A
321 |  |  |  | Chris Schaupmann (Airbus) to provide initial Fiber Connection Requirements white paper | Chris Schaupmann | Airbus
322 |  |  |  | Schedule Next KSAT SC WebConference | Jose Godoy | ARINC IA
323 |  |  |  | Coordinate with FOS and CSS | Jose and Smitty | ARINC IA |  | 3Dec2020: Ongoing See item
324 |  |  |  | Schedule Next KSAT Vitual Meetig | Jose Godoy | ARINC IA |  | Meetings Dec 2-3, 2020 and 5-6Jan2021
325 |  |  |  | Carlile to submit white paper for next thermal subgroup meeting
KSAT Virtual Meeting - December 2-3, 2020
330 |  |  |  | Victor to contact Markus/Subgroup and identify issue (jose send email to parties)
331 |  |  |  | Peter to provide updates to A791P2 (Josh, Anh, and Matt to assist)
332 |  |  |  | Loren to provide A792 strawman (AMU material)
333 |  |  |  | Jose to add other inputs (i.e., Viasat) to A791P2 Strawman after Peter makes it available
334 |  |  |  | Work with Fiber group, identify requirements / maybe APIM
335 |  |  |  | Chris to update Fiber presentation (see 321)
336 |  |  |  | What AMU Modes to be supported, are wiring changes required (see 242, 243)
337 |  |  |  | ARINC 629 is being removed
338 |  |  |  | Submit APIM 16-006A (see item 320)
339 |  |  |  | Boeing, Matt Landel (astronics) and Airbus will further develop MIB section
340 |  |  |  | Draft agenda for Jan 5-6, 2021
341 |  |  |  | Update KSAT SharePoint with meeting white papers and presentations (e.g., Mitsubitshi fittings)
342 |  |  |  | Add KSAT SharePoint folders for Action Items, Fiber, AMU, etc
343 |  |  |  | Schedule Next KSAT SC Teams Meetings (Jan 5 and 6, 2021)
344 |  |  |  | Develop Draft 2 of Supplement 2 to ARINC Characteristic 791 Part 2
345 |  |  |  | Update APIM 16-006A
346 |  |  |  | Standardize passthrough method (see item 298)
347 |  |  |  | Create feedthrough requirements; supports multiple cable types (fiber, coax, cooper) see item 297
348 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 5, 2021 (Day 1 of 2) | Jose Godoy | ARINC IA / SAE ITC
KSAT Virtual Meeting - January 5-6, 2021
350 |  |  |  | Thermal and Form Factor SuGroup to provide briefing to KSAT Subcommittee
351 |  |  |  | Review A791P2 strawman - develop Draft 2
352 |  |  |  | Review A792-1 Draft 1
353
354 |  |  |  | Submit revised A791P2-2 APIM to SAI
355 |  |  |  | Submit ARINC 791 P2 D2 S2
356 |  |  |  | Submit ARINC 792 D1 S1
357 |  |  |  | Schedule Next KSAT Vitual Meeting - Jan 22, 2021
FOS Kickoff Meeting - February 9, 2021
360 |  |  |  | FOS to develop quentionaire
361 |  |  |  | KSAT will use FOS questionaire to generate requirements list for FOS recommendations
362 |  |  |  | Schedule Next KSAT Vitual Meeting - March 3, 2021
KSAT Conference - March 3, 2021
364 |  |  |  | Expand FO requirements list for FOS | Subcommittee | Subcommittee |  | e.g., list signal type
365 |  |  |  | Schedule Next KSAT AMU Confernece - April 7, 2021 |  |  |  | Changed from March 31st due to conflict with Thermo Management / Form Factor
KSAT at IPS Sucommittee Meeting - March 18, 2021
367 |  |  |  | Review Honeywell Inputs to APIM 16-006A | KSAT Subcommittee | KSAT Subcommittee
368 |  |  |  | Complere APIM (revise or leave as is) | KSAT Subcommittee | KSAT Subcommittee
FOS Meeting - March 24, 2021
370 |  |  |  | Expand FOS/KSAT Matrix |  |  |  | See item # 375
371 |  |  |  | Label each of the 26 connections and describe (Ethernet/RF, Freq/Speed, # of disconnects, type) | KSAT Subcommittee | KSAT Subcommittee |  | worst case length from pr
372 |  |  |  | Provide Link Budget, include in requirements matrix for FOS
373 |  |  |  | Distribute KSAT / Fiber Requirements Matrix | Jose and Smitty | ARINC IA/SAE ITC
KSAT Conference - April 7, 2021
375 |  |  |  | Expand FO requirements list for FOS | FOS & KSAT | FOS & KSAT
379 |  |  |  | Schedule Next KSAT Online Conference (10May2021)
380 |  |  |  | Schedule Next KSAT Virtual Meeting (multi-Day)
KSAT Conference - May 10, 2021
381 |  |  |  | No FOS Requirements Updates (no new inputs, didn't update during meeting)
382 |  |  |  | Review 792 Network Architecture
383 |  |  |  | Loren to present A792 Strawman
384 |  |  |  | Loren to provide A792 Draft foir distribution and formating
385 |  |  |  | Add Attachment/Appendix sections (i.e, keyline definition) to Loren's A792 Draft and distribute
386 |  |  |  | Michael (Boeing) to check if keyline is already defined in ARINC XXX
387 |  |  |  | Add Power Budget (suggested by Loren), Peter to implement
388 |  |  |  | Totaport to provide updatred mural pdf
389 |  |  |  | Distribute revised "mural" A792 pdf
390 |  |  |  | Change AMU to Auxilary Modem Unit (globally - ARINC 792 and 792A)
391 |  |  |  | Plan briefing by Markus (Thermo and Form Factor recommendations)
392 |  |  |  | Plan joint session with NIS
393 |  |  |  | Need help with IPv6 editing siggestions
394 |  |  |  | Schedule Next KSAT Online Conference (May 21 11:00AM - 1:00PM EST
395 |  |  |  | Schedule Next KSAT Virtual Meeting (multi-Day)
KSAT Conference - June 21, 2021
400 |  |  |  | Add GeorgeNicola (OneWeb) and Brad Smith (Viasa) to AEEC KSAT Teams
401 |  |  |  | Provide Updated FO Requirements Matrix to Ron (GlenAir) and Subcommittee
402 |  |  |  | Jose and ARINC Staff to address ref issue (See Loren's email)
403 |  |  |  | Loren Ayotte,intelsat, to update A792-1 Figures + AMU 1per conferece decisions
404 |  |  |  | Add Meeting Docs to Teams
405 |  |  |  | Schedule Next KSAT Online Conference (July 19, 11:00AM - 1:00PM EST)
406
KSAT Conference - July 19, 2021
410 |  |  |  | Announce New Co-Chair
411 |  |  |  | Loren to contact Bob with info for cavity 2 (support fiber and be able to convert to (Quadrax) 792 pre Supplement 1)
412 |  |  |  | Schedule leadership Meeting (Thurday 29July2021)
413 |  |  |  | Distribute July 21st FOS meeting invitation
414 |  |  |  | Ron Logan to update FO Requirements Matrix (LF ) based on Trevor's email
415 |  |  |  | Schedule next Meeting (Sept 21-23)
416 |  |  |  | Jonathan to Verify req speeds for IQ transmission or suggest abandoning I/Q because rates for supporting greater than 10G/sec in this environment are challenging
417 |  |  |  | Totaport to comment on Jonathan's calculations (see above item)
418 |  |  |  | Annotate the arc block diagram with signal description (including IQ, Ethernet or other)
419
420 |  |  |  | Schedule next KSAT meeting (MIBs and AMU ) - 12Aug2021 (11:00 AM EST USA)
421 |  |  |  | Extensive MIBs update required - add to agenda (12August)
425 |  |  |  | Contact IPS and NIS so they can brief group on Status (tenatively for Sept 21st after intro)
KSAT Conference - Aug 12, 2021
430 |  |  |  | invite NIS and IPS (IPv6) present at Sept 21-23 meeting
431 |  |  |  | invite to preset: FOS and Thermal Management and Form Factor and EFB A834A
432 |  |  |  | What to about MIBs Section/s; align A792 add new LRUs)
433 |  |  |  | need volunteer for MIBs - What information (protocols) are required for MIBser LRU - Josh to look at work and advise, Chris will again request internal support, Mike wil look at Boeing requirements - inputs
434 |  |  |  | MIBs list of Concerns (see 433) + Create Working Group (Peter, Josh, Michael, Chris, ?)
435 |  |  |  | Distribute invite for MIBs SubGroup - Peter to coordinate with Josh and send info to Jose for invitation distribution
436 |  |  |  | Threat analysis - categorize each threat analysis / level of threats and what if flow chart
437 |  |  |  | Request modem suppliers attend a dedicated session during sept meeting ( Hughes and iDirect, Viasat, OneWeb,
438 |  |  |  | Can KPSU be changed? 5 Kg at 2200 Watts
439 |  |  |  | Announce and distribute next FOS (17August) | Jose Godoy | ARINC IA / SAE ITC
440 |  |  |  | Post Sept 21-23 SMA (Meeting Announcement) | Jose Godoy | ARINC IA / SAE ITC
KSAT LEADERSHIP September 2 and 9, 2021
441 |  |  |  | invite NIS and IPS (IPv6) , Markus-Airbus (Thermal and Form Factor); Fiber to present staus on Sept 21st | Jose Godoy | ARINC IA / SAE ITC
442 |  |  |  | Contact Modem and Sat Providers (iDirect, SES, HUGHES, Viasat, OneWeb, StarLink, gLat, NewTech) seamless
443 |  |  |  | Create AGENDA (6 Session) Day 1 FF/Thermal, NIS, IPS); Day 2: Fiber and A792; Day 3: MIBs, Schedule, Action Items) | Jose Godoy | ARINC IA / SAE ITC
444 |  |  |  | Contact Loren - A792 | Jose Godoy | ARINC IA / SAE ITC
445 |  |  |  | Contact Peter and Josh - when is the next subgroup meeting - who's particpating | Jose Godoy | ARINC IA / SAE ITC
446 |  |  |  | AMIP - what to do with MIBs, align 792 and A791P2 (only high level ? ) | KSAT Subcommittee | KSAT Subcommittee
447 |  |  |  | Schedule Leadership Meeting (Sept 9th at 9:30AM EST) | Jose Godoy | ARINC IA / SAE ITC
|  |  |  | Load A792-1 Strawman to KSAT Teams | Jose Godoy | ARINC IA / SAE ITC
KSAT Virtual Meeting - September 21-23, 2021
450 |  |  |  | Boeing and Airbus Action to study the installs for KPSU and KRFUs. Weight Issue went from 4.5 to 5, what next 7, 8 ? | Chris and Mike | Airbus and The Boeing Company
451 |  |  |  | Boeing and Airbus to arrange Thermal Management Meeting (Markus and Brenda) include Brad Purpuse, Matt Landell) | Markus Altmann and Mike Reinbold | Airbus and The Boeing Company
452 |  |  |  | Make Form Factor and Thermal Presentations avalable (including July 1st email summary) | Markus Altmann and Jose Godoy | Airbus and ARINC IA/SAE ITC
453 |  |  |  | Brad Purpose to provide Form Factor inputs) | Brad Purpus | Carlisle
454 |  |  |  | ARINC I A Staff to work on A792-1 strawman and share with Loren to assure links and figures are correct before posting | Jose Godoy | ARINC IA / SAE ITC
455 |  |  |  | ARINC IA to post ARINC 792-1 strawman can Attachment 1A and 1B be used | Jose Godoy | ARINC IA / SAE ITC
456 |  |  |  | Reach out to iDirect and wavestream (Keith King) for keyline timing verification | Greg Otto | VIASAT
457 |  |  |  | Request Subcommittee (Peter Lemme) present to SAI Subcommittee (ask to join a future SAI meeting - after Mid-Term | Jose Godoy | ARINC IA / SAE ITC
458 |  |  |  | Contact modem suppliers and provide FOS matrix so they may include their requirments (data rates) | Leadership
459 |  |  |  | Subcommittee to comment on P. Lemme's mural document on Teams | KSAT Subcommittee | KSAT Subcommittee
460 |  |  |  | Peter and Josh to arrange MIBs subgroup conference/s for thise that need to attend (matt to help Peter and Josh) - Working | Peter Lemme and Josh Laing | TOTAPORT and Honeywell
461 |  |  |  | Who can be added as A792A Industry Editor (per Section/Paragrpah/topic) Chris and Mike to lead effort | TBD
462 |  |  |  | Ron Logan (GlenAir) to provide updated Matrix (KSAT Optics requirements) | Ron Logan | GlenAir
463 |  |  |  | Recieve briefing on status of Staellite Providers Survey from Eric Cross, Viasat | Eric Cross | VIASAT
464 |  |  |  | Eric Cross to revise Survey and send to ARINC IA (Jose) for distribution | Eric Cross | VIASAT
465 |  |  |  | Send Satellite Providers Survey to Telesat, StarLink, MicroSoft, OneWeb, etc - info received form SES, Eutelsat and Viasat | Eric Cross | VIASAT |  | Eric Cross to provide and Jose to distribute
466 |  |  |  | Schedule the next Leadership Meeting 9:00 AM on Monday, Sept 27th) | Jose Godoy | ARINC IA / SAE ITC
467 |  |  |  | Schedule the next KSAT Subcommittee Confernce = October 19th 11:00 AM EST) | Jose Godoy | ARINC IA / SAE ITC
468 |  |  |  | Schedule the next KSAT Subcommittee Meeting (Dec 13-15, 2021) | Jose Godoy | ARINC IA / SAE ITC
KSAT LEADERSHIP September 28 and October 12, 2021
470 |  |  |  | Add spice to production breaks calcuations (wiring)
471 |  |  |  | Add drawing illustrating production breaks, disconnects (expand patch panel)
472 |  |  |  | Create Modem Survuey (information request) | Mike Reinbold and Chris Schaupmann | The Boeing Company and Airbus
473 |  |  |  | Section 3 - Pass Through ask Structural - including Brad Purpus | Brad Purpus | Carlisle
474 |  |  |  | Section 4 - Modem / Modem Manager | Modem Suppliers | Modem Suppliers
475 |  |  |  | Assign Modem Experts for industry editors for section 4 (Gilat, Hughes, iDirect, SES, etc. | Modem Suppliers | Modem Suppliers
476 |  |  |  | Drafted leter , send to modem distribution today on 12 October or early 10/13 | Jose Godoy | ARINC IA / SAE ITC
477 |  |  |  | Conatact Peter and Josh for MIBs meeting | Mike Reinbold | The Boeing Company
478 |  |  |  | Assign to section 5 (AMU)
479 |  |  |  | Ask Loren to review 5.1.1.5. AMU to Modem Interfaces
480 |  |  |  | 6 Section - KPSU: Challenge KPSU maybe Jonathan Epstein) Airbus and Boeing toalso support | Loren Ayotte
481 |  |  |  | 7 APIM - no forseen changes
482 |  |  |  | 8 - grounding and Bonding (any deltas due to fiber instead of fiber) Airframers to lead (mike and Chris) | Mike Reinbold and Chris Schaupmann | The Boeing Company and Airbus
483 |  |  |  | 9 - Installation and Alignment (
484 |  |  |  | 10 Maintenance and test (use existing 792 Text ask for Airline input
485 |  |  |  | Update Agenda
KSAT Online Conference - October 19, 2021
490 |  |  |  | Review Modem Suppliers survey - Hughes advised that 10Gb/sec satisfies all their current products, will continue internal inquiry
491 |  |  |  | Need more inputs from Modem Suppliersd
492 |  |  |  | Add Marcio Ferraz Gobato, Embraer, to AEEC KSAT
493 |  |  |  | What Fiber Type (multi-mode), ARINC 846?, 12 One Direction (Tx and Rx) or 4 x 4 (6 Tx and 6 Rx not available)
494 |  |  |  | Final Decision on disconnects (4 is minimum and 10 is default max)
495 |  |  |  | Decide on number of Beams to be supported, at Least 2 or 3, up to 6 (Main, HO, 2nd, 2nd HO, ATC and Broadcast)
496
497 |  |  |  | Need to purge excessive excessive information from MIBs Section - Need a volunteer to lead MIBs edits (use cases) and organize SG meetings (Update MIBs table) |  |  |  | MIBS Section must meet operator (Mechanic & Flt Crew requirements, Is it an outage, A/C issue, LRU @ fault, degraded operation, identify LRU trends
498 |  |  |  | Review proposed new Appendix provided by Peter Lemme (totaport)
499
500 |  |  |  | Schedule the next KSAT Subcommittee Conference: November 17 (11:00 AM EST) | Jose Godoy | ARINC IA / SAE ITC
501 |  |  |  | Next KSAT Subcommittee Meeting is Dec 13-15, 2021 - Create SMA | Jose Godoy | ARINC IA / SAE ITC
502
KSAT Leadership - October 28, November 4, and November 11, 2021
505 |  |  |  | Send Survey and invitation to Glat' - Suggext 9:00 AM EST on Nov 2 or 3rd (Tuesday or Wednesday) | Jose Godoy | ARINC IA / SAE ITC
506 |  |  |  | Create November 17 Meeting Draft Agenda | Jose Godoy | ARINC IA / SAE ITC
507 |  |  |  | Create December Meeting Draft Agenda (six sessions , 2 per day, 3 days)
508 |  |  |  | Send reminder with Agenda, highlight that mature drafts for A791P2 and A792-1 are due in late March to meet schedule (2022 AEEC GS) | Jose Godoy | ARINC IA / SAE ITC
509 |  |  |  | Remind FOS Leadership and Markus Altmann of November 17th meeting | Jose and Chris | ARINC IA / SAE ITC and Airbus
510 |  |  |  | Discuss Intersystem Protocol commonality (Industry) led by Airframers - coordinate with IPS?
511 |  |  |  | Complete Nov 17 Agenda (add A791P2 (by Chapters) and A792-1 (Is it mature for 2022 GS adoption) | Jose Godoy | ARINC IA / SAE ITC
512 |  |  |  | Distribute Nov 17 agenda | Jose Godoy | ARINC IA / SAE ITC
513 |  |  |  | Modem Suppliers Survey (4 out of 5 agree current propoal 10G/sec is adequate for present and short term (approx. next 5 years )
514 |  |  |  | Draft December Meeting Agenda | Jose Godoy | ARINC IA / SAE ITC
515 |  |  |  | Update A792A architecture (remove Extar Radio to reduce wiring to 24 connections (AMU 1/2, Modem, OAE Manager, + 2 spares) | Chris Schaupmann | Airbus
KSAT Meeting - Dec 13-15, 2021
520 |  |  |  | Share Boeing Thermal Presentation add to Teams KSAT Dec2021 Meeting Folder | Jose Godoy | ARINC IA / SAE ITC
521 |  |  |  | Share Airbus Thermal Slides add to Teams KSAT Dec2021 Meeting Folder | Jose Godoy | ARINC IA / SAE ITC
522 |  |  |  | Share Carlisle Thermal Presentation (Adapter - radome) and add to Teams KSAT Dec2021 Meeting Folder (after updated with weight) | Jose Godoy | ARINC IA / SAE ITC
523 |  |  |  | Add High Level Guidance to Standard on thermal assessment modeling + temp limit agreeed by OEMs ( 180 degrees F) | Markus
524 |  |  |  | Include designassurance level for shutoff mechanism before fatiguing skin (is it the same temp for all fuselage) led Markus and Brenda
525 |  |  |  | OEMs to Draft value (numbers for blue and violet vectors (Heat Transfer along and through A/C skin)
526 |  |  |  | Boeing and Embraer to review Airbus proposal (when Airbus makes suggestions) Heat Transfer Coefficient/factor + temperatures - Blk fuselage in Dubai
527 |  |  |  | Include Use cases (operators that use A/C to kool aircraft or equipment)
528 |  |  |  | ARINC 792 Form Factor: What to do with reduction from 6 to 4 settings; Boeing believes that this belongs in a different standard (differnet loads than in A792)
529 |  |  |  | Embraer to share presentations with internal structural department for comments | Jose Godoy | ARINC IA / SAE ITC
530 |  |  |  | Distribute older Airbus white paper with fittings options (reduction by eliminating 4 and 6, or bring them inward)
531 |  |  |  | Get Brad's alternate fittings paper
532 |  |  |  | OEMs to have an offline Fittings Reduction (Airbus and Boeing as Embraer will shut down til January 25)
533 |  |  |  | Jonathan to add commentary on effects of Cable Length
534 |  |  |  | Embraer to verify if 10 Kg for the KPSU is acceptable for their configurations
535 |  |  |  | Loren to revise ARINC 792A-1 Strawman with weight and power commentary
536 |  |  |  | Share Loren's A792-1 Updates White Paper and add to Teams KSAT Dec2021 Meeting Folder
537 |  |  |  | Include Thermal Guidance in Draft 2 o Draft 3 (based on timimg os OEMs assessment)
538 |  |  |  | Embraer to submit Qual Test info (RTCA DO-160 Table) | Marcio Ferraz Gobato | Embraer
539 |  |  |  | Subcommittee to review and comment on ARINC 792-1 Strawman as reviwed and updated by Loren Ayotte)
540
541 |  |  |  | DAY 2
542
543 |  |  |  | Reference FO link in the digital representation, what are the characteristics?
544 |  |  |  | Based on 543, Study the fiber optics are tere more requirements?
545 |  |  |  | Contact Jack Mandela (SeamLess) regarding alignment on interfaces and messages | Chris
546 |  |  |  | Leadership to contact Peter to assure any changes that he has made are incorporated into the A791P2-2 Strawman
547 |  |  |  | Josh to populate Teams Folder with the 3 Sections he has A582:E586
Eric Cross (Viasat) to send LEO contacts so that they may complete SAT Providers Survey
TeleSAT, OneWeb, SES, Amazon, SatLink, Inmarsat should be contacted
Jose to send email with Survey to SAT Providers
DAY 3
|  |  |  | PP792A: Section 3 - Revise existing Legacy IF Diagram and add fiber | Brad
|  |  |  | PP792A: Section 3 - Revise existing Legacy IF Diagram and create the digital version (Two Fifures 31a and 31b) base band | Ron
Peter Lemme (totaport) to provide source doc for the figure in Section 3.1 (Jonathan, Peter, Ron, Gary) managed by Brad
Kevin Tat (Hughes) leads Section 4 - Modman
Consult with iDirect/Gilat and confirm Section 4 is acceptable? (per Gary, Kevin)
Provide iDirect/Gilat contact (and LEOs) - OneWeb to mediate
preserve existing

## Compatibility Report
Compatibility Report for AGCS SC_Action Items _ 20Aug2017.xls
Run on 8/21/2017 21:25
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 3 | Excel 97-2003