## Slide 1: Global Aircraft Tracking Working Group SAI Subcommittee
Jessie Turner
AEEC SAI/Executive Committee
The Boeing Company
AEEC General Session
April 24, 2018
Chuck Adler – GAT WG Chairman
The Boeing Company
Peter H. Grau – Secretary
ARINC Industry Activities

## Slide 2: Overview
  Autonomous Distress Tracking (ADT) activities in-work per APIM 17-004. Supports Jan. 1, 2021 forward-fit ICAO and European Union mandates
  Timely Recovery of Flight Data (TRFD) planning activities have initiated per APIM 17-005. Supports Jan. 1, 2021 ICAO mandate for new Type Cert applications
  ADT Phase 1: Initial Requirements - Complete
  ADT Phase 2: Proposed Architectures - In-Progress (ECD Oct. 2018) with Architecture Teams developing architectures for:
      Emergency Locator Transmitter – Distress Tracker (ELT-DT)
      Spaced-Based Automatic Dependent Surveillance – Broadcast (SB ADS-B)
      SATCOM-based (Inmarsat & Iridium) Trackers
      Dissimilar-complimentary/minimal change approaches
  ADT Phase 3: Detailed Aircraft Interfaces & Installation Requirements (ECD Jan. 2019)

## Slide 3: 2017-2018 Activity and Accomplishments
  Issued two drafts of Project Paper 680 (Architectures Report)
  Five face-to-face meetings:
      June 2017 – Denver (Panasonic)
      August 2017 – Seattle (Boeing)
      November 2017 – Hamburg (Airbus)
      February 2018 – Miami (Gables Engineering)
      April 2018 – London (Inmarsat)
  Weekly WebEx meetings
  Five Architectural Working Groups developing details
  Participation of 22 organizations across (2) airlines, (12) suppliers, (3) airframers, (3) service providers, NTSB, and FAA
  Harmonization efforts with EASA, BEA, and others

## Slide 4
AEEC Mid Term Session
APIMs Submitted
2018
J F M A M J J A S O N D
2019
J F M A M J J A S O N D
2017
J F M A M J J A S O N D
2016
J F M A M J J A S O N D
AEEC General Session
ARINC APIMs Approval
2020
J F M A M J J A S O N D
2021
J F M A M J
ADT Phase 1 (Requirements)
ADT Phase 2 (Architecture Selection)
ADT Phase 3 Develop ARINC Characteristic(s)
ICAO ADT Production Applicability
ADT EIS
ARINC AEEC
ARINC AEEC Autonomous Distress Tracker (ADT)
(APIM 17-004)
Timely Recovery of Flight Data (TRFD)
(APIM 17-005)
ADT Phase 1 (Requirements) Pre-Meeting
AEEC Mid Term Session
ADT Phase 1 Report Out
TRFD Phase 1 (Requirements)
TRFD Phase 2 (Architecture Selection)
TRFD Phase 3 Develop ARINC Characteristic(s)
ICAO TRFD New Type Cert Applicability
AEEC General Session
ADT Phase 1 and 2 Report Approval
AEEC General Session
ADT Characteristics Approval
TRFD Phase 1 Report
AEEC General Session
TRFD Phase 1 and 2 Report Approval
AEEC Mid term Session
TRFD Characteristics Approval
APIM 17-004 Autonomous Distress Tracker
APIM 17-005 Timely Recovery of Flight Data
Project Schedule Overview
Oct.
2018
Complete
Mid-Term Session

## Slide 5: Detailed Near-Term Schedule
2018
APR 23-26
AEEC GEN SESSION
JUNE 11-13
FEDEX
SAI+GAT
Memphis
Skytrac
Kelowna, BC
ADT Detail Char. Completion
Submitted to ARINC
JAN 2019
ADT Standards
Start
MAR
APR
MAY
JUN
JUL
AUG
SEPT
OCT
NOV
DEC
JAN
TRFD REQ Finish
TRFD ARCH Start
Inmarsat
London
Iridium
Wash DC
Dec 4-6
Inmarsat
Hawaii
Oct 23-25
APR 10,11,12
August 21-23
Requirements and Architectural Report Submitted
Arch Report Approval
AEEC Mid-Term SESSION
Meetings
MAR
APR
MAY
JUN
JUL
AUG
SEPT
OCT
NOV
DEC
JAN
FEB
ADT Reqts and Arch Report Timeline
Review updates, Doc 10054, updates
Gen edit/arch updates
Team reviews, integration and refinement
draft 2
draft 3
Final updates, team edits, SAI edits/input
Final draft
REV NEW
SAE/ ARINC Edit and Release
Common interface list, draft straw horse and assumptions
By-architecture Interface Proposals
Cross-architecture Interface Integration
draft 1
Integration and Refinement
draft 2
Integration and Refinement, SAI, External Reviews
ADT Detailed Characteristics (Interfaces, Power, Form Factor) Timeline
draft 3
draft 4
Final draft
SAE/ ARINC Edit and Release

## Slide 6
Industry/Regulatory Related Time Lines
Jan 2021 ADT Mandates
2011
2012
2013
2014
2015
2010
2016
2017
2018
LF-ULD Mandates
ICAO Annex 6
TSO-C142a
(NRLB)
2008
FAA
NRLB
SC, MOC
DO-227A
NRLB MOPS
TSO-142B
NRLB
Regulator and Industry
Lithium Battery Requirements
Industry
Distress Tracking Related Requirements
2019
2020
Normal Tracking Mandates
ICAO Annex
6 ,11
ADT,
TRFD
90 day ULBs
LF-ULD
ICAO GADSS CONOPS V6
ICAO 10054
EASA CS, AMC/GM for ADT
EU Regulation 2015/2338
Location of A/C in Distress
ED-237
Distress Trigger MASPS
ED-62
ELT-DT
MOPS
(SC-229)
18 months!
International Regulator
SARPS, Rules and Mandates
NRLB – Non-Rechargeable Lithium Batteries
ULB – Underwater Locator Beacons
LF-ULD – Low-Frequency-Underwater Locating Device
DOES NOT SUPPORT JAN. 2021 MANDATE IMPLEMENTATION
(Min. 30 months required)

## Slide 7: Risks and Issues
  Extremely tight schedule, but feasible for standards development
  Outstanding requirements and guidance from ICAO/Regulators – potential for late breaking requirements requiring implementation updates close to regulation dates:
          ICAO Doc. 10054 (ECD May 2018)
          EASA Certification Specifications (CS), Acceptable Means of Compliance (AMC), Guidance Material (GM) (ECD June 2019). Doesn’t support a Jan. 2021 forward-fit implementation! Minimum of 30 months required from release of EASA CSs and AMC/GM.
  Outstanding GADSS distress data repository ownership and implementation
  Impact of new lithium battery regulations on meeting autonomy requirements and on certification time flows

## Slide 8: Thank You! Questions / Comments?