## Sheet1
Action Item | Description | Responsible | Company | Date Opened | Due Date | Comments
1 | Send APIM template to Traffic and Surveillance WG | Jose Godoy | ARINC IA | 2014-05-21 | Closed 21May14
2 | Complete draft A735B-2 APIM | Darrick Krause and Jessie Terner | ACSS and Boeing | 2014-05-21 | Closed 24June14 | Jessie Provided revised APIM to be reviewed during 25June WebEx and Presented to SAI Subcommittee meeting
3 | Review TCAS/Traffic Computer ARINC 429 Bus for LRU inputs | Darrick Krause | ACSS | 2014-05-21 | Closed 18June14 | Darrick provided revised proposal with Label 351 with new Source information.
4 | Determine Traffic/TCAS Computer strapping requirements | Randy Jacobson | Rockwell Collins | 2014-05-21 | Closed 01Dec2014 | 25June14: Provided by Rockwell Collins on 25June14. Traffic and Surveillance WG to review. 01Dec2014: Item is closed. ASee items 18 and 19.
5 | Decide what to name TCAS input for Hybrid Surveillance fault annunciation | Traffic and Surveillance Work Group | Traffic and Surveillance Work Group | 2014-05-21 | Closed on 6/25/2014 | List as TCAS Hybrid Surveillance or GPS Input
6 | Decide if new ARINC 429 Maintenance discrete is required, or use existing Label 350 and/or 162 | Traffic and Surveillance Work Group | Traffic and Surveillance Work Group | 2014-05-21 | Closed 18June14 | Create Maintenace Label 351? 25June14: ACSS proposes new A429 Label 351
7 | Create A735B-2 Action Items List | Jose Godoy | ARINC IA | 2014-05-21 | Closed 21May14
8 | Schedule Next Online Conference | Jose Godoy | ARINC IA | 2014-05-21 | Closed 21May14 | Scheduled for June 25, 2014
9 | Advise WG date of next SAI meeting | Jose Godoy | ARINC IA | 2014-05-21 | Closed 21May14 | June 24-26, 2014 in Renton, Washington
10 | Present draft APIM to AEEC SAI Subcommittee | Jessie Turner | The Boeing Company | 2014-05-21 | 2014-06-25 | Dependent on Action Item # 2 25June14: Presented to SAI during WebEx Conference
11 | Rockwell Collins to propose new Maintenance Discrete Label for TCAS Inputs Status | Randy Jacobson | Rockwell Collins | 2014-06-25 | Closed 01Dec2014 | Avionics OEM to agree on A429 Label that is presently not utilized by ACSS, Honeywell or Rockwelll Collins. 01Dec2014: Provided with item 4
12 | Airframer to confirm if they support the APIM | Airbus, Boeing, Embraer | Airbus, Boeing, Embraer | 2014-06-25 | Closed
13 | Update APIM with 25june14 WebEx suggestions | Jessie Turner | The Boeing Company | 2014-06-25 | Closed
14 | Schedule Next Online Conference | Jose Godoy | ARINC IA | 2014-06-25 | Closed 21May14 | Tentatively scheduled for 22July2014
15 | Schedule Next Online Conference | Jose Godoy | ARINC IA | 2014-07-22 | Closed | Scheduled for 01Dec2014
16 | Jessie to mark-up Label 352 (proposal provided by ACSS) and submit to group | Jessie Turner | The Boeing Company | 2014-12-01 | Closed on 01Dec14 | Jose to distribute/post on SharePoint site. Comments will be emailed to leadership team and discussed during 06Jan2015 Online Conference
17 | Jose Godoy to load documents into SharePoint site | Jose Godoy | ARINC IA | 2014-12-01 | Closed
18 | Working Group to review Discrete information submitted by Rockwell Collins | Traffic and Surveillance Work Group | Traffic and Surveillance Work Group | 2014-12-01
19 | Kevin to mark up Discrete Word 364/365 (originally provided by randy (RC) | Kevin Wilson | Honeywell | 2014-12-01 | Closed on 01Dec2014 | Jose to distribute/post on SharePoint site. Comments will be emailed to leadership team and discussed during 06Jan2015 Online Conference
20 | Complete Draft 1 of A735B-2 | Traffic and Surveillance Work Group | Traffic and Surveillance Work Group | 2014-12-01 | 2015-01-21 | 07Jan2015: Revised for 21Jan 2015
21 | Post A735B D1S2 | Jose Godoy | ARINC IA | 2014-12-01 | 2015-01-28 | 07Jan2015: Revised for 21Jan 2015
22 | Schedule Next Online Conference | Jose Godoy | ARINC IA | 2014-12-01 | Closed on 01Dec14 | Scheduled for 06Jan2015
23 | Jessie to update ACSS document with Boeing markups, per 07Jan15 online conference | Jessie Turner | The Boeing Company | 2015-01-07 | Closed on 07Jan15
24 | Kevin to update Discrete, per 07Jan15 online conference | Kevin Wilson | Honeywell | 2015-01-07 | Closed on 07Jan15
25 | Jose Godoy to load updated documents into SharePoint site and distribute | Jose Godoy | ARINC IA | 2015-01-07 | Closed on 07Jan15
26 | Determine what to do with unused pins for coding perpuse. i.e, Label 365 pin 14 | Jose Godoy | ARINC IA | 2015-01-07
27 | Schedule Next Online Conference | Jose Godoy | ARINC IA | 2015-01-07 | Closed on 07Jan15 | Scheduled for10Feb2015
| Complete mature A735B-2 draft | Traffic and Surveillance Work Group | Traffic and Surveillance Work Group | 2015-01-07 | 2015-03-02 | Required date for submittal for adoption consideration by ExCom at 2015 AEEC General Session
| Post A735B S2 mature draft | Jose Godoy | ARINC IA | 2015-01-07 | 2015-03-13 | Required date for submittal for adoption consideration by ExCom at 2015 AEEC General Session
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72