## Sheet1
# | Source | Entry Date | Action | Status | Assignee(s) | Discussion | Due Date
1 | Committee | 2020-04-01 | Propose whether program pins will be supported in A768A | Closed | Seth Cooper | 9/22/20 - OEMs only require one SDI pin. Will continue to reserve 11 pins total. 8/29/20- 2 SDI and 9 'program' pins to be supported 8/4/20 - Agreed to utilize 9 pins. A768A draft needs to be updated with content. 6/9/20 - Majority of the PP will be handled through Soft PP option. There is a need for A/C configuration hardware PP. Baseline (i.e. range should need to be defined) needs to be defined however, specific will be handled by OEM level. Industry Editor to propose. | 2020-09-01
2 | Committee | 2020-04-01 | Propose CyberSecurity references and language | Closed | Garmin | 12/10/20 - Update per bullet points from Boeing Presentation 6/9/20 - Section 3.10 has been added to draft along with related references. Committee needs to review draft section. | 2020-01-15 | Can delay due date?
3 | Committee | 2020-04-01 | Propose EWIS applicability and usage for A768A | Closed | Garmin | 9/1/20 - Garmin will add statement on EWIS to the document and commentary that assessment is done on the regs as they exist. The regs may change and EWIS will need to be reevaluated at time of cert. Leverage Bill's document 8/4/20 - Bill took the action to review and provide input to the committee. 6/9/20 - Spec needs to comply with EWIS 25.1701 as a requirement. Owner for action needs to be identified to determine, and propose if needed, any updates to the spec to comply. | 2020-09-22
4 | Committee | 2020-04-01 | Create drawings for omnidirectional antenna in attachment 3B and include placement and isolation guidance. | Open | Mohammed Ahmed | 9/30/20 - Merged in AI #10 about isolation guidance. 9/16/20 - Mohammed to propose specific Antenna drawings and content to be included in A768A. 9/1/20 - Larry to provide source conent for Antenna drawings and attachments to include in A768A draft. Garmin will include antenna drawings, installation drawings, and isolation drawings from existing standards 8/4/20 - ARINC 718 and ARINC 735 have references for the antennas that can be used in the A768A draft. 6/9/20 - Owner needs to be identified to create drawings. | 2020-09-22 | Need to resync on assignee and due date?
5 | Committee | 2020-04-01 | Assess power supply and wiring interfaces for 28VDC | Closed | Seth Cooper | 6/9/20 - Update to 28VDC with a single power input per LRU. | 2020-11-01
6 | Committee | 2020-04-01 | Assess and propose requirements for function during loss of inflight cooling and for how long | Closed | Garmin | 12/10/20 - Update Loss of Cooling section- <time limit> at 40 deg C without loss of functionality; shall not cause any loss of function. Add notes? May be required 65 deg C in some installations? "Consideration of cooling required may be specific to airframe requirements"? 9/22/20 - Airbus specifies 20 hours after loss of cooling with requirement for Transponder, ADS-B Out, TCAS. Max temp after loss is +65C for a composite airframe. Boeing requires DME, TAWS, and ADS-B IN for last 30 minutes of flight. 9/1/20 - Airbus and Boeing agree to provide environment and performance requirements for the 2GISS "beyond DO-160" for loss of cooling Prior notes deleted. See previous versions for more history | 2020-01-15 | Can delay due date?
7 | Committee | 2020-06-09 | Assess whether new Equipment ID/Index Code needed for 2GISS (currently is 158) | Closed | Garmin | 9/1/20 - Garmin will use the equipment code ID already in the standard based on different size unit. Retain Code 158 and update document. Larry and Paul agree code reuse is acceptable. 6/9/20 - Section 2.2.1 identifies an index code of #158 based on A768 spec. Paul to confirm if this can be reused for A768A as well. | 2020-09-22
8 | Committee | 2020-04-01 | Propose removal of material that exists/will exist in referenced ARINC Standards (mostly A718A and A735C) | Open | Garmin |  | 2020-11-01
9 | Committee | 2020-04-01 | Propose the 2GISS annunciations that need to be specified in 2GISS | Open | Committee | 7/1/20 - Current action is for committee to review those proposed in the draft. | 2020-09-09
10 | Committee | 2020-04-01 | Propose antenna isolation guidance | Closed | Mohammed Ahmed | 9/30/20 - Closing due to merging with AI #4 9/16/20 - Mohammed to propose specific Antenna drawings and content to be included in A768A. | 2020-09-01
11 | Committee | 2020-04-01 | Propose DME functional test guidance | Closed | Randy Jacobson | 3/12/21 - Randy took this task | 2020-09-01
12 | Committee | 2020-04-01 | Suppression bus trade-offs | Closed | Boeing | 8/4/20 - Obsolete and closed | 2020-09-01
13 | Committee | 2020-04-01 | I/O list (audio) | Closed | OEM | 8/4/20 - Obsolete and closed per AI #24. | 2020-09-01
14 | Committee | 2020-04-01 | I/O list (optical) | Open | OEMs Fiber Optic A664 WG | 4/1/22 - New Fiber APIM active. Action still to Airbus to determine whether they want copper, which Tim thinks means a unique insert. Action to OEMs to agree on uni-directional versus bidirectional Fiber channels. 7/25/21 - New APIM to address common physical interface for Aircraft Data Network. 4/9/21 - Mohammed/Andre to meet with A664 Committee week of 4/12/21 to confirm wavelength. 3/15/21 - Need wavelength spec from Mohammed and Andre; Boeing's Bob Nigh 12/10/20 - Garmin to investigate ARINC 600 inserts (Quadrax v. Coax) and propose. Also awaiting XT/TX resolution to confirm intra-unit connection. 11/18/20 - Airlines wans fiber at top to keep debris from falling from copper connections dropping wear shavings onto glass below 9/22/20 - OEMs have identified potential suppliers and will arrange a presentation/training for the committee 9/1/20 - Airbus and Boeing agree to provide Optical I/O Specifications 7/15/20 - This will impact the bottom plug selection based on which Fiber connectors are required. 7/14/20 - Mohammed confirmed that between Airbus and Boeing the 2GISSPU will be going to use a Fiber Optic A664 interface. Boeing has the action to specify the A80X interface standards for the interface (i.e. connectors). | 2021-01-15 | Check 11/18 and 12/10 notes. Revise Action title to reflect connector as well as I/O list?
15 | SAE | 2020-03-17 | Standards updates and callouts | Open | Garmin | Maintained while working through draft, but won't be closed until completion. | 2021-01-01
16 | American Airlines | 2020-06-09 | Control Panel Definition - Soft/Display Control Panel, Back-up Secondary Control Panel, and Physical Control Panels if considered. | Closed | OEM | 2/9/2021 - A comment was raised in committee to consider inviting someone from the FAA to provide input on display/control considerations for the standard. 6/9/20 - A harmonized control panel approach for training, both HW/Physical and SW/A661 controls, be coordinated as part of the standard. | 2020-09-01
17 | Industry Editor | 2020-07-03 | Spelling and grammar updates | Open | Garmin | To be completed last. | 2021-01-01
18 | Committee | 2020-06-09 | Antenna reference alignment - Clarifying that there are two antennas, a Top Directional and a Bottom Omni-Directional. | Closed | Seth Cooper | 8/17/20 - Proposed wording added. | 2020-11-01
19 | Industry Editor | 2020-06-09 | Terrain Display definition - Section 3.5.2 scope | Open | Garmin |  | 2020-09-01
20 | Industry Editor | 2020-06-09 | Display interface - Section 3.7.1.1 identifies an ARINC818 interface, is that expected? | Closed | Committee | 8/17/20 - Proposed wording added. | 2020-09-01
21 | Industry Editor | 2020-06-09 | Section 3.7.1.8 - Identify cross side 2GISS control/data architecture and coordination for ACAS-X and cross-side transponder (possibly non-2GISSPU Transponder). Airbus and Boeing will provide: -Expected data flow diagram -Expected control architecture (Master/Slave?) for all functions -Reversionary modes for data flow -Reversionary modes for control -ARINC 664 Protocol: A429 labels over network? Something else? | Closed | OEM | 11/18/20 - Master/Slave architecture proposed by Airbus. Action to Airbus to specify dataflows in such installations 9/22/20 - XT-TX (ARINC 735) over direct A429 link is only way to meet timing requirements. Boeing prefers AFDX, but suppliers do not think timing requirements can be met via AFDX. Closing. 9/1/20 - OEMs to provide sample expected installations to support (e.g. Dual 2GISS with single directional antenna, Single 2GISS with cross-side XPDR, etc…) 8/17/20 - Proposed wording added. | 2020-01-15 | Revise action title? Anything else?
22 | July 14/5th Meeting | 2020-07-14 | Remove A818 references as this won't be required (i.e. Sec 3.7) | Closed | Seth Cooper | 8/17/20 - Proposed wording added. 7/14/20 - Decision was made to not include a standalone Fiber Optic (A818) video interface for the 2GISS. | 2020-09-01
23 | July 14/5th Meeting | 2020-07-14 | Confirm Single ARINC 664 Fiber Optic interface bandwidth will be acceptable for the 2GISS functions and expected forward Growth requirements. | Closed | OEM | 8/4/20 - Addressed by AI#14. 7/14/20 - Concern was raised related to the amount of functionality being driven into a single LRU and the expectation for future-growth support and whether a dual A664 network connection would be more appropriate. This would aid in A661/Display changes and the potential increase to network data to support these for functionality such as TAWS layers on Moving Maps, Vertical Displays, possibly Synthetic Vision overlays, etc on multiple displays. | 2020-09-01
24 | July 14/5th Meeting | 2020-07-15 | Confirmation that a single Audio output for combined TAWS/TCAS alerts and a single Audio output for DME audio is acceptable. | Closed | Airbus | 9/22/20 - Airbus confirms one analog audio output for alerts, one for DME station identification. Closing. 9/1/20 - Airbus to confirm proposed audio before next meeting 7/15/20 - Concern was identified that with only a single DME audio output this may reduce deferred dispatchability of a 2G ISS system. Also, need to recognize that this may limit installations and that should be captured within the specification (this installation would be focused on FWD-Fit). -> Boesing - Prefers 1-TCAS/TAWS Alerts and 1-DME Audio as they prefer digital installs and a FWD-Fit solution only. -> Airbus - Is about 90% confident with this same approach, but has the action to confirum. | 2020-09-22
25 | July 14/5th Meeting | 2020-07-15 | Confirm Backup control path (A429 Rx/Tx) paths for Transponder and DME - Need to specify backup control functionality and architecture. | Closed | OEM | 9/22/20 - OEMs confirmed one A429 input for backup Mode A control, one A429 output to echo back. Closing. 7/15/20 - OEMs need to confirm: -> DME needs only a single backup A429 Rx/Tx -> XPDR needs only Mode-A a single backup A429 Rx/Tx OEMs will provide an architecture to confirm and finalize a consolidated/single architecture. | 2020-09-22
26 | July 14/5th Meeting | 2020-07-15 | Confirm that 2-SDI pins are required. | Closed | Committee | 9/22/20 - OEMs confirm only one SDI pin required. 8/4/20 - Addressed by AI#1. 7/15/20 - OEMs to confirm that two SDI pins are required as the committee identified an opportunity to reduce the number of SDI pins to 1-SDI pin. Suppliers to confirm that reliability isn't negatively impacted/reduced by moving to 1-SDI pin. | 2020-09-01
27 | July 14/5th Meeting | 2020-07-15 | Propose a "Network Identification Pin" approach that combines, but reduces, the number of Program Pins and SDI pins to enable a 2GISS to identify a 2GISSPU uniquely for the connected network. | Closed | Garmin | 8/4/20 - Addressed by AI#1. 7/15/20 - Discussion related to network identification in a unique but reliable way. Possibly just a simple look-up table with monitoring for the power-up sequence of a 2GISSPU. | 2020-09-01
28 | July 14/5th Meeting | 2020-07-15 | Review Shield-paths, Return-paths,… for minimized loops on middle plug wiring. | Closed | Garmin | 9/30/2020 - Middle plug signals balanced and likely sheilded. Sufficient grounds for discretes and reserved. Can't find precendent for shield termination pins in A768 or A735. ARINC 600 backshells accomodate shield termination. Curious what committee wants to do. Recommend closing. 9/21/2020 - Garmin confirmed there is no DO-160 committee guidance for shielding termination. 9/1/20 - Airbus/Boeing to review internal guidance on sheild terminations. Garmin to consult DO-160 committee on sheilding termination guidance. | 2020-09-22 | Any update needed?
29 | July 14/5th Meeting | 2020-07-15 | Clean-up I/O spreadsheet/diagram to show the Size 2 connector and currently desired plugs. | Closed | Garmin | 7/15/20 - Updated reference material to aid discussion related to I/O. Incorporate all of Tim's notes and upload update | 2020-08-01
30 | July 14/5th Meeting | 2020-07-15 | Update A768A draft to identify the need for a "coherent" A743 data packet being received over A664. This should include references to latency related data for ADS-B In/Out requirements. | Closed | Garmin | 8/17/20 - Proposed wording added. 7/15/20 - Need to capture the need for data coherency to be maintained for related PVT data. This should include latency related requirement references for ADS-B IN/OUT functions. | 2020-09-01
31 | July 14/5th Meeting | 2020-07-15 | RF Spoofing requirements can be removed for TCAS XPDR Security. Indicate that security considerations continue throughout the design and life cycle of the unit. | Closed | Garmin | 8/29/20- Updated per 7/15/20 input 7/15/20 - Refer to the security MOPS to indicate they are required reading. Ensure that security maintenance is a requirement. | 2020-09-01
32 | July 14/5th Meeting | 2020-07-15 | OEM security experts will review security section of ARINC768A draft | Closed | OEM | 11/18/2020 - OEM feedback provided. AI#2 reopened to revise per feedback. AI closed. | 2020-09-01
33 | July 14/5th Meeting | 2020-07-15 | Investigate Loss of cooling, can we reduce nominal cerified functionality, e.g. load shedding without a deviation needed from cert authorities | Closed | Garmin | 8/4/20 - Addressed by AI#6. | 2020-09-01
34 | Dec 10 Meeting | 2020-12-10 | At AEEC Council meeting, present questions to airlines to better understand their intent/need for 2GISS. | Closed | OEM | 12/10/2020 - Try to get answers: What configurations does the market want? Newer aircraft, supporting updated existing airplanes? Airlines needs and preferences? What options are viable for the airlines? | ?? | New action. When was meeting?
35 | Industry Editor | 2021-03-11 | Propose language indicating that shared antennas are not recommended for 2GISSPU units. Commentary added to 1.4.4 to be reviewed by committee | Closed | Committee
36 | Committee | 2021-03-15 | Add language addressing return to service concerns | Closed | Tim Gibson
37 | Committee | 2021-04-09 | Add language to standard defining spare, supplier reserved, and provisional. | Closed | Tim Gibson | 4/9/21 - Need to add common terminology for specifying supplier vs OEM vs standard use of pins. | 2021-04-23
38 | Industry Editor | 2021-05-24 | Add Notes on NVM fault logging and general what data lives where in the fault log strategy, notes | Closed | Tim Gibson |  | 2021-06-11
39 | Industry Editor | 2021-07-21 | Define format/source for airport map data and approach data. These are required for use by TAWS-A in terminal environment. ARINC 816 can be used for an airport map database, but does not include needed approach data. Committee to recommend how to handle this. | Open | Committee
40 | Industry Editor | 2022-02-04 | Need to identify a schema for how Network ID codes are going to be allocated within the Pinout definition. | Open | Garmin | 4/1/22 - Randy presented his proposal in meeting. There were no objections to the approach as presented. Sam B will send to committee. A means of allocating blocks still needs to be worked out. Boeing and Airbus to confirm that 128 states is adequate for each of them. 2/7/22 - Randy Jacobson provided suggested block allocation scheme that can be reviewed in committee 2/4/22 - Boeing and Airbus to identify/determine codes to be used with allocation for spares for other OEMs.
41 | Industry Editor | 2022-02-04 | Wiring/pinout review for signal segregation and layout for the pinout. | Open | Airbus | 2/4/22 - Review pinout and provide recommendations for specific segregation and organization expectations.
42 | Industry Editor | 2022-02-04 | Identify any limitations on supplier reserved interfaces due to Security needs of OEMs (e.g. ethernet on Supplier reserved pins). | Open | Boeing | 4/1/22 - Need to understand the security measure expectations for such interfaces. They are needed to log data for certification. 2/4/22 - OEMs may require physical access to unit as an attack vector to consider in security analyses, which may result in restriction on digital interfaces.